## Sources & Method
00 ¦ METHODOLOGY & SOURCES
Reference / Topic | Details | Source / Link | Status
Jira baseline | 4 Epics, 17 Stories, 6 Tasks, 117 Subtasks; 110 Done, 3 In Progress, 4 To Do. | Ako_Project.xlsx | Project source
Subtask normalisation | Different decomposition granularity; reference mean 68/15=4.53, approximately 77 equivalent subtasks. | Jira export / project estimation convention | Assumption
Labour estimation | 260 hours allocated by activity; not directly recorded worklogs. | Labour Cost sheet | Planning estimate
Labour rate benchmarks | Rates NZ$75–110/h are budget inputs pending market-source verification. | https://www.h2r.co.nz/h2r-consulting/services/contractors/salary-vs-hourly-rate/contractor-hourly-rate-guide/ | Market reference
Additional rate benchmark | New Zealand salary guide reference; verify comparable hourly contract basis. | https://www.betterworldofwork.io/more-than-money/search-salaries | Market reference
Laptop depreciation | Straight-line 36-month allocation; 0.75 month approximates 3 weeks. | Assumptions sheet | Assumption
Cash vs economic cost | Student labour is valued economically; not treated as paid wages. | Cost Summary and Resources | Method
Contingency | 10% of base economic development cost. | Assumptions sheet | Assumption
Sensitivity | ±10% labour hours or hourly rates; other costs unchanged. | Sensitivity sheet | Scenario

## Assumptions
01 ¦ MODEL ASSUMPTIONS
Input | Value | Unit / Definition | Basis / Source
Team members | 4 | people | Project team / Jira context
Project duration | 3 | weeks | Project planning assumption
Normalised subtask count | 77.07 | equivalent subtasks | Jira Oct 27 16:30; reference average 4.53
Reference subtasks per story | 4.53 | subtasks/story | Other 15 stories: 68 / 15
Requirements hourly rate | 95 | NZD/hour | H2R Technology — Business Analyst
Management hourly rate | 100 | NZD/hour | H2R Technology — IT Project Manager
Architecture hourly rate | 110 | NZD/hour | H2R Technology — IT Architect
Development hourly rate | 100 | NZD/hour | H2R Technology — Web Developer
Testing hourly rate | 95 | NZD/hour | H2R Technology — Testing / QA
Documentation hourly rate | 75 | NZD/hour | Better World of Work — Technical Writer
Laptop value | 2000 | NZD/device | Planning assumption
Laptop life | 36 | months | Straight-line allocation assumption
Project laptop allocation | 0.75 | months | Approximation for three-week project
Home office allocation | 15 | NZD/member/week | Planning assumption
Electricity allocation | 2 | NZD/member/week | Planning assumption
Internet allocation | 3 | NZD/member/week | Planning assumption
Contingency rate | 0.1 | fraction of base cost | Budget policy assumption
Effort sensitivity | 0.1 | fraction | Scenario assumption

## Jira Workload
02 ¦ JIRA WORKLOAD BASELINE
Metric | Count | Treatment / Notes | Source
Epics | 4 | Scope grouping only | Jira export
Stories | 17 | Functional scope | Jira export
Tasks | 6 | Planning and project setup | Jira export
Subtasks | 117 | Raw issue count | Jira export
Subtasks Done | 110 | Status at export | Jira export
Subtasks In Progress | 3 | Status at export | Jira export
Subtasks To Do | 4 | Status at export | Jira export
Subtasks linked to Stories | 116 | One subtask not linked to Story | Jira export
Reference Stories | 15 | Excludes exceptionally granular decomposition | Jira normalisation calculation
Reference linked Subtasks | 68 | Reference sample for normalisation | Jira normalisation calculation
Average Subtasks per Story | 4.53 | Reference sample average | Calculated
Normalised equivalent Subtasks | 77 | Comparable workload indicator; not hours | Calculated
Recorded Worklogs | 0 | Hours not available; estimates used | Jira export

## Labour Cost
03 ¦ LABOUR COST ESTIMATE
Activity | Jira / Workstream | Hours | Rate (NZD/h) | Cost (NZD) | Basis
Requirements Analysis | AKO-26 — Requirements and acceptance criteria | 15 | 95 | 1425 | Activity estimate; Jira-linked where applicable
Requirements Analysis | AKO-28 — MVP scope and prioritisation | 10 | 95 | 950 | Activity estimate; Jira-linked where applicable
Requirements Analysis | Stakeholder discussions and requirements refinement | 10 | 95 | 950 | Activity estimate; Jira-linked where applicable
Project Management | AKO-27 — Jira setup and backlog | 10 | 100 | 1000 | Activity estimate; Jira-linked where applicable
Project Management | AKO-29 — Sprint planning and responsibilities | 8 | 100 | 800 | Activity estimate; Jira-linked where applicable
Project Management | Sprint coordination, reviews and meeting records | 12 | 100 | 1200 | Activity estimate; Jira-linked where applicable
Architecture | AKO-30 — Technical architecture | 10 | 110 | 1100 | Activity estimate; Jira-linked where applicable
Architecture | AKO-31 — Repository and development workflow | 5 | 110 | 550 | Activity estimate; Jira-linked where applicable
Architecture | Database, RBAC, UML and UI design | 20 | 110 | 2200 | Activity estimate; Jira-linked where applicable
Development | AKO-8/9 — Authentication and staff accounts | 16 | 100 | 1600 | Activity estimate; Jira-linked where applicable
Development | AKO-10/12/13/22/23 — Learners and attendance | 22 | 100 | 2200 | Activity estimate; Jira-linked where applicable
Development | AKO-11 — Class sessions | 8 | 100 | 800 | Activity estimate; Jira-linked where applicable
Development | AKO-14/16/21 — Lesson library and shared materials | 20 | 100 | 2000 | Activity estimate; Jira-linked where applicable
Development | AKO-15 — Māori content review | 6 | 100 | 600 | Activity estimate; Jira-linked where applicable
Development | AKO-17/18 — Club information and enquiries | 10 | 100 | 1000 | Activity estimate; Jira-linked where applicable
Development | AKO-19/20 — QR attendance functions | 8 | 100 | 800 | Activity estimate; Jira-linked where applicable
Development | AKO-24 — CSV learner import | 6 | 100 | 600 | Activity estimate; Jira-linked where applicable
Development | Cross-feature debugging and adjustments | 4 | 100 | 400 | Activity estimate; Jira-linked where applicable
Testing | Test planning and acceptance test design | 10 | 95 | 950 | Activity estimate; Jira-linked where applicable
Testing | Unit and functional testing | 12 | 95 | 1140 | Activity estimate; Jira-linked where applicable
Testing | Integration and acceptance testing | 9 | 95 | 855 | Activity estimate; Jira-linked where applicable
Testing | Regression testing and defect verification | 4 | 95 | 380 | Activity estimate; Jira-linked where applicable
Documentation | Technical and project documentation | 12 | 75 | 900 | Activity estimate; Jira-linked where applicable
Documentation | Project report preparation | 8 | 75 | 600 | Activity estimate; Jira-linked where applicable
Documentation | Presentation and delivery preparation | 5 | 75 | 375 | Activity estimate; Jira-linked where applicable
TOTAL LABOUR |  | 260 |  | 25375

## Resources
04 ¦ ALLOCATED RESOURCES
Resource | Units / People | Unit Cost / Rate | Duration / Basis | Cost (NZD) | Calculation Note
Laptops | 4 | 2000 | 0.75 | 166.67 | 4 × laptop value ÷ useful life × allocation months
Home office | 4 | 15 | 3 | 180 | 4 members × weekly allocation × 3 weeks
Electricity | 4 | 2 | 3 | 24 | 4 members × weekly allocation × 3 weeks
Internet | 4 | 3 | 3 | 36 | 4 members × weekly allocation × 3 weeks
Cloud hosting | 1 | 0 | 1 | 0 | No paid hosting assumed
TOTAL RESOURCES |  |  |  | 406.67

## Tools
05 ¦ SOFTWARE & TOOL COSTS
Tool | Purpose | Cost (NZD) | Licence / Assumption
Jira Free | Agile project management | 0 | Free/open-source or no additional licence cost
GitHub Free | Version control | 0 | Free/open-source or no additional licence cost
Visual Studio Code | Development environment | 0 | Free/open-source or no additional licence cost
Microsoft Teams | Communication | 0 | Free/open-source or no additional licence cost
Next.js | Frontend framework | 0 | Free/open-source or no additional licence cost
React | UI development | 0 | Free/open-source or no additional licence cost
FastAPI | Backend API | 0 | Free/open-source or no additional licence cost
PostgreSQL | Database | 0 | Free/open-source or no additional licence cost
Docker | Containerised development | 0 | Free/open-source or no additional licence cost
Nginx | Web server and routing | 0 | Free/open-source or no additional licence cost
TOTAL TOOLS |  | 0

## Cost Summary
06 ¦ PROJECT COST SUMMARY
Category | Cost (NZD) | Share of Base | Interpretation
Labour | 25375 | 98.42% | Market-valued development effort
Tools | 0 | 0% | Free and open-source software
Resources | 406.67 | 1.577% | Allocated equipment and household resources
BASE DEVELOPMENT COST | 25781.67 |  | Economic cost excluding reserve
Contingency (10%) | 2578.17 |  | Budget allowance, not incurred expenditure
TOTAL PROJECT BUDGET | 28359.84 |  | Base cost plus contingency
Labour activity | Cost (NZD)
Requirements Analysis | 3325
Project Management | 3000
Architecture | 3850
Development | 10000
Testing | 3325
Documentation | 1875

## Sensitivity
07 ¦ COST SENSITIVITY
Scenario | Labour Multiplier | Labour Cost (NZD) | Base Cost (NZD) | Budget with 10% Reserve
Low (−10%) | 0.9 | 22837.5 | 23244.17 | 25568.587
Base | 1 | 25375 | 25781.67 | 28359.837
High (+10%) | 1.1 | 27912.5 | 28319.17 | 31151.087
The same scenarios apply to proportional hourly-rate changes with hours held constant.