## All Issues
Key | Type | Summary | Status | Assignee | Reporter | Parent | Created | Updated | Resolved | Story Points
AKO-4 | Subtask | Subtask 2.1 | Done |  | Huanchen Wu |  | 2026-10-13T22:00:06.616+1300 | 2026-10-29T14:05:05.273+1300 | 2026-10-29T14:05:05.251+1300
AKO-5 | Epic | [EP-01]Accounts and Access | Done |  | Huanchen Wu |  | 2026-10-16T15:33:53.720+1300 | 2026-10-29T14:05:03.246+1300 | 2026-10-29T14:05:03.222+1300
AKO-6 | Epic | [EP-02]Learners and Attendance | Done |  | Huanchen Wu |  | 2026-10-16T15:33:54.998+1300 | 2026-10-29T14:05:01.310+1300 | 2026-10-29T14:05:01.288+1300
AKO-7 | Epic | [EP-03]Lesson Library | Done |  | Huanchen Wu |  | 2026-10-16T15:33:55.711+1300 | 2026-10-29T14:04:59.284+1300 | 2026-10-29T14:04:59.261+1300
AKO-8 | Story | US-001 Log in by role | Done | Huanchen Wu | Huanchen Wu | AKO-5 | 2026-10-16T15:53:20.489+1300 | 2026-10-23T21:31:36.496+1300 | 2026-10-23T21:31:36.481+1300
AKO-9 | Story | US-002 Manage staff accounts | Done | Huanchen Wu | Huanchen Wu | AKO-5 | 2026-10-16T15:53:21.359+1300 | 2026-10-24T09:18:48.783+1300 | 2026-10-24T09:18:48.761+1300
AKO-10 | Story | US-003 Keep learner records | Done | Pei Wu | Huanchen Wu | AKO-6 | 2026-10-16T15:53:22.087+1300 | 2026-10-23T12:48:58.965+1300 | 2026-10-23T12:48:58.949+1300
AKO-11 | Story | US-014 Manage class sessions | Done | Shuohui Liu | Huanchen Wu | AKO-6 | 2026-10-16T15:53:22.714+1300 | 2026-10-26T13:03:36.291+1300 | 2026-10-26T13:03:36.270+1300
AKO-12 | Story | US-004 Record attendance by hand | Done | Pei Wu | Huanchen Wu | AKO-6 | 2026-10-16T15:53:23.357+1300 | 2026-10-23T14:06:07.611+1300 | 2026-10-23T14:06:07.588+1300
AKO-13 | Story | US-005 Print attendance record | Done | Shuohui Liu | Huanchen Wu | AKO-6 | 2026-10-16T15:53:24.018+1300 | 2026-10-26T18:41:18.458+1300 | 2026-10-26T18:41:18.436+1300
AKO-14 | Story | US-006 Create a lesson | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-7 | 2026-10-16T15:53:24.638+1300 | 2026-10-26T18:41:58.460+1300 | 2026-10-26T18:41:58.439+1300
AKO-15 | Story | US-008 Flag Māori content for review | Done | Pei Wu | Pei Wu | AKO-7 | 2026-10-16T15:53:25.272+1300 | 2026-10-26T20:22:29.576+1300 | 2026-10-26T20:22:29.555+1300
AKO-16 | Story | US-007 Find and copy lessons | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-7 | 2026-10-19T18:09:13.112+1300 | 2026-10-26T18:41:45.565+1300 | 2026-10-26T18:41:45.540+1300
AKO-17 | Story | US-009 View club information | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-25 | 2026-10-19T18:09:14.257+1300 | 2026-10-26T21:22:16.602+1300 | 2026-10-26T21:22:16.586+1300
AKO-18 | Story | US-010 Register interest in classes | Done | Huanchen Wu | Huanchen Wu | AKO-25 | 2026-10-19T18:09:15.058+1300 | 2026-10-26T14:30:26.297+1300 | 2026-10-26T14:30:26.275+1300
AKO-19 | Story | US-011 Open check-in with a QR code | Done | Shuohui Liu | Huanchen Wu | AKO-6 | 2026-10-19T18:09:15.818+1300 | 2026-10-26T21:22:10.867+1300 | 2026-10-26T21:22:10.842+1300
AKO-20 | Story | US-012 Sign in by scanning the QR code | Done | Pei Wu | Huanchen Wu | AKO-6 | 2026-10-19T18:09:16.606+1300 | 2026-10-25T16:43:55.187+1300 | 2026-10-25T16:43:55.162+1300
AKO-21 | Story | US-013 Access shared lesson materials after signing in | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-7 | 2026-10-19T18:09:17.374+1300 | 2026-10-25T19:23:26.960+1300 | 2026-10-24T18:25:26.171+1300
AKO-22 | Story | US-015 Correct a past attendance record | Done | Pei Wu | Pei Wu | AKO-6 | 2026-10-19T18:09:18.090+1300 | 2026-10-25T21:35:21.815+1300 | 2026-10-25T21:35:21.799+1300
AKO-23 | Story | US-016 View a learner's attendance history | Done | Shuohui Liu | Huanchen Wu | AKO-6 | 2026-10-19T18:09:18.822+1300 | 2026-10-27T09:20:18.034+1300 | 2026-10-27T09:20:18.013+1300
AKO-24 | Story | US-017 Import learners from a CSV file | Done | Huanchen Wu | Huanchen Wu | AKO-6 | 2026-10-19T18:09:19.556+1300 | 2026-10-27T16:03:33.959+1300 | 2026-10-27T16:03:33.942+1300
AKO-25 | Epic | [EP-04]Public page and promotion | Done |  | Huanchen Wu |  | 2026-10-19T18:15:02.301+1300 | 2026-10-29T14:04:57.453+1300 | 2026-10-29T14:04:57.431+1300
AKO-26 | Task | T-001 Finalise project requirements and acceptance criteria | Done | Pei Wu | Huanchen Wu |  | 2026-10-19T20:22:17.244+1300 | 2026-10-19T20:24:49.575+1300 | 2026-10-19T20:24:29.340+1300
AKO-27 | Task | T-002 Configure Jira Scrum project and backlog | Done | Huanchen Wu | Huanchen Wu |  | 2026-10-19T20:22:18.162+1300 | 2026-10-19T20:24:59.437+1300 | 2026-10-19T20:24:56.883+1300
AKO-28 | Task | T-003 Define MVP scope and prioritise user stories | Done | Sandhya Tiwari | Sandhya Tiwari |  | 2026-10-19T20:22:18.842+1300 | 2026-10-25T19:21:36.074+1300 | 2026-10-19T20:25:46.182+1300
AKO-29 | Task | T-004 Prepare Sprint plan and team responsibilities | Done | Huanchen Wu | Huanchen Wu |  | 2026-10-19T20:22:19.495+1300 | 2026-10-19T20:25:48.058+1300 | 2026-10-19T20:25:48.035+1300
AKO-30 | Task | T-005 Document technical architecture and technology choices | Done | Shuohui Liu | Huanchen Wu |  | 2026-10-19T20:22:20.134+1300 | 2026-10-19T20:25:49.952+1300 | 2026-10-19T20:25:49.931+1300
AKO-31 | Task | T-006 Establish GitHub repository and collaboration rules | Done | Shuohui Liu | Huanchen Wu |  | 2026-10-19T20:22:20.984+1300 | 2026-10-19T20:25:51.937+1300 | 2026-10-19T20:25:51.916+1300
AKO-32 | Subtask | Review Existing Authentication and Design RBAC Database Schema | Done | Huanchen Wu | Huanchen Wu | AKO-8 | 2026-10-21T20:11:30.487+1300 | 2026-10-23T16:46:50.466+1300 | 2026-10-23T16:46:50.451+1300
AKO-33 | Subtask | Define RBAC Roles, Permissions and Cross-Service Authorization | Done | Huanchen Wu | Huanchen Wu | AKO-8 | 2026-10-21T20:11:31.761+1300 | 2026-10-23T16:46:54.286+1300 | 2026-10-23T16:46:54.266+1300
AKO-34 | Subtask | Enhance Authentication and Implement Account Lockout | Done | Huanchen Wu | Huanchen Wu | AKO-8 | 2026-10-21T20:11:32.740+1300 | 2026-10-23T16:47:16.020+1300 | 2026-10-23T16:47:16.005+1300
AKO-35 | Subtask | Implement Secure Server-Side Session Management | Done | Huanchen Wu | Huanchen Wu | AKO-8 | 2026-10-21T20:11:33.565+1300 | 2026-10-23T21:31:19.692+1300 | 2026-10-23T21:31:19.677+1300
AKO-36 | Subtask | Integrate Role-Based Login UI and Protected Navigation | Done | Huanchen Wu | Huanchen Wu | AKO-8 | 2026-10-21T20:11:34.498+1300 | 2026-10-23T21:31:25.874+1300 | 2026-10-23T21:31:25.851+1300
AKO-37 | Subtask | Test Authentication, RBAC and Multi-Instance Sessions | Done | Huanchen Wu | Huanchen Wu | AKO-8 | 2026-10-21T20:11:35.828+1300 | 2026-10-23T21:31:29.859+1300 | 2026-10-23T21:31:29.844+1300
AKO-38 | Subtask | Design Staff Management APIs and Data Validation | Done | Huanchen Wu | Huanchen Wu | AKO-9 | 2026-10-21T20:11:45.697+1300 | 2026-10-29T13:59:13.716+1300 | 2026-10-29T13:59:13.701+1300
AKO-39 | Subtask | Implement Teacher Account Creation and Role Assignment | Done | Huanchen Wu | Huanchen Wu | AKO-9 | 2026-10-21T20:11:46.582+1300 | 2026-10-29T13:59:17.175+1300 | 2026-10-29T13:59:17.154+1300
AKO-40 | Subtask | Implement Staff Update, Deactivation and Coordinator Protection | Done | Huanchen Wu | Huanchen Wu | AKO-9 | 2026-10-21T20:11:47.545+1300 | 2026-10-29T13:59:19.554+1300 | 2026-10-29T13:59:19.537+1300
AKO-41 | Subtask | Develop Coordinator Staff Management UI | Done | Huanchen Wu | Huanchen Wu | AKO-9 | 2026-10-21T20:11:48.413+1300 | 2026-10-29T13:59:21.521+1300 | 2026-10-29T13:59:21.500+1300
AKO-42 | Subtask | Implement Initial Coordinator Setup and Staff Acceptance Tests | Done | Huanchen Wu | Huanchen Wu | AKO-9 | 2026-10-21T20:11:49.376+1300 | 2026-10-29T13:59:25.758+1300 | 2026-10-29T13:59:25.742+1300
AKO-43 | Subtask | Implement learner add, view and update functions | Done | Pei Wu | Pei Wu | AKO-10 | 2026-10-21T23:28:54.842+1300 | 2026-10-23T11:33:22.152+1300 | 2026-10-23T11:33:22.128+1300
AKO-44 | Subtask | Write unit tests for learner functions | Done | Pei Wu | Pei Wu | AKO-10 | 2026-10-21T23:39:39.283+1300 | 2026-10-23T11:47:48.434+1300 | 2026-10-23T11:47:48.419+1300
AKO-45 | Subtask | Build the Learners page and Add/Edit form | Done | Pei Wu | Pei Wu | AKO-10 | 2026-10-21T23:40:15.348+1300 | 2026-10-23T12:24:22.914+1300 | 2026-10-23T12:24:22.888+1300
AKO-46 | Subtask | Write system tests for the Learners page | Done | Pei Wu | Pei Wu | AKO-10 | 2026-10-21T23:40:44.045+1300 | 2026-10-23T12:48:48.353+1300 | 2026-10-23T12:48:48.328+1300
AKO-47 | Subtask | Create the lesson data model and tag list | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-14 | 2026-10-23T09:47:43.361+1300 | 2026-10-25T00:54:05.066+1300 | 2026-10-25T00:54:05.052+1300
AKO-48 | Subtask | Build the create lesson form with validation | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-14 | 2026-10-23T09:48:17.919+1300 | 2026-10-25T00:54:08.267+1300 | 2026-10-25T00:54:08.247+1300
AKO-49 | Subtask | Show the lesson list | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-14 | 2026-10-23T09:48:35.633+1300 | 2026-10-25T00:54:11.312+1300 | 2026-10-25T00:54:11.289+1300
AKO-50 | Subtask | Add file upload with type and size checks | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-14 | 2026-10-23T09:50:17.367+1300 | 2026-10-25T00:54:14.463+1300 | 2026-10-25T00:54:14.440+1300
AKO-51 | Subtask | Add download of files | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-14 | 2026-10-23T09:50:33.502+1300 | 2026-10-25T00:54:17.387+1300 | 2026-10-25T00:54:17.371+1300
AKO-52 | Subtask | Add edit and delete with confirmation | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-14 | 2026-10-23T09:50:56.028+1300 | 2026-10-25T00:54:20.333+1300 | 2026-10-25T00:54:20.314+1300
AKO-53 | Subtask | Enforce author or coordinator permissions | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-14 | 2026-10-23T09:51:17.962+1300 | 2026-10-25T00:54:23.315+1300 | 2026-10-25T00:54:23.301+1300
AKO-54 | Subtask | Write tests and record results | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-14 | 2026-10-23T09:51:33.163+1300 | 2026-10-25T00:54:26.145+1300 | 2026-10-25T00:54:26.131+1300
AKO-55 | Subtask | Update the README and merge | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-14 | 2026-10-23T09:51:53.697+1300 | 2026-10-26T19:58:20.773+1300 | 2026-10-26T19:58:20.765+1300
AKO-56 | Subtask | Implement mark present and unmark functions | Done | Pei Wu | Pei Wu | AKO-12 | 2026-10-23T12:57:21.674+1300 | 2026-10-23T13:26:12.461+1300 | 2026-10-23T13:26:12.442+1300
AKO-57 | Subtask | Connect to the User service and add “Add and mark present” | Done | Pei Wu | Pei Wu | AKO-12 | 2026-10-23T12:58:09.584+1300 | 2026-10-23T13:34:57.498+1300 | 2026-10-23T13:34:57.474+1300
AKO-58 | Subtask | Write unit tests for attendance functions | Done | Pei Wu | Pei Wu | AKO-12 | 2026-10-23T13:00:32.684+1300 | 2026-10-23T13:41:31.754+1300 | 2026-10-23T13:41:31.733+1300
AKO-59 | Subtask | Build the sign-in page | Done | Pei Wu | Pei Wu | AKO-12 | 2026-10-23T13:00:49.759+1300 | 2026-10-23T13:56:28.307+1300 | 2026-10-23T13:56:28.283+1300
AKO-60 | Subtask | Write system tests for the sign-in flow | Done | Pei Wu | Pei Wu | AKO-12 | 2026-10-23T13:01:07.619+1300 | 2026-10-23T14:05:45.912+1300 | 2026-10-23T14:05:45.895+1300
AKO-61 | Subtask | Implement flag Māori content functions | Done | Pei Wu | Pei Wu | AKO-15 | 2026-10-23T15:27:00.068+1300 | 2026-10-25T14:50:14.211+1300 | 2026-10-25T14:50:14.186+1300
AKO-62 | Subtask | Implement review recording and reset rules | Done | Pei Wu | Pei Wu | AKO-15 | 2026-10-23T15:27:15.681+1300 | 2026-10-25T14:55:58.046+1300 | 2026-10-25T14:55:58.031+1300
AKO-63 | Subtask | Write unit tests for the review functions | Done | Pei Wu | Pei Wu | AKO-15 | 2026-10-23T15:27:34.539+1300 | 2026-10-25T15:45:26.024+1300 | 2026-10-25T15:45:26.004+1300
AKO-64 | Subtask | Build the flag and review pages | Done | Pei Wu | Pei Wu | AKO-15 | 2026-10-23T15:27:52.735+1300 | 2026-10-25T15:55:00.847+1300 | 2026-10-25T15:55:00.831+1300
AKO-65 | Subtask | Write system tests for the review flow | Done | Pei Wu | Pei Wu | AKO-15 | 2026-10-23T15:28:28.568+1300 | 2026-10-26T13:44:10.894+1300 | 2026-10-26T13:44:10.876+1300
AKO-66 | Subtask | Use real teacher sign-in for the lesson library | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-21 | 2026-10-24T14:17:52.043+1300 | 2026-10-26T19:58:23.883+1300 | 2026-10-26T19:58:23.852+1300
AKO-67 | Subtask | Show the lesson library with its materials | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-21 | 2026-10-24T14:18:40.159+1300 | 2026-10-26T19:58:25.461+1300 | 2026-10-26T19:58:25.434+1300
AKO-68 | Subtask | Apply the Māori content review rule to materials | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-21 | 2026-10-24T14:19:04.271+1300 | 2026-10-26T19:58:26.988+1300 | 2026-10-26T19:58:26.977+1300
AKO-69 | Subtask | Open or download lesson files | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-21 | 2026-10-24T14:19:56.064+1300 | 2026-10-26T19:58:28.349+1300 | 2026-10-26T19:58:28.327+1300
AKO-70 | Subtask | Block protected materials from visitors who are not signed in | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-21 | 2026-10-24T14:20:19.097+1300 | 2026-10-26T19:58:29.766+1300 | 2026-10-26T19:58:29.740+1300
AKO-71 | Subtask | Test the story and record the evidence | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-21 | 2026-10-24T14:20:39.746+1300 | 2026-10-26T19:58:31.236+1300 | 2026-10-26T19:58:31.212+1300
AKO-72 | Subtask | Review, merge and Story Owner check | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-21 | 2026-10-24T14:21:01.176+1300 | 2026-10-27T16:19:06.324+1300 | 2026-10-27T16:19:06.305+1300
AKO-73 | Subtask | Design Enquiry Data Model and API | Done | Huanchen Wu | Huanchen Wu | AKO-18 | 2026-10-24T14:57:56.974+1300 | 2026-10-26T14:29:56.699+1300 | 2026-10-26T14:29:56.689+1300
AKO-74 | Subtask | Implement Enquiry Submission Backend | Done | Huanchen Wu | Huanchen Wu | AKO-18 | 2026-10-24T14:59:38.009+1300 | 2026-10-26T14:30:00.460+1300 | 2026-10-26T14:30:00.439+1300
AKO-75 | Subtask | Implement Coordinator Enquiry API | Done | Huanchen Wu | Huanchen Wu | AKO-18 | 2026-10-24T15:00:47.219+1300 | 2026-10-26T14:30:05.330+1300 | 2026-10-26T14:30:05.304+1300
AKO-76 | Subtask | Develop Public Enquiry Form | Done | Huanchen Wu | Huanchen Wu | AKO-18 | 2026-10-24T15:01:22.054+1300 | 2026-10-26T14:30:07.328+1300 | 2026-10-26T14:30:07.306+1300
AKO-77 | Subtask | Develop Coordinator Enquiry Management Page | Done | Huanchen Wu | Huanchen Wu | AKO-18 | 2026-10-24T15:01:52.001+1300 | 2026-10-26T14:30:09.806+1300 | 2026-10-26T14:30:09.783+1300
AKO-78 | Subtask | Perform Testing and Integration | Done | Huanchen Wu | Huanchen Wu | AKO-18 | 2026-10-24T15:02:24.795+1300 | 2026-10-26T14:30:12.610+1300 | 2026-10-26T14:30:12.590+1300
AKO-79 | Subtask | A1 Record the current lesson preparation time | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:33:22.574+1300 | 2026-10-29T14:04:44.159+1300 | 2026-10-29T14:04:44.143+1300
AKO-80 | Subtask | A2 Create the US-007 branch | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:33:31.848+1300 | 2026-10-26T19:58:22.394+1300 | 2026-10-26T19:58:22.368+1300
AKO-81 | Subtask | A3 Seed test lessons for search | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:33:35.279+1300 | 2026-10-24T22:34:18.136+1300 | 2026-10-24T22:34:18.112+1300
AKO-82 | Subtask | B1 Filter lessons by tag in GET /lessons | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:33:38.801+1300 | 2026-10-24T22:34:21.365+1300 | 2026-10-24T22:34:21.348+1300
AKO-83 | Subtask | B2 Search lesson titles by whole word in any letter case | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:33:42.420+1300 | 2026-10-24T22:34:24.391+1300 | 2026-10-24T22:34:24.369+1300
AKO-84 | Subtask | B3 Combine keyword and tag filters | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:33:45.893+1300 | 2026-10-24T22:34:27.584+1300 | 2026-10-24T22:34:27.565+1300
AKO-85 | Subtask | B4 Keep lesson search under 2 seconds | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:33:49.201+1300 | 2026-10-24T22:34:30.775+1300 | 2026-10-24T22:34:30.757+1300
AKO-86 | Subtask | B5 Add POST /lessons/{id}/copy endpoint | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:33:52.569+1300 | 2026-10-24T22:34:33.826+1300 | 2026-10-24T22:34:33.811+1300
AKO-87 | Subtask | B6 Validate copy: lesson date required | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:33:55.964+1300 | 2026-10-24T22:34:37.046+1300 | 2026-10-24T22:34:37.023+1300
AKO-88 | Subtask | B7 Apply copy permission and author rules | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:33:59.267+1300 | 2026-10-24T22:34:40.149+1300 | 2026-10-24T22:34:40.130+1300
AKO-89 | Subtask | B8 Document search parameters and copy endpoint | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:34:08.193+1300 | 2026-10-24T22:34:43.170+1300 | 2026-10-24T22:34:43.151+1300
AKO-90 | Subtask | C1 Add search and copy calls to lessons-api.ts | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:34:11.830+1300 | 2026-10-24T22:34:46.239+1300 | 2026-10-24T22:34:46.225+1300
AKO-91 | Subtask | C2 Add search box and tag chips to the lessons page | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:34:15.771+1300 | 2026-10-24T22:34:49.539+1300 | 2026-10-24T22:34:49.516+1300
AKO-92 | Subtask | C3 Show 'No lessons found' with a create link | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:34:19.135+1300 | 2026-10-24T22:34:52.591+1300 | 2026-10-24T22:34:52.568+1300
AKO-93 | Subtask | C4 Add 'Copy as new lesson' button | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:34:22.525+1300 | 2026-10-24T22:34:57.901+1300 | 2026-10-24T22:34:57.878+1300
AKO-94 | Subtask | C5 Build the copied lesson draft page | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:34:26.118+1300 | 2026-10-24T22:35:01.342+1300 | 2026-10-24T22:35:01.323+1300
AKO-95 | Subtask | C6 Save the copied draft and require a date | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:34:29.397+1300 | 2026-10-24T22:35:04.418+1300 | 2026-10-24T22:35:04.398+1300
AKO-96 | Subtask | C7 Handle long titles on copy | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:34:32.579+1300 | 2026-10-24T22:35:07.494+1300 | 2026-10-24T22:35:07.477+1300
AKO-97 | Subtask | D1 API tests for search (UT-49) | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:34:35.986+1300 | 2026-10-24T22:35:10.501+1300 | 2026-10-24T22:35:10.487+1300
AKO-98 | Subtask | D2 API tests for copy (UT-50) | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:34:44.936+1300 | 2026-10-24T22:35:13.539+1300 | 2026-10-24T22:35:13.524+1300
AKO-99 | Subtask | D3 Timing test for search (NT-07) | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:34:48.535+1300 | 2026-10-24T22:35:16.490+1300 | 2026-10-24T22:35:16.475+1300
AKO-100 | Subtask | D4 Playwright system tests for search and copy | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:34:51.927+1300 | 2026-10-24T22:35:19.809+1300 | 2026-10-24T22:35:19.790+1300
AKO-101 | Subtask | D5 Write manual test script for search and copy | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:34:55.690+1300 | 2026-10-24T22:35:23.111+1300 | 2026-10-24T22:35:23.096+1300
AKO-102 | Subtask | D6 Run linters and build checks | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:34:59.555+1300 | 2026-10-24T22:35:26.331+1300 | 2026-10-24T22:35:26.317+1300
AKO-103 | Subtask | E1 Open PR and complete code review | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:35:02.857+1300 | 2026-10-27T16:18:12.719+1300 | 2026-10-27T16:18:12.692+1300
AKO-104 | Subtask | E2 Test search and copy on the full Docker stack | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:35:06.327+1300 | 2026-10-24T22:35:29.555+1300 | 2026-10-24T22:35:29.541+1300
AKO-105 | Subtask | E3 Story Owner walkthrough (UA-04 extended) | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T21:35:10.355+1300 | 2026-10-27T16:18:14.646+1300 | 2026-10-27T16:18:14.629+1300
AKO-106 | Subtask | C8 Add Delete to the lessons list actions | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-16 | 2026-10-24T23:38:42.029+1300 | 2026-10-24T23:38:47.430+1300 | 2026-10-24T23:38:47.416+1300
AKO-107 | Subtask | A1 Run the current app and record the baseline | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-17 | 2026-10-25T00:24:47.889+1300 | 2026-10-27T16:18:31.595+1300 | 2026-10-27T16:18:31.573+1300
AKO-108 | Subtask | A2 Work on the US-009 branch | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-17 | 2026-10-25T00:24:56.789+1300 | 2026-10-27T16:18:34.349+1300 | 2026-10-27T16:18:34.324+1300
AKO-109 | Subtask | A3 Get class day, time, venue and contact from Julie | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-17 | 2026-10-25T00:25:00.340+1300 | 2026-10-27T16:18:39.421+1300 | 2026-10-27T16:18:39.405+1300
AKO-110 | Subtask | A4 Arrange the Kaiārahi check of te reo wording | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-17 | 2026-10-25T00:25:04.109+1300 | 2026-10-27T16:18:41.451+1300 | 2026-10-27T16:18:41.442+1300
AKO-111 | Subtask | B1 Write the club details content file | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-17 | 2026-10-25T00:25:08.105+1300 | 2026-10-25T00:45:35.487+1300 | 2026-10-25T00:45:35.471+1300
AKO-112 | Subtask | B2 Write the page text in plain English | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-17 | 2026-10-25T00:25:11.933+1300 | 2026-10-25T00:45:38.271+1300 | 2026-10-25T00:45:38.256+1300
AKO-113 | Subtask | C1 Add the public route group and layout | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-17 | 2026-10-25T00:25:15.707+1300 | 2026-10-25T00:45:43.326+1300 | 2026-10-25T00:45:43.313+1300
AKO-114 | Subtask | C2 Build the club information page | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-17 | 2026-10-25T00:25:19.352+1300 | 2026-10-25T00:45:46.423+1300 | 2026-10-25T00:45:46.400+1300
AKO-115 | Subtask | C3 Make the page work on a 360 px phone | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-17 | 2026-10-25T00:25:22.882+1300 | 2026-10-25T00:45:49.482+1300 | 2026-10-25T00:45:49.458+1300
AKO-116 | Subtask | C4 Meet the text size and contrast rules | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-17 | 2026-10-25T00:25:26.638+1300 | 2026-10-25T00:45:52.406+1300 | 2026-10-25T00:45:52.391+1300
AKO-117 | Subtask | C5 Add a friendly Page not found page | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-17 | 2026-10-25T00:25:30.256+1300 | 2026-10-25T00:45:55.410+1300 | 2026-10-25T00:45:55.389+1300
AKO-118 | Subtask | C6 Link the login page to the club page | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-17 | 2026-10-25T00:25:33.763+1300 | 2026-10-25T00:45:58.470+1300 | 2026-10-25T00:45:58.456+1300
AKO-119 | Subtask | D1 Add a page object for the public page | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-17 | 2026-10-25T00:25:37.363+1300 | 2026-10-25T00:46:01.378+1300 | 2026-10-25T00:46:01.355+1300
AKO-120 | Subtask | D2 Test the details and the 360 px layout | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-17 | 2026-10-25T00:25:41.286+1300 | 2026-10-25T00:46:04.604+1300 | 2026-10-25T00:46:04.589+1300
AKO-121 | Subtask | D3 Add the plain-English sentence check | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-17 | 2026-10-25T00:25:44.854+1300 | 2026-10-25T00:46:07.482+1300 | 2026-10-25T00:46:07.459+1300
AKO-122 | Subtask | D4 Run the accessibility audit | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-17 | 2026-10-25T00:25:48.387+1300 | 2026-10-25T00:46:10.518+1300 | 2026-10-25T00:46:10.499+1300
AKO-123 | Subtask | D5 Test the Page not found page | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-17 | 2026-10-25T00:25:51.826+1300 | 2026-10-25T00:46:13.500+1300 | 2026-10-25T00:46:13.478+1300
AKO-124 | Subtask | E1 Write the US-009 manual system tests | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-17 | 2026-10-25T00:25:55.645+1300 | 2026-10-25T00:46:16.501+1300 | 2026-10-25T00:46:16.480+1300
AKO-125 | Subtask | E2 Open the pull request and get it reviewed | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-17 | 2026-10-25T00:25:59.143+1300 | 2026-10-27T16:18:22.414+1300 | 2026-10-27T16:18:22.391+1300
AKO-126 | Subtask | E3 Story Owner walkthrough on a phone | Done | Sandhya Tiwari | Sandhya Tiwari | AKO-17 | 2026-10-25T00:26:02.773+1300 | 2026-10-27T16:18:27.489+1300 | 2026-10-27T16:18:27.466+1300
AKO-127 | Subtask | Design CSV Import Requirements and API | Done | Huanchen Wu | Huanchen Wu | AKO-24 | 2026-10-25T10:01:53.226+1300 | 2026-10-26T14:30:59.826+1300 | 2026-10-26T14:30:59.806+1300
AKO-128 | Subtask | Implement CSV Parsing and Validation | Done | Huanchen Wu | Huanchen Wu | AKO-24 | 2026-10-25T10:02:04.561+1300 | 2026-10-26T14:31:01.539+1300 | 2026-10-26T14:31:01.511+1300
AKO-129 | Subtask | Implement Coordinator CSV Import API | Done | Huanchen Wu | Huanchen Wu | AKO-24 | 2026-10-25T10:04:17.158+1300 | 2026-10-27T09:39:20.736+1300 | 2026-10-27T09:39:20.711+1300
AKO-130 | Subtask | Develop CSV Upload Interface | Done | Huanchen Wu | Huanchen Wu | AKO-24 | 2026-10-25T10:05:34.314+1300 | 2026-10-27T09:39:24.318+1300 | 2026-10-27T09:39:24.297+1300
AKO-131 | Subtask | Integrate CSV Import into Learner Management | Done | Huanchen Wu | Huanchen Wu | AKO-24 | 2026-10-25T10:09:10.382+1300 | 2026-10-27T16:03:27.223+1300 | 2026-10-27T16:03:27.205+1300
AKO-132 | Subtask | Perform Testing and Integration | Done | Huanchen Wu | Huanchen Wu | AKO-24 | 2026-10-25T10:10:11.673+1300 | 2026-10-27T16:03:30.358+1300 | 2026-10-27T16:03:30.341+1300
AKO-133 | Subtask | Implement check-in token validation functions | Done | Pei Wu | Pei Wu | AKO-20 | 2026-10-25T16:16:44.424+1300 | 2026-10-25T16:21:28.220+1300 | 2026-10-25T16:21:28.198+1300
AKO-134 | Subtask | Add learner name lookup to the User service for sign-in | Done | Pei Wu | Pei Wu | AKO-20 | 2026-10-25T16:17:06.820+1300 | 2026-10-25T16:37:38.375+1300 | 2026-10-25T16:37:38.354+1300
AKO-135 | Subtask | Implement learner sign-in and the public sign-in endpoint | Done | Pei Wu | Pei Wu | AKO-20 | 2026-10-25T16:17:18.734+1300 | 2026-10-25T16:37:50.930+1300 | 2026-10-25T16:37:50.909+1300
AKO-136 | Subtask | Write unit tests for sign-in | Done | Pei Wu | Pei Wu | AKO-20 | 2026-10-25T16:17:31.764+1300 | 2026-10-25T16:55:49.299+1300 | 2026-10-25T16:55:49.284+1300
AKO-137 | Subtask | Build the phone sign-in page | Done | Pei Wu | Pei Wu | AKO-20 | 2026-10-25T16:17:43.840+1300 | 2026-10-25T17:03:25.453+1300 | 2026-10-25T17:03:25.429+1300
AKO-138 | Subtask | Write system tests for the sign-in flow | Done | Pei Wu | Pei Wu | AKO-20 | 2026-10-25T16:17:55.621+1300 | 2026-10-25T17:14:45.510+1300 | 2026-10-25T17:14:45.487+1300
AKO-139 | Subtask | Implement attendance correction functions | Done | Pei Wu | Pei Wu | AKO-22 | 2026-10-25T17:16:32.485+1300 | 2026-10-25T17:27:41.862+1300 | 2026-10-25T17:27:41.846+1300
AKO-140 | Subtask | Make the change log append-only | Done | Pei Wu | Pei Wu | AKO-22 | 2026-10-25T17:21:43.790+1300 | 2026-10-25T17:34:06.092+1300 | 2026-10-25T17:34:06.068+1300
AKO-141 | Subtask | Add correction and history endpoints | Done | Pei Wu | Pei Wu | AKO-22 | 2026-10-25T17:21:56.011+1300 | 2026-10-25T17:42:29.921+1300 | 2026-10-25T17:42:29.906+1300
AKO-142 | Subtask | Write unit tests for corrections | Done | Pei Wu | Pei Wu | AKO-22 | 2026-10-25T17:22:08.602+1300 | 2026-10-25T21:01:32.740+1300 | 2026-10-25T21:01:32.716+1300
AKO-143 | Subtask | Build the correction view on the attendance page | Done | Pei Wu | Pei Wu | AKO-22 | 2026-10-25T17:22:21.448+1300 | 2026-10-25T21:12:11.145+1300 | 2026-10-25T21:12:11.127+1300
AKO-144 | Subtask | Write system tests for corrections | Done | Pei Wu | Pei Wu | AKO-22 | 2026-10-25T17:22:35.129+1300 | 2026-10-25T21:35:02.809+1300 | 2026-10-25T21:35:02.787+1300
AKO-145 | Subtask | Add the Māori content tick box and review labels | Done | Pei Wu | Pei Wu | AKO-15 | 2026-10-26T10:36:09.336+1300 | 2026-10-26T20:22:16.632+1300 | 2026-10-26T20:22:16.608+1300
AKO-146 | Subtask | Build the review form for coordinators | Done | Pei Wu | Pei Wu | AKO-15 | 2026-10-26T10:36:30.019+1300 | 2026-10-26T14:01:31.423+1300 | 2026-10-26T14:01:31.398+1300
AKO-147 | Subtask | Complete manual system tests for Māori content review | Done | Pei Wu | Pei Wu | AKO-15 | 2026-10-27T12:51:36.826+1300 | 2026-10-27T12:51:45.346+1300 | 2026-10-27T12:51:45.329+1300

## Sprints
Sprint ID | Sprint | State | Start | End | Complete | Goal | Board ID
1 | SCRUM Sprint 2 | closed | 2026-10-19T11:00:23.284Z | 2026-10-23T10:30:00.000Z | 2026-10-23T20:05:00.311Z | Deliver a working core system with role-based access, learner management, class sessions, and manual attendance recording. | 1
2 | SCRUM Sprint 1 | active | 2026-10-16T09:00:00.000Z | 2026-10-19T09:00:00.000Z |  | Finalise project requirements, establish the Scrum backlog, and prepare the project for development. | 1
3 | SCRUM Sprint 3 | active | 2026-10-23T11:00:50.184Z | 2026-10-27T11:00:00.000Z |  | Implement lesson management and Māori content review, complete attendance reporting, and integrate and test the MVP and other features | 1

## Sprint Issues
Sprint ID | Sprint | Sprint State | Issue | Type | Summary | Assignee | Parent | Current Status | Status at Close | Membership Source
1 | SCRUM Sprint 2 | closed | AKO-10 | Story | US-003 Keep learner records | Pei Wu | AKO-6 | Done | Done | Sprint API (current association)
1 | SCRUM Sprint 2 | closed | AKO-11 | Story | US-014 Manage class sessions | Shuohui Liu | AKO-6 | Done | To Do | Sprint API (current association)
1 | SCRUM Sprint 2 | closed | AKO-12 | Story | US-004 Record attendance by hand | Pei Wu | AKO-6 | Done | Done | Sprint API (current association)
1 | SCRUM Sprint 2 | closed | AKO-14 | Story | US-006 Create a lesson | Sandhya Tiwari | AKO-7 | Done | In Review | Sprint API (current association)
1 | SCRUM Sprint 2 | closed | AKO-8 | Story | US-001 Log in by role | Huanchen Wu | AKO-5 | Done | Done | Sprint API (current association)
1 | SCRUM Sprint 2 | closed | AKO-9 | Story | US-002 Manage staff accounts | Huanchen Wu | AKO-5 | Done | In Progress | Sprint API (current association)
2 | SCRUM Sprint 1 | active | AKO-26 | Task | T-001 Finalise project requirements and acceptance criteria | Pei Wu |  | Done |  | Sprint API (current association)
2 | SCRUM Sprint 1 | active | AKO-27 | Task | T-002 Configure Jira Scrum project and backlog | Huanchen Wu |  | Done |  | Sprint API (current association)
2 | SCRUM Sprint 1 | active | AKO-28 | Task | T-003 Define MVP scope and prioritise user stories | Sandhya Tiwari |  | Done |  | Sprint API (current association)
2 | SCRUM Sprint 1 | active | AKO-29 | Task | T-004 Prepare Sprint plan and team responsibilities | Huanchen Wu |  | Done |  | Sprint API (current association)
2 | SCRUM Sprint 1 | active | AKO-30 | Task | T-005 Document technical architecture and technology choices | Shuohui Liu |  | Done |  | Sprint API (current association)
2 | SCRUM Sprint 1 | active | AKO-31 | Task | T-006 Establish GitHub repository and collaboration rules | Shuohui Liu |  | Done |  | Sprint API (current association)
3 | SCRUM Sprint 3 | active | AKO-11 | Story | US-014 Manage class sessions | Shuohui Liu | AKO-6 | Done |  | Sprint API (current association)
3 | SCRUM Sprint 3 | active | AKO-13 | Story | US-005 Print attendance record | Shuohui Liu | AKO-6 | Done |  | Sprint API (current association)
3 | SCRUM Sprint 3 | active | AKO-14 | Story | US-006 Create a lesson | Sandhya Tiwari | AKO-7 | Done |  | Sprint API (current association)
3 | SCRUM Sprint 3 | active | AKO-15 | Story | US-008 Flag Māori content for review | Pei Wu | AKO-7 | Done |  | Sprint API (current association)
3 | SCRUM Sprint 3 | active | AKO-16 | Story | US-007 Find and copy lessons | Sandhya Tiwari | AKO-7 | Done |  | Sprint API (current association)
3 | SCRUM Sprint 3 | active | AKO-17 | Story | US-009 View club information | Sandhya Tiwari | AKO-25 | Done |  | Sprint API (current association)
3 | SCRUM Sprint 3 | active | AKO-18 | Story | US-010 Register interest in classes | Huanchen Wu | AKO-25 | Done |  | Sprint API (current association)
3 | SCRUM Sprint 3 | active | AKO-19 | Story | US-011 Open check-in with a QR code | Shuohui Liu | AKO-6 | Done |  | Sprint API (current association)
3 | SCRUM Sprint 3 | active | AKO-20 | Story | US-012 Sign in by scanning the QR code | Pei Wu | AKO-6 | Done |  | Sprint API (current association)
3 | SCRUM Sprint 3 | active | AKO-21 | Story | US-013 Access shared lesson materials after signing in | Sandhya Tiwari | AKO-7 | Done |  | Sprint API (current association)
3 | SCRUM Sprint 3 | active | AKO-22 | Story | US-015 Correct a past attendance record | Pei Wu | AKO-6 | Done |  | Sprint API (current association)
3 | SCRUM Sprint 3 | active | AKO-23 | Story | US-016 View a learner's attendance history | Shuohui Liu | AKO-6 | Done |  | Sprint API (current association)
3 | SCRUM Sprint 3 | active | AKO-24 | Story | US-017 Import learners from a CSV file | Huanchen Wu | AKO-6 | Done |  | Sprint API (current association)
3 | SCRUM Sprint 3 | active | AKO-9 | Story | US-002 Manage staff accounts | Huanchen Wu | AKO-5 | Done |  | Sprint API (current association)

## Sprint Performance
Sprint ID | Sprint | State | Total Associated Issues | Done | Not Done | Completion Rate | Status Basis | Start | Planned End | Actual Close | Goal | Caveat
1 | SCRUM Sprint 2 | closed | 6 | 3 | 3 | 50% | At actual close (reconstructed) | 2026-10-19T11:00:23.284Z | 2026-10-23T10:30:00.000Z | 2026-10-23T20:05:00.311Z | Deliver a working core system with role-based access, learner management, class sessions, and manual attendance recording. | Sprint API reflects current association; removed issues may be missing
2 | SCRUM Sprint 1 | active | 6 | 6 | 0 | 100% | Current snapshot | 2026-10-16T09:00:00.000Z | 2026-10-19T09:00:00.000Z |  | Finalise project requirements, establish the Scrum backlog, and prepare the project for development. | Sprint API reflects current association; removed issues may be missing
3 | SCRUM Sprint 3 | active | 14 | 14 | 0 | 100% | Current snapshot | 2026-10-23T11:00:50.184Z | 2026-10-27T11:00:00.000Z |  | Implement lesson management and Māori content review, complete attendance reporting, and integrate and test the MVP and other features | Sprint API reflects current association; removed issues may be missing

## Change History
Issue | Date | Author | Field | From | To
AKO-4 | 2026-10-13T22:00:07.120+1300 | Huanchen Wu | status | To Do | To Do
AKO-4 | 2026-10-29T14:05:05.273+1300 | Huanchen Wu | status | To Do | Done
AKO-4 | 2026-10-29T14:05:05.273+1300 | Huanchen Wu | resolution |  | Done
AKO-5 | 2026-10-16T15:46:11.202+1300 | Huanchen Wu | summary | Accounts and Access | [EP-01]Accounts and Access
AKO-5 | 2026-10-29T14:05:03.246+1300 | Huanchen Wu | status | To Do | Done
AKO-5 | 2026-10-29T14:05:03.246+1300 | Huanchen Wu | resolution |  | Done
AKO-6 | 2026-10-16T15:56:40.231+1300 | Huanchen Wu | Attachment |  | image-20261016-025637.png
AKO-6 | 2026-10-16T15:57:12.097+1300 | Huanchen Wu | summary | Learners and Attendance | [EP-02]Learners and Attendance
AKO-6 | 2026-10-23T17:04:54.852+1300 | Huanchen Wu | Attachment | image-20261016-025637.png
AKO-6 | 2026-10-29T14:05:01.310+1300 | Huanchen Wu | resolution |  | Done
AKO-6 | 2026-10-29T14:05:01.310+1300 | Huanchen Wu | status | To Do | Done
AKO-7 | 2026-10-16T15:57:21.194+1300 | Huanchen Wu | summary | Lesson Library | [EP-03]Lesson Library
AKO-7 | 2026-10-29T14:04:59.284+1300 | Huanchen Wu | resolution |  | Done
AKO-7 | 2026-10-29T14:04:59.284+1300 | Huanchen Wu | status | To Do | Done
AKO-8 | 2026-10-16T15:55:43.469+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-5
AKO-8 | 2026-10-16T21:11:17.176+1300 | Huanchen Wu | assignee |  | Huanchen Wu
AKO-8 | 2026-10-19T18:04:33.852+1300 | Huanchen Wu | IssueParentAssociation | AKO-5
AKO-8 | 2026-10-19T18:04:34.100+1300 | Huanchen Wu | Story point estimate |  | 5
AKO-8 | 2026-10-19T18:04:34.100+1300 | Huanchen Wu | description | As an authorised volunteer, I want to log in securely so that I can access permitted club functions. Proposed acceptance checks: Login succeeds for valid accounts; invalid credentials are rejected; role-based access is enforced. Story Owner: Leon Target Sprint: Sprint 1 (2026-10-16 to 2026-10-19) Planning note: Core Status: Proposed; stakeholder validation pending. | USER STORY As a club coordinator I want volunteers to log in with their own account and see only what their role allows so that learner information is only seen by the people who need it NOTES AND ASSUMPTIONS Two roles: Coordinator and Teacher. Learners do not log in; they use the QR check-in page (US-012). Volunteer features work in any desktop browser, as many volunteers have no smartphone. Passwords are stored hashed. Open question: coordinator resets passwords (no email)? DEPENDENCIES None ACCEPTANCE CRITERIA 1. Given: An active teacher account exists When: The teacher enters the correct username and password Then: The teacher's home page opens within 3 seconds and shows only the teacher menu 2. Given: The login page is open When: A wrong password is entered Then: "Username or password is incorrect" appears and the user stays on the login page 3. Given: An account has 4 failed logins in a row When: A 5th wrong password is entered Then: The account is locked for 10 minutes and the message says when to try again 4. Given: A teacher is logged in When: They type the address of the account-management page Then: Access is refused with "You do not have permission" and no account data is shown 5. Given: A user is logged in When: They press Log out, or 30 minutes pass with no activity Then: The session ends and the login page appears DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result.
AKO-8 | 2026-10-19T18:04:34.100+1300 | Huanchen Wu | summary | US-001 Volunteer Login | US-001 Log in by role
AKO-8 | 2026-10-19T19:10:25.654+1300 | Huanchen Wu | description | USER STORY As a club coordinator I want volunteers to log in with their own account and see only what their role allows so that learner information is only seen by the people who need it NOTES AND ASSUMPTIONS Two roles: Coordinator and Teacher. Learners do not log in; they use the QR check-in page (US-012). Volunteer features work in any desktop browser, as many volunteers have no smartphone. Passwords are stored hashed. Open question: coordinator resets passwords (no email)? DEPENDENCIES None ACCEPTANCE CRITERIA 1. Given: An active teacher account exists When: The teacher enters the correct username and password Then: The teacher's home page opens within 3 seconds and shows only the teacher menu 2. Given: The login page is open When: A wrong password is entered Then: "Username or password is incorrect" appears and the user stays on the login page 3. Given: An account has 4 failed logins in a row When: A 5th wrong password is entered Then: The account is locked for 10 minutes and the message says when to try again 4. Given: A teacher is logged in When: They type the address of the account-management page Then: Access is refused with "You do not have permission" and no account data is shown 5. Given: A user is logged in When: They press Log out, or 30 minutes pass with no activity Then: The session ends and the login page appears DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result. | USER STORY As a club coordinator I want volunteers to log in with their own account and see only what their role allows so that learner information is only seen by the people who need it NOTES AND ASSUMPTIONS Two roles: Coordinator and Teacher. Learners do not log in. For the MVP, teachers record attendance manually (US-004); QR check-in (US-011 and US-012) is deferred. A learner may view only the current session confirmation shown after their check-in, without accessing historical records. Volunteer features work in any desktop browser, as many volunteers have no smartphone. Passwords are stored hashed. Open question: coordinator resets passwords (no email)? DEPENDENCIES None ACCEPTANCE CRITERIA 1. Given: An active teacher account exists When: The teacher enters the correct username and password Then: The teacher's home page opens within 3 seconds and shows only the teacher menu 2. Given: The login page is open When: A wrong password is entered Then: "Username or password is incorrect" appears and the user stays on the login page 3. Given: An account has 4 failed logins in a row When: A 5th wrong password is entered Then: The account is locked for 10 minutes and the message says when to try again 4. Given: A teacher is logged in When: They type the address of the account-management page Then: Access is refused with "You do not have permission" and no account data is shown 5. Given: A user is logged in When: They press Log out, or 30 minutes pass with no activity Then: The session ends and the login page appears DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result.
AKO-8 | 2026-10-19T19:45:52.822+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-5
AKO-8 | 2026-10-19T20:07:08.645+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 2
AKO-8 | 2026-10-20T14:00:30.017+1300 | Huanchen Wu | status | To Do | In Progress
AKO-8 | 2026-10-23T21:31:36.496+1300 | Huanchen Wu | resolution |  | Done
AKO-8 | 2026-10-23T21:31:36.496+1300 | Huanchen Wu | status | In Progress | Done
AKO-9 | 2026-10-16T15:56:24.126+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-5
AKO-9 | 2026-10-19T18:04:35.017+1300 | Huanchen Wu | IssueParentAssociation | AKO-5
AKO-9 | 2026-10-19T18:04:35.042+1300 | Huanchen Wu | Story point estimate |  | 3
AKO-9 | 2026-10-19T18:04:35.042+1300 | Huanchen Wu | description | As a coordinator, I want to manage volunteer accounts and roles so that authorised people have appropriate access. Proposed acceptance checks: Coordinator can create, update and deactivate accounts; role changes affect permissions. Story Owner: Leon Target Sprint: Sprint 3 (2026-10-24 to 2026-10-27) Planning note: Enhancement Status: Proposed; stakeholder validation pending. | USER STORY As a club coordinator I want to add, edit and deactivate teacher accounts so that only current volunteers can use the system NOTES AND ASSUMPTIONS Accounts are deactivated, not deleted, so past lessons and attendance keep their author. The first coordinator account is created by a setup script described in the README. DEPENDENCIES US-001 (can be built with a test coordinator account) ACCEPTANCE CRITERIA 1. Given: A coordinator is logged in When: They submit a new teacher's name, a username and a temporary password of 8 characters or more Then: The account is created and appears in the staff list 2. Given: The add form is open When: The username already exists Then: "Username already taken" is shown and no account is created 3. Given: The add form is open When: The temporary password has 7 characters Then: "Password must be at least 8 characters" is shown and no account is created 4. Given: An active teacher account has created lessons When: The coordinator deactivates it Then: The teacher can no longer log in, and the lessons and attendance they created are still visible 5. Given: Only one active coordinator account exists When: That coordinator tries to deactivate it Then: The action is blocked with a message that at least one coordinator must stay active 6. Given: An active teacher account exists When: The coordinator changes the teacher's name and saves Then: The new name shows in the staff list DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result.
AKO-9 | 2026-10-19T18:04:35.042+1300 | Huanchen Wu | summary | US-002 Manage Teacher Accounts and Roles | US-002 Manage staff accounts
AKO-9 | 2026-10-19T19:45:57.877+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-5
AKO-9 | 2026-10-19T20:07:14.764+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 2
AKO-9 | 2026-10-19T20:08:38.866+1300 | Huanchen Wu | assignee |  | Sandhya Tiwari
AKO-9 | 2026-10-19T20:08:41.829+1300 | Huanchen Wu | assignee | Sandhya Tiwari | Huanchen Wu
AKO-9 | 2026-10-21T17:40:06.473+1300 | Huanchen Wu | status | To Do | In Progress
AKO-9 | 2026-10-24T09:05:00.490+1300 | Huanchen Wu | Sprint | SCRUM Sprint 2 | SCRUM Sprint 2, SCRUM Sprint 3
AKO-9 | 2026-10-24T09:18:48.783+1300 | Huanchen Wu | resolution |  | Done
AKO-9 | 2026-10-24T09:18:48.783+1300 | Huanchen Wu | status | In Progress | Done
AKO-10 | 2026-10-16T15:58:02.728+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-6
AKO-10 | 2026-10-19T18:04:35.665+1300 | Huanchen Wu | IssueParentAssociation | AKO-6
AKO-10 | 2026-10-19T18:04:35.675+1300 | Huanchen Wu | Story point estimate |  | 3
AKO-10 | 2026-10-19T18:04:35.675+1300 | Huanchen Wu | description | As a teacher, I want to maintain minimal learner records so that I can identify returning learners. Proposed acceptance checks: Add, view and edit learner records; validate required fields; minimise personal data. Story Owner: Pei Wu Target Sprint: Sprint 1 (2026-10-16 to 2026-10-19) Planning note: Core Status: Proposed; stakeholder validation pending. | USER STORY As a volunteer teacher I want to add and update a learner's basic details so that I have an up-to-date class list without paper forms NOTES AND ASSUMPTIONS Both roles can add and update learners. Collect only what the club needs: first name, family name, optional phone or email, first language. No date of birth, home address or ID numbers (privacy and Protection principle). The demo and the submitted code use made-up learners only. DEPENDENCIES US-001 (can be built with a test teacher account) ACCEPTANCE CRITERIA 1. Given: A teacher is logged in When: They enter a first name and a family name and save Then: The learner appears in the class list within 2 seconds 2. Given: The add form is open When: The first name is empty Then: "First name is required" is shown and nothing is saved 3. Given: A learner exists When: The teacher changes the first language and saves Then: The new value shows in the class list and on the learner's page 4. Given: A learner with the same first and family name exists When: A teacher adds another with that name Then: A warning is shown and the teacher can choose Cancel or Add anyway, because two people can share a name 5. Given: The add form is open When: A name of 101 characters is entered Then: It is rejected with "Name must be 100 characters or fewer" DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result.
AKO-10 | 2026-10-19T18:04:35.675+1300 | Huanchen Wu | summary | US-003 Manage Learner Records | US-003 Keep learner records
AKO-10 | 2026-10-19T19:46:16.643+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-6
AKO-10 | 2026-10-19T20:07:17.663+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 2
AKO-10 | 2026-10-19T20:33:34.630+1300 | Huanchen Wu | assignee |  | Pei Wu
AKO-10 | 2026-10-23T11:34:14.848+1300 | Pei Wu | status | To Do | In Progress
AKO-10 | 2026-10-23T12:48:58.965+1300 | Pei Wu | resolution |  | Done
AKO-10 | 2026-10-23T12:48:58.965+1300 | Pei Wu | status | In Progress | Done
AKO-11 | 2026-10-16T15:58:12.575+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-6
AKO-11 | 2026-10-19T18:04:39.088+1300 | Huanchen Wu | IssueParentAssociation | AKO-6
AKO-11 | 2026-10-19T18:04:39.116+1300 | Huanchen Wu | Story point estimate |  | 3
AKO-11 | 2026-10-19T18:04:39.116+1300 | Huanchen Wu | description | As a teacher, I want to create dated class sessions so that attendance is recorded against a specific meeting. Proposed acceptance checks: Create and view sessions; associate a lesson; preserve sessions with attendance. Story Owner: Michael Target Sprint: Sprint 2 (2026-10-20 to 2026-10-23) Planning note: Core Status: Proposed; stakeholder validation pending. | USER STORY As a volunteer teacher I want to create a dated class session and link a lesson to it so that attendance is recorded against a specific meeting NOTES AND ASSUMPTIONS One session per class date. No advance enrolment: learners are chosen or added when attendance is taken (US-004). A session that has attendance is never deleted. Split out of US-004 and US-011 so that each story can be tested alone. DEPENDENCIES US-001; US-006 (to link a lesson) ACCEPTANCE CRITERIA 1. Given: A teacher is logged in When: They choose "Start today's class" Then: A session for today's date is created and opens within 2 seconds 2. Given: A session for today already exists When: The teacher chooses "Start today's class" again Then: The existing session opens and no second session is created 3. Given: A session is open and lessons are saved When: The teacher picks a saved lesson and saves Then: The session shows the lesson's title and the lesson itself is unchanged 4. Given: Sessions exist for 3 different dates When: The teacher opens the session list Then: All 3 are listed newest first, each with its date and lesson title 5. Given: A session has attendance records When: The teacher tries to delete it Then: Deletion is refused with "This session has attendance and cannot be deleted" 6. Given: The new-session form is open When: The teacher enters a date in the future Then: "Date cannot be in the future" is shown and no session is created DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result.
AKO-11 | 2026-10-19T18:04:39.116+1300 | Huanchen Wu | summary | US-014 Manage Class Sessions | US-014 Manage class sessions
AKO-11 | 2026-10-19T19:46:19.474+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-6
AKO-11 | 2026-10-19T20:07:23.348+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 2
AKO-11 | 2026-10-19T20:36:23.022+1300 | Huanchen Wu | assignee |  | Shuohui Liu
AKO-11 | 2026-10-24T09:05:00.803+1300 | Huanchen Wu | Sprint | SCRUM Sprint 2 | SCRUM Sprint 2, SCRUM Sprint 3
AKO-11 | 2026-10-24T11:30:15.588+1300 | Shuohui Liu | status | To Do | In Progress
AKO-11 | 2026-10-26T13:03:36.291+1300 | Shuohui Liu | resolution |  | Done
AKO-11 | 2026-10-26T13:03:36.291+1300 | Shuohui Liu | status | In Progress | Done
AKO-12 | 2026-10-16T15:58:25.216+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-6
AKO-12 | 2026-10-19T18:04:36.324+1300 | Huanchen Wu | IssueParentAssociation | AKO-6
AKO-12 | 2026-10-19T18:04:36.335+1300 | Huanchen Wu | Story point estimate |  | 3
AKO-12 | 2026-10-19T18:04:36.335+1300 | Huanchen Wu | description | As a teacher, I want to mark learners present at a class session so that participation is recorded without advance enrolment. Proposed acceptance checks: Select existing or add walk-in learner; record/correct attendance; prevent duplicate learner-session entries. Story Owner: Pei Wu Target Sprint: Sprint 2 (2026-10-20 to 2026-10-23) Planning note: Core Status: Proposed; stakeholder validation pending. | USER STORY As a volunteer teacher I want to mark learners present at a class session by hand so that participation is recorded without paper sign-in sheets and without advance enrolment NOTES AND ASSUMPTIONS Runs in a desktop browser on a club or library laptop. The session comes from US-014. A learner who is not on the list is added and marked present in one step. Self sign-in by QR code is planned for later (US-011, US-012). DEPENDENCIES US-003 (class list), US-014 (session), US-001 ACCEPTANCE CRITERIA 1. Given: A class session for today is open and 20 learners are listed When: The teacher ticks one learner Then: The learner shows "Present" with the time and the present count rises by 1 2. Given: A learner is not on the list When: The teacher types the name and chooses "Add and mark present" Then: The learner is added to the class list and marked present in one step 3. Given: A learner is already marked present When: The teacher ticks the same learner again Then: No duplicate record is created and "Already signed in" is shown 4. Given: A learner was marked present by mistake When: The teacher unticks the learner Then: The present record is removed and the present count falls by 1 5. Given: The class list has 50 learners When: The teacher opens the sign-in page Then: The full list is shown within 3 seconds DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result.
AKO-12 | 2026-10-19T18:04:36.335+1300 | Huanchen Wu | summary | US-004 Manual Attendance Check-in | US-004 Record attendance by hand
AKO-12 | 2026-10-19T19:10:26.283+1300 | Huanchen Wu | description | USER STORY As a volunteer teacher I want to mark learners present at a class session by hand so that participation is recorded without paper sign-in sheets and without advance enrolment NOTES AND ASSUMPTIONS Runs in a desktop browser on a club or library laptop. The session comes from US-014. A learner who is not on the list is added and marked present in one step. Self sign-in by QR code is planned for later (US-011, US-012). DEPENDENCIES US-003 (class list), US-014 (session), US-001 ACCEPTANCE CRITERIA 1. Given: A class session for today is open and 20 learners are listed When: The teacher ticks one learner Then: The learner shows "Present" with the time and the present count rises by 1 2. Given: A learner is not on the list When: The teacher types the name and chooses "Add and mark present" Then: The learner is added to the class list and marked present in one step 3. Given: A learner is already marked present When: The teacher ticks the same learner again Then: No duplicate record is created and "Already signed in" is shown 4. Given: A learner was marked present by mistake When: The teacher unticks the learner Then: The present record is removed and the present count falls by 1 5. Given: The class list has 50 learners When: The teacher opens the sign-in page Then: The full list is shown within 3 seconds DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result. | USER STORY As a volunteer teacher I want to mark learners present at a class session by hand so that participation is recorded without paper sign-in sheets and without advance enrolment NOTES AND ASSUMPTIONS Runs in a desktop browser on a club or library laptop. The session comes from US-014. A learner who is not on the list is added and marked present in one step. Self sign-in by QR code is planned for later (US-011, US-012). DEPENDENCIES US-003 (class list), US-014 (session), US-001 ACCEPTANCE CRITERIA 1. Given: A class session for today is open and 20 learners are listed When: The teacher ticks one learner Then: The learner shows "Present" with the time and the present count rises by 1 2. Given: A learner is not on the list When: The teacher types the name and chooses "Add and mark present" Then: The learner is added to the class list and marked present in one step 3. Given: A learner is already marked present When: The teacher ticks the same learner again Then: No duplicate record is created and "Already signed in" is shown 4. Given: A learner was marked present by mistake When: The teacher unticks the learner Then: The present record is removed and the present count falls by 1 5. Given: The class list has 50 learners When: The teacher opens the sign-in page Then: The full list is shown within 3 seconds 6. Given: A learner has just been marked present for the current session When: The teacher opens the check-in confirmation view Then: The class name, session date and time, and check-in confirmation are shown without requiring a learner account; no other learners' records or attendance history are displayed DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result.
AKO-12 | 2026-10-19T19:46:21.255+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-6
AKO-12 | 2026-10-19T20:07:35.580+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 2
AKO-12 | 2026-10-19T20:33:52.645+1300 | Huanchen Wu | Rank |  | Ranked higher
AKO-12 | 2026-10-19T20:33:57.869+1300 | Huanchen Wu | assignee |  | Pei Wu
AKO-12 | 2026-10-23T13:01:33.713+1300 | Pei Wu | status | To Do | In Progress
AKO-12 | 2026-10-23T14:06:07.611+1300 | Pei Wu | resolution |  | Done
AKO-12 | 2026-10-23T14:06:07.611+1300 | Pei Wu | status | In Progress | Done
AKO-13 | 2026-10-16T15:58:32.077+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-6
AKO-13 | 2026-10-19T18:04:36.964+1300 | Huanchen Wu | IssueParentAssociation | AKO-6
AKO-13 | 2026-10-19T18:04:36.988+1300 | Huanchen Wu | Story point estimate |  | 3
AKO-13 | 2026-10-19T18:04:36.988+1300 | Huanchen Wu | description | As authorised staff, I want to export attendance records so that I can prepare reports. Proposed acceptance checks: Filter by date/session; export accurate CSV or agreed format; restrict access. Story Owner: Michael Target Sprint: Sprint 3 (2026-10-24 to 2026-10-27) Planning note: Enhancement Status: Proposed; stakeholder validation pending. | USER STORY As a club coordinator I want to print or save attendance for a range of dates so that the club still has a paper record for the library or other supporters NOTES AND ASSUMPTIONS Responds to the club's wish to keep paper. Output: printable A4 PDF and CSV. Open question: ask Julie what layout the club or library would actually want. DEPENDENCIES US-004, US-014 ACCEPTANCE CRITERIA 1. Given: Attendance exists for 3 classes When: The coordinator selects those dates and chooses PDF Then: A printable A4 PDF downloads with each learner's name and Present or Absent for each date 2. Given: No classes fall in the chosen dates When: The coordinator chooses Export Then: "No classes found for these dates" is shown and no file is created 3. Given: The date picker is open When: The start date is later than the end date Then: "Start date must be before end date" is shown and nothing is exported 4. Given: 12 classes and 50 learners are in the range When: The coordinator requests the PDF Then: It downloads within 10 seconds and no name is cut off at the page edge 5. Given: The same date range is selected When: The coordinator chooses CSV Then: The file opens in a spreadsheet with one row per learner and one column per date DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result.
AKO-13 | 2026-10-19T18:04:36.988+1300 | Huanchen Wu | summary | US-005 Export Attendance Records | US-005 Print attendance record
AKO-13 | 2026-10-19T19:46:28.878+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-6
AKO-13 | 2026-10-19T20:07:54.130+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 3
AKO-13 | 2026-10-19T20:34:11.188+1300 | Huanchen Wu | assignee |  | Shuohui Liu
AKO-13 | 2026-10-24T11:30:21.848+1300 | Shuohui Liu | Rank |  | Ranked higher
AKO-13 | 2026-10-24T11:30:22.081+1300 | Shuohui Liu | status | To Do | In Progress
AKO-13 | 2026-10-26T18:41:18.458+1300 | Shuohui Liu | resolution |  | Done
AKO-13 | 2026-10-26T18:41:18.458+1300 | Shuohui Liu | status | In Progress | Done
AKO-14 | 2026-10-16T15:58:48.957+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-7
AKO-14 | 2026-10-19T18:04:37.607+1300 | Huanchen Wu | IssueParentAssociation | AKO-7
AKO-14 | 2026-10-19T18:04:37.615+1300 | Huanchen Wu | Story point estimate |  | 5
AKO-14 | 2026-10-19T18:04:37.615+1300 | Huanchen Wu | description | As a teacher, I want to create lessons and attach teaching materials so that I can prepare and reuse class resources. Proposed acceptance checks: Create/edit lesson; upload validated supported files within agreed limits; staff-only access in current MVP. Story Owner: Sandhya Target Sprint: Sprint 1 (2026-10-16 to 2026-10-19) Planning note: Scope review; split if file uploads exceed capacity Status: Proposed; stakeholder validation pending. | USER STORY As a volunteer teacher I want to save a lesson with its date, topic tags and attached materials in one place so that I can find and reuse it later instead of searching through paper folders NOTES AND ASSUMPTIONS The club covers many parts of life in New Zealand, so tags are topics such as transport, health, shopping. Lessons are shared between teachers so they can be reused, but only the author or a coordinator can edit or delete a lesson. A lesson is teaching content and is not tied to one class. Allowed files: PDF, DOCX, JPG, PNG, up to 10 MB each. Each file has a "Share with learners" tick, off by default (US-013). Uploaded files are kept outside the code zip. Open question: confirm the tag list. DEPENDENCIES US-001 (can be built with a test teacher account) ACCEPTANCE CRITERIA 1. Given: A teacher is logged in When: They enter a title, a lesson date and at least one topic tag and save Then: The lesson appears in the lesson list with its date and tags 2. Given: The lesson form is open When: The title is empty Then: "Title is required" is shown and the lesson is not saved 3. Given: The lesson form is open When: A PDF of 10 MB or less is attached Then: It is saved and can be downloaded again with the same file name 4. Given: The lesson form is open When: A file over 10 MB, or a type other than PDF, DOCX, JPG or PNG, is attached Then: It is rejected with a message that states the rule and the other lesson details are kept 5. Given: A lesson is saved When: The teacher edits the title and saves Then: The list shows the new title and the lesson's date and materials are unchanged 6. Given: A saved lesson is no longer needed When: The teacher chooses Delete and confirms the warning Then: The lesson leaves the list and its files can no longer be downloaded DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result.
AKO-14 | 2026-10-19T18:04:37.615+1300 | Huanchen Wu | summary | US-006 Create Lessons and Upload Materials | US-006 Create a lesson
AKO-14 | 2026-10-19T19:46:46.165+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-7
AKO-14 | 2026-10-19T20:08:17.249+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 3
AKO-14 | 2026-10-19T20:34:22.614+1300 | Huanchen Wu | assignee |  | Sandhya Tiwari
AKO-14 | 2026-10-21T16:41:09.859+1300 | Huanchen Wu | Sprint | SCRUM Sprint 3 | SCRUM Sprint 2
AKO-14 | 2026-10-21T16:41:10.456+1300 | Huanchen Wu | Rank |  | Ranked higher
AKO-14 | 2026-10-23T00:02:38.808+1300 | Sandhya Tiwari | description | USER STORY As a volunteer teacher I want to save a lesson with its date, topic tags and attached materials in one place so that I can find and reuse it later instead of searching through paper folders NOTES AND ASSUMPTIONS The club covers many parts of life in New Zealand, so tags are topics such as transport, health, shopping. Lessons are shared between teachers so they can be reused, but only the author or a coordinator can edit or delete a lesson. A lesson is teaching content and is not tied to one class. Allowed files: PDF, DOCX, JPG, PNG, up to 10 MB each. Each file has a "Share with learners" tick, off by default (US-013). Uploaded files are kept outside the code zip. Open question: confirm the tag list. DEPENDENCIES US-001 (can be built with a test teacher account) ACCEPTANCE CRITERIA 1. Given: A teacher is logged in When: They enter a title, a lesson date and at least one topic tag and save Then: The lesson appears in the lesson list with its date and tags 2. Given: The lesson form is open When: The title is empty Then: "Title is required" is shown and the lesson is not saved 3. Given: The lesson form is open When: A PDF of 10 MB or less is attached Then: It is saved and can be downloaded again with the same file name 4. Given: The lesson form is open When: A file over 10 MB, or a type other than PDF, DOCX, JPG or PNG, is attached Then: It is rejected with a message that states the rule and the other lesson details are kept 5. Given: A lesson is saved When: The teacher edits the title and saves Then: The list shows the new title and the lesson's date and materials are unchanged 6. Given: A saved lesson is no longer needed When: The teacher chooses Delete and confirms the warning Then: The lesson leaves the list and its files can no longer be downloaded DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result. | USER STORY As a volunteer teacher I want to save a lesson with its date, topic tags and attached materials in one place so that I can find and reuse it later instead of searching through paper folders NOTES AND ASSUMPTIONS The club covers many parts of life in New Zealand, so tags are topics such as transport, health, shopping, history and lifestyle. Lessons are shared between teachers so they can be reused, but only the author or a coordinator can edit or delete a lesson. A lesson is teaching content and is not tied to one class. Allowed files: PDF, DOCX, JPG, PNG, up to 10 MB each. Each file has a "Share with learners" tick, off by default (US-013). Uploaded files are kept outside the code zip. Open question: confirm the tag list. DEPENDENCIES US-001 (can be built with a test teacher account) ACCEPTANCE CRITERIA 1. Given: A teacher is logged in When: They enter a title, a lesson date and at least one topic tag and save Then: The lesson appears in the lesson list with its date and tags 2. Given: The lesson form is open When: The title is empty Then: "Title is required" is shown and the lesson is not saved 3. Given: The lesson form is open When: A PDF of 10 MB or less is attached Then: It is saved and can be downloaded again with the same file name 4. Given: The lesson form is open When: A file over 10 MB, or a type other than PDF, DOCX, JPG or PNG, is attached Then: It is rejected with a message that states the rule and the other lesson details are kept 5. Given: A lesson is saved When: The teacher edits the title and saves Then: The list shows the new title and the lesson's date and materials are unchanged 6. Given: A saved lesson is no longer needed When: The teacher chooses Delete and confirms the warning Then: The lesson leaves the list and its files can no longer be downloaded DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result.
AKO-14 | 2026-10-23T09:56:31.147+1300 | Sandhya Tiwari | status | To Do | In Progress
AKO-14 | 2026-10-23T10:43:32.283+1300 | Sandhya Tiwari | status | In Progress | In Review
AKO-14 | 2026-10-23T21:21:07.528+1300 | Sandhya Tiwari | description | USER STORY As a volunteer teacher I want to save a lesson with its date, topic tags and attached materials in one place so that I can find and reuse it later instead of searching through paper folders NOTES AND ASSUMPTIONS The club covers many parts of life in New Zealand, so tags are topics such as transport, health, shopping, history and lifestyle. Lessons are shared between teachers so they can be reused, but only the author or a coordinator can edit or delete a lesson. A lesson is teaching content and is not tied to one class. Allowed files: PDF, DOCX, JPG, PNG, up to 10 MB each. Each file has a "Share with learners" tick, off by default (US-013). Uploaded files are kept outside the code zip. Open question: confirm the tag list. DEPENDENCIES US-001 (can be built with a test teacher account) ACCEPTANCE CRITERIA 1. Given: A teacher is logged in When: They enter a title, a lesson date and at least one topic tag and save Then: The lesson appears in the lesson list with its date and tags 2. Given: The lesson form is open When: The title is empty Then: "Title is required" is shown and the lesson is not saved 3. Given: The lesson form is open When: A PDF of 10 MB or less is attached Then: It is saved and can be downloaded again with the same file name 4. Given: The lesson form is open When: A file over 10 MB, or a type other than PDF, DOCX, JPG or PNG, is attached Then: It is rejected with a message that states the rule and the other lesson details are kept 5. Given: A lesson is saved When: The teacher edits the title and saves Then: The list shows the new title and the lesson's date and materials are unchanged 6. Given: A saved lesson is no longer needed When: The teacher chooses Delete and confirms the warning Then: The lesson leaves the list and its files can no longer be downloaded DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result. | USER STORY As a volunteer teacher I want to save a lesson with its date, topic tags and attached materials in one place so that I can find and reuse it later instead of searching through paper folders NOTES AND ASSUMPTIONS The club covers many parts of life in New Zealand, so tags are topics such as transport, health, shopping, culture,history and lifestyle. Lessons are shared between teachers so they can be reused, but only the author or a coordinator can edit or delete a lesson. A lesson is teaching content and is not tied to one class. Allowed files: PDF, DOCX, JPG, PNG, up to 10 MB each. Each file has a "Share with learners" tick, off by default (US-013). Uploaded files are kept outside the code zip. Open question: confirm the tag list. DEPENDENCIES US-001 (can be built with a test teacher account) ACCEPTANCE CRITERIA 1. Given: A teacher is logged in When: They enter a title, a lesson date and at least one topic tag and save Then: The lesson appears in the lesson list with its date and tags 2. Given: The lesson form is open When: The title is empty Then: "Title is required" is shown and the lesson is not saved 3. Given: The lesson form is open When: A PDF of 10 MB or less is attached Then: It is saved and can be downloaded again with the same file name 4. Given: The lesson form is open When: A file over 10 MB, or a type other than PDF, DOCX, JPG or PNG, is attached Then: It is rejected with a message that states the rule and the other lesson details are kept 5. Given: A lesson is saved When: The teacher edits the title and saves Then: The list shows the new title and the lesson's date and materials are unchanged 6. Given: A saved lesson is no longer needed When: The teacher chooses Delete and confirms the warning Then: The lesson leaves the list and its files can no longer be downloaded DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result.
AKO-14 | 2026-10-24T09:05:01.066+1300 | Huanchen Wu | Sprint | SCRUM Sprint 2 | SCRUM Sprint 2, SCRUM Sprint 3
AKO-14 | 2026-10-24T09:42:22.648+1300 | Sandhya Tiwari | description | USER STORY As a volunteer teacher I want to save a lesson with its date, topic tags and attached materials in one place so that I can find and reuse it later instead of searching through paper folders NOTES AND ASSUMPTIONS The club covers many parts of life in New Zealand, so tags are topics such as transport, health, shopping, culture,history and lifestyle. Lessons are shared between teachers so they can be reused, but only the author or a coordinator can edit or delete a lesson. A lesson is teaching content and is not tied to one class. Allowed files: PDF, DOCX, JPG, PNG, up to 10 MB each. Each file has a "Share with learners" tick, off by default (US-013). Uploaded files are kept outside the code zip. Open question: confirm the tag list. DEPENDENCIES US-001 (can be built with a test teacher account) ACCEPTANCE CRITERIA 1. Given: A teacher is logged in When: They enter a title, a lesson date and at least one topic tag and save Then: The lesson appears in the lesson list with its date and tags 2. Given: The lesson form is open When: The title is empty Then: "Title is required" is shown and the lesson is not saved 3. Given: The lesson form is open When: A PDF of 10 MB or less is attached Then: It is saved and can be downloaded again with the same file name 4. Given: The lesson form is open When: A file over 10 MB, or a type other than PDF, DOCX, JPG or PNG, is attached Then: It is rejected with a message that states the rule and the other lesson details are kept 5. Given: A lesson is saved When: The teacher edits the title and saves Then: The list shows the new title and the lesson's date and materials are unchanged 6. Given: A saved lesson is no longer needed When: The teacher chooses Delete and confirms the warning Then: The lesson leaves the list and its files can no longer be downloaded DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result. | USER STORY As a volunteer teacher I want to save a lesson with its date, topic tags and attached materials in one place so that I can find and reuse it later instead of searching through paper folders NOTES AND ASSUMPTIONS The club covers many parts of life in New Zealand, so tags are topics such as transport, health, shopping, culture,history and lifestyle. Lessons are shared between teachers so they can be reused, but only the author or a coordinator can edit or delete a lesson. A lesson is teaching content and is not tied to one class. Allowed files: PDF, DOCX, JPG, PNG,add the 1 KB minimum to the wording of AC4 and UT-40 and 10MB maximum. Each file has a "Share with learners" tick, off by default (US-013). Uploaded files are kept outside the code zip. Open question: confirm the tag list. DEPENDENCIES US-001 (can be built with a test teacher account) ACCEPTANCE CRITERIA 1. Given: A teacher is logged in When: They enter a title, a lesson date and at least one topic tag and save Then: The lesson appears in the lesson list with its date and tags 2. Given: The lesson form is open When: The title is empty Then: "Title is required" is shown and the lesson is not saved 3. Given: The lesson form is open When: A PDF of 10 MB or less is attached Then: It is saved and can be downloaded again with the same file name 4. Given: The lesson form is open When: A file over 10 MB, or a type other than PDF, DOCX, JPG or PNG, is attached Then: It is rejected with a message that states the rule and the other lesson details are kept 5. Given: A lesson is saved When: The teacher edits the title and saves Then: The list shows the new title and the lesson's date and materials are unchanged 6. Given: A saved lesson is no longer needed When: The teacher chooses Delete and confirms the warning Then: The lesson leaves the list and its files can no longer be downloaded DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result.
AKO-14 | 2026-10-25T19:22:08.951+1300 | Huanchen Wu | reporter | Huanchen Wu | Sandhya Tiwari
AKO-14 | 2026-10-26T18:41:58.460+1300 | Shuohui Liu | resolution |  | Done
AKO-14 | 2026-10-26T18:41:58.460+1300 | Shuohui Liu | status | In Review | Done
AKO-15 | 2026-10-16T15:58:57.171+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-7
AKO-15 | 2026-10-19T18:04:38.368+1300 | Huanchen Wu | IssueParentAssociation | AKO-7
AKO-15 | 2026-10-19T18:04:38.379+1300 | Huanchen Wu | Story point estimate |  | 3
AKO-15 | 2026-10-19T18:04:38.379+1300 | Huanchen Wu | description | As an authorised volunteer, I want to flag Māori-related content for review so that cultural materials follow an agreed process. Proposed acceptance checks: Flag and track review status; implement only consultation-confirmed rules; do not claim unverified approval. Story Owner: Pei Wu Target Sprint: Sprint 3 (2026-10-24 to 2026-10-27) Planning note: Consultation dependent Status: Proposed; stakeholder validation pending. | USER STORY As a volunteer teacher I want to mark a lesson that includes te reo Māori or Māori cultural content and see whether it has been reviewed so that Māori content is shared correctly and respectfully NOTES AND ASSUMPTIONS Supports the Protection principle of Te Tiriti o Waitangi. The review step and its wording are agreed with a Kaiārahi, and that consultation is recorded for the report. The coordinator records the review after the Kaiārahi confirms outside the system. Open question: block or only label unreviewed lessons? Start with a label and change it after consultation. DEPENDENCIES US-006; external: Kaiārahi consultation ACCEPTANCE CRITERIA 1. Given: The lesson form is open When: The teacher ticks "Contains Māori content" and saves Then: The lesson shows "Māori content – not yet reviewed" in the list and on its page 2. Given: A lesson is labelled not yet reviewed When: A coordinator enters the reviewer's name and review date and saves Then: The label changes to "Reviewed by [name], [date]" 3. Given: The review form is open When: The reviewer name is empty, or the date is in the future Then: It is rejected with a message and the label does not change 4. Given: A lesson is labelled reviewed When: A teacher changes its attached materials and saves Then: The label goes back to "not yet reviewed" 5. Given: A lesson title contains a macron, e.g. "Te reo Māori" When: The lesson is saved and listed Then: The macron is shown exactly as typed in the list, on the lesson page and in exports DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result.
AKO-15 | 2026-10-19T18:04:38.379+1300 | Huanchen Wu | summary | US-008 Flag Māori Content for Review | US-008 Flag Māori content for review
AKO-15 | 2026-10-19T19:46:50.617+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-7
AKO-15 | 2026-10-19T20:08:17.496+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 3
AKO-15 | 2026-10-19T20:34:50.777+1300 | Huanchen Wu | assignee |  | Pei Wu
AKO-15 | 2026-10-23T15:24:10.383+1300 | Pei Wu | status | To Do | In Progress
AKO-15 | 2026-10-25T17:19:20.912+1300 | Pei Wu | reporter | Huanchen Wu | Pei Wu
AKO-15 | 2026-10-26T20:22:29.576+1300 | Pei Wu | resolution |  | Done
AKO-15 | 2026-10-26T20:22:29.576+1300 | Pei Wu | status | In Progress | Done
AKO-16 | 2026-10-19T19:46:53.160+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-7
AKO-16 | 2026-10-19T20:34:39.935+1300 | Huanchen Wu | assignee |  | Sandhya Tiwari
AKO-16 | 2026-10-24T22:30:26.678+1300 | Sandhya Tiwari | description | USER STORY As a volunteer teacher I want to search past lessons by topic or keyword and copy one as the start of a new lesson so that I spend less time preparing each week NOTES AND ASSUMPTIONS Preparation time is the teachers' main pain point. Search covers titles and tags only, not the text inside files. A copy keeps tags and materials but leaves the date empty. Ask the teachers how long preparation takes now, so the report has a baseline. DEPENDENCIES US-006 ACCEPTANCE CRITERIA 1. Given: 10 lessons are saved and 2 are tagged "transport" When: The teacher selects the tag "transport" Then: Only those 2 lessons are listed 2. Given: Lessons are saved When: The teacher types a word from a lesson title, in any letter case Then: Matching lessons are listed within 2 seconds 3. Given: Lessons are saved When: A search matches nothing Then: "No lessons found" is shown with a link to create a new lesson 4. Given: A lesson is saved When: The teacher chooses "Copy as new lesson" Then: A draft opens titled "Copy of ..." with the same tags and materials and an empty date, and the original is unchanged 5. Given: A copied draft is open When: The teacher saves without a date Then: "Lesson date is required" is shown and nothing is saved DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result. | USER STORY As a volunteer teacher I want to search past lessons by topic or keyword and copy one as the start of a new lesson so that I spend less time preparing each week NOTES AND ASSUMPTIONS Preparation time is the teachers' main pain point. Search covers titles and tags only, not the text inside files. A copy keeps tags and materials but leaves the date empty. Ask the teachers how long preparation takes now, so the report has a baseline. DECISIONS (confirmed 24 Oct) 1. The keyword search matches whole words in lesson titles only, in any letter case. It does not match part of a word ("bu" does not find "bus") and does not match tag names. Tags are found only through the tag filter. 2. A copy keeps the original lesson's Māori content flag and its review status. DEPENDENCIES US-006 ACCEPTANCE CRITERIA 1. Given: 10 lessons are saved and 2 are tagged "transport" When: The teacher selects the tag "transport" Then: Only those 2 lessons are listed 2. Given: Lessons are saved When: The teacher types a word from a lesson title, in any letter case Then: Matching lessons are listed within 2 seconds 3. Given: Lessons are saved When: A search matches nothing Then: "No lessons found" is shown with a link to create a new lesson 4. Given: A lesson is saved When: The teacher chooses "Copy as new lesson" Then: A draft opens titled "Copy of ..." with the same tags and materials and an empty date, and the original is unchanged 5. Given: A copied draft is open When: The teacher saves without a date Then: "Lesson date is required" is shown and nothing is saved DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result.
AKO-16 | 2026-10-24T22:35:32.889+1300 | Sandhya Tiwari | status | To Do | In Progress
AKO-16 | 2026-10-24T22:35:44.691+1300 | Sandhya Tiwari | description | USER STORY As a volunteer teacher I want to search past lessons by topic or keyword and copy one as the start of a new lesson so that I spend less time preparing each week NOTES AND ASSUMPTIONS Preparation time is the teachers' main pain point. Search covers titles and tags only, not the text inside files. A copy keeps tags and materials but leaves the date empty. Ask the teachers how long preparation takes now, so the report has a baseline. DECISIONS (confirmed 24 Oct) 1. The keyword search matches whole words in lesson titles only, in any letter case. It does not match part of a word ("bu" does not find "bus") and does not match tag names. Tags are found only through the tag filter. 2. A copy keeps the original lesson's Māori content flag and its review status. DEPENDENCIES US-006 ACCEPTANCE CRITERIA 1. Given: 10 lessons are saved and 2 are tagged "transport" When: The teacher selects the tag "transport" Then: Only those 2 lessons are listed 2. Given: Lessons are saved When: The teacher types a word from a lesson title, in any letter case Then: Matching lessons are listed within 2 seconds 3. Given: Lessons are saved When: A search matches nothing Then: "No lessons found" is shown with a link to create a new lesson 4. Given: A lesson is saved When: The teacher chooses "Copy as new lesson" Then: A draft opens titled "Copy of ..." with the same tags and materials and an empty date, and the original is unchanged 5. Given: A copied draft is open When: The teacher saves without a date Then: "Lesson date is required" is shown and nothing is saved DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result. | USER STORY As a volunteer teacher I want to search past lessons by topic or keyword and copy one as the start of a new lesson so that I spend less time preparing each week NOTES AND ASSUMPTIONS Preparation time is the teachers' main pain point. Search covers titles and tags only, not the text inside files. A copy keeps tags and materials but leaves the date empty. Ask the teachers how long preparation takes now, so the report has a baseline. DECISIONS (confirmed 24 Oct) 1. The keyword search matches whole words in lesson titles only, in any letter case. It does not match part of a word ("bu" does not find "bus") and does not match tag names. Tags are found only through the tag filter. 2. A copy keeps the original lesson's Māori content flag and its review status. 3. A copy keeps each file's "Share with learners" tick. DEPENDENCIES US-006 ACCEPTANCE CRITERIA 1. Given: 10 lessons are saved and 2 are tagged "transport" When: The teacher selects the tag "transport" Then: Only those 2 lessons are listed 2. Given: Lessons are saved When: The teacher types a word from a lesson title, in any letter case Then: Matching lessons are listed within 2 seconds 3. Given: Lessons are saved When: A search matches nothing Then: "No lessons found" is shown with a link to create a new lesson 4. Given: A lesson is saved When: The teacher chooses "Copy as new lesson" Then: A draft opens titled "Copy of ..." with the same tags and materials and an empty date, and the original is unchanged 5. Given: A copied draft is open When: The teacher saves without a date Then: "Lesson date is required" is shown and nothing is saved DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result.
AKO-16 | 2026-10-25T11:26:18.727+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 3
AKO-16 | 2026-10-25T11:26:19.286+1300 | Huanchen Wu | Rank |  | Ranked higher
AKO-16 | 2026-10-25T19:23:35.596+1300 | Huanchen Wu | reporter | Huanchen Wu | Sandhya Tiwari
AKO-16 | 2026-10-26T13:03:06.848+1300 | Shuohui Liu | resolution |  | Done
AKO-16 | 2026-10-26T13:03:06.848+1300 | Shuohui Liu | status | In Progress | Done
AKO-16 | 2026-10-26T13:03:17.950+1300 | Shuohui Liu | resolution | Done
AKO-16 | 2026-10-26T13:03:17.950+1300 | Shuohui Liu | status | Done | In Review
AKO-16 | 2026-10-26T18:41:45.565+1300 | Shuohui Liu | resolution |  | Done
AKO-16 | 2026-10-26T18:41:45.565+1300 | Shuohui Liu | status | In Review | Done
AKO-17 | 2026-10-19T19:47:29.028+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-7
AKO-17 | 2026-10-19T19:47:32.264+1300 | Huanchen Wu | IssueParentAssociation | AKO-7 | AKO-25
AKO-17 | 2026-10-19T20:35:19.373+1300 | Huanchen Wu | assignee |  | Sandhya Tiwari
AKO-17 | 2026-10-25T00:45:32.112+1300 | Sandhya Tiwari | status | To Do | In Progress
AKO-17 | 2026-10-25T11:26:25.824+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 3
AKO-17 | 2026-10-25T11:26:26.243+1300 | Huanchen Wu | Rank |  | Ranked higher
AKO-17 | 2026-10-25T19:23:11.796+1300 | Huanchen Wu | reporter | Huanchen Wu | Sandhya Tiwari
AKO-17 | 2026-10-26T21:22:16.602+1300 | Shuohui Liu | resolution |  | Done
AKO-17 | 2026-10-26T21:22:16.602+1300 | Shuohui Liu | status | In Progress | Done
AKO-18 | 2026-10-19T19:47:34.712+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-25
AKO-18 | 2026-10-19T20:35:28.296+1300 | Huanchen Wu | assignee |  | Huanchen Wu
AKO-18 | 2026-10-23T19:55:32.759+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 3
AKO-18 | 2026-10-23T19:55:33.234+1300 | Huanchen Wu | Rank |  | Ranked higher
AKO-18 | 2026-10-25T11:20:21.608+1300 | Huanchen Wu | status | To Do | In Progress
AKO-18 | 2026-10-26T14:30:26.297+1300 | Huanchen Wu | resolution |  | Done
AKO-18 | 2026-10-26T14:30:26.297+1300 | Huanchen Wu | status | In Progress | Done
AKO-19 | 2026-10-19T19:49:31.938+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-6
AKO-19 | 2026-10-19T20:35:43.207+1300 | Huanchen Wu | assignee |  | Shuohui Liu
AKO-19 | 2026-10-26T18:42:53.349+1300 | Shuohui Liu | Sprint |  | SCRUM Sprint 3
AKO-19 | 2026-10-26T18:43:03.040+1300 | Shuohui Liu | status | To Do | In Progress
AKO-19 | 2026-10-26T21:22:10.867+1300 | Shuohui Liu | resolution |  | Done
AKO-19 | 2026-10-26T21:22:10.867+1300 | Shuohui Liu | status | In Progress | Done
AKO-20 | 2026-10-19T19:49:33.978+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-6
AKO-20 | 2026-10-19T20:35:54.238+1300 | Huanchen Wu | assignee |  | Pei Wu
AKO-20 | 2026-10-25T11:27:51.898+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 3
AKO-20 | 2026-10-25T11:27:52.290+1300 | Huanchen Wu | Rank |  | Ranked higher
AKO-20 | 2026-10-25T16:13:49.484+1300 | Pei Wu | status | To Do | In Progress
AKO-20 | 2026-10-25T16:43:55.187+1300 | Pei Wu | resolution |  | Done
AKO-20 | 2026-10-25T16:43:55.187+1300 | Pei Wu | status | In Progress | Done
AKO-21 | 2026-10-19T19:10:26.803+1300 | Huanchen Wu | description | USER STORY As a learner I want to see and download today's lesson materials after I sign in so that I can follow the lesson and study again at home NOTES AND ASSUMPTIONS Teachers and coordinators see materials in the lesson library (US-006); learners see them here and need no account. Only files the teacher has ticked "Share with learners" are shown, and nothing is shared by default. Lessons labelled "Māori content, not yet reviewed" (US-008) stay hidden from learners until reviewed. This rule is to be agreed with a Kaiārahi. Open question: should handouts be copyright-checked before sharing? Planned for later. DEPENDENCIES US-012, US-006, US-008, US-014 ACCEPTANCE CRITERIA 1. Given: A learner has just signed in and today's lesson has 2 shared files When: The materials list opens Then: Both file names are listed and each file downloads with its original name 2. Given: A visitor has not signed in When: They open the materials address directly Then: No file name or content is shown and the sign-in page opens instead 3. Given: A lesson has one file ticked "Share with learners" and one not ticked When: A learner signs in Then: Only the ticked file is listed 4. Given: The lesson is labelled "Māori content, not yet reviewed" When: A learner signs in Then: No materials are listed, "Materials will be added soon" is shown, and the sign-in is still recorded 5. Given: No lesson is linked to today's class When: A learner signs in Then: "No materials for today" is shown and the sign-in is still recorded 6. Given: A learner signed in 20 hours ago on the same phone When: They open the materials page again Then: The files are listed; after 24 hours the page asks them to scan a code again DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result. | USER STORY As a volunteer teacher I want to access shared lesson materials after signing in so that I can prepare for and deliver my assigned lessons NOTES AND ASSUMPTIONS Only authenticated teachers and coordinators can access the protected lesson library. Learners do not log in and are not given lesson-material access through this Story. After a teacher records a learner's check-in (US-004), the learner may view only the current session confirmation. Existing Māori content review controls (US-008) remain applicable; unreviewed content must not be exposed contrary to the agreed review policy. DEPENDENCIES US-001, US-006; US-008 for Māori content review controls ACCEPTANCE CRITERIA 1. Given: A volunteer teacher has signed in When: They open the lesson library Then: Available shared lesson materials are displayed according to their permissions 2. Given: A lesson has uploaded materials accessible to the teacher When: The teacher selects the lesson Then: They can open or download the associated files 3. Given: A visitor is not authenticated When: They attempt to access protected lesson materials directly Then: Access is denied and no protected files or file names are exposed DEFINITION OF DONE Acceptance criteria met; code reviewed and integrated; relevant tests pass; the Story Owner verifies the result.
AKO-21 | 2026-10-19T19:10:26.803+1300 | Huanchen Wu | summary | US-013 See lesson materials after signing in | US-013 Access shared lesson materials after signing in
AKO-21 | 2026-10-19T19:48:28.753+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-7
AKO-21 | 2026-10-19T20:08:17.698+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 3
AKO-21 | 2026-10-19T20:08:18.087+1300 | Huanchen Wu | Rank |  | Ranked higher
AKO-21 | 2026-10-19T20:36:07.157+1300 | Huanchen Wu | assignee |  | Sandhya Tiwari
AKO-21 | 2026-10-24T18:25:26.197+1300 | Sandhya Tiwari | resolution |  | Done
AKO-21 | 2026-10-24T18:25:26.197+1300 | Sandhya Tiwari | status | To Do | Done
AKO-21 | 2026-10-25T19:23:26.960+1300 | Huanchen Wu | reporter | Huanchen Wu | Sandhya Tiwari
AKO-22 | 2026-10-19T19:48:43.153+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-6
AKO-22 | 2026-10-19T20:36:32.768+1300 | Huanchen Wu | assignee |  | Pei Wu
AKO-22 | 2026-10-25T11:27:56.151+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 3
AKO-22 | 2026-10-25T11:27:56.571+1300 | Huanchen Wu | Rank |  | Ranked higher
AKO-22 | 2026-10-25T17:15:20.605+1300 | Pei Wu | status | To Do | In Progress
AKO-22 | 2026-10-25T17:19:35.286+1300 | Pei Wu | reporter | Huanchen Wu | Pei Wu
AKO-22 | 2026-10-25T21:35:21.815+1300 | Pei Wu | resolution |  | Done
AKO-22 | 2026-10-25T21:35:21.815+1300 | Pei Wu | status | In Progress | Done
AKO-23 | 2026-10-19T19:48:53.134+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-6
AKO-23 | 2026-10-19T20:36:41.825+1300 | Huanchen Wu | assignee |  | Shuohui Liu
AKO-23 | 2026-10-26T21:22:24.768+1300 | Shuohui Liu | Sprint |  | SCRUM Sprint 3
AKO-23 | 2026-10-26T21:22:31.160+1300 | Shuohui Liu | status | To Do | In Progress
AKO-23 | 2026-10-27T09:20:18.034+1300 | Shuohui Liu | resolution |  | Done
AKO-23 | 2026-10-27T09:20:18.034+1300 | Shuohui Liu | status | In Progress | Done
AKO-24 | 2026-10-19T19:48:54.850+1300 | Huanchen Wu | IssueParentAssociation |  | AKO-6
AKO-24 | 2026-10-19T20:36:50.296+1300 | Huanchen Wu | assignee |  | Huanchen Wu
AKO-24 | 2026-10-23T19:55:40.010+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 3
AKO-24 | 2026-10-23T19:55:40.405+1300 | Huanchen Wu | Rank |  | Ranked higher
AKO-24 | 2026-10-25T11:20:24.965+1300 | Huanchen Wu | status | To Do | In Progress
AKO-24 | 2026-10-26T14:30:35.209+1300 | Huanchen Wu | status | In Progress | In Progress
AKO-24 | 2026-10-27T16:03:33.959+1300 | Huanchen Wu | resolution |  | Done
AKO-24 | 2026-10-27T16:03:33.959+1300 | Huanchen Wu | status | In Progress | Done
AKO-25 | 2026-10-19T19:45:32.750+1300 | Huanchen Wu | summary | Public page and promotion | [EP-04]Public page and promotion
AKO-25 | 2026-10-29T14:04:57.453+1300 | Huanchen Wu | status | To Do | Done
AKO-25 | 2026-10-29T14:04:57.453+1300 | Huanchen Wu | resolution |  | Done
AKO-26 | 2026-10-19T20:23:50.087+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 1
AKO-26 | 2026-10-19T20:24:29.365+1300 | Huanchen Wu | resolution |  | Done
AKO-26 | 2026-10-19T20:24:29.365+1300 | Huanchen Wu | status | To Do | Done
AKO-26 | 2026-10-19T20:24:49.575+1300 | Huanchen Wu | assignee |  | Pei Wu
AKO-27 | 2026-10-19T20:24:04.405+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 1
AKO-27 | 2026-10-19T20:24:56.903+1300 | Huanchen Wu | status | To Do | Done
AKO-27 | 2026-10-19T20:24:56.903+1300 | Huanchen Wu | resolution |  | Done
AKO-27 | 2026-10-19T20:24:59.437+1300 | Huanchen Wu | assignee |  | Huanchen Wu
AKO-28 | 2026-10-19T20:24:04.678+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 1
AKO-28 | 2026-10-19T20:25:24.164+1300 | Huanchen Wu | assignee |  | Sandhya Tiwari
AKO-28 | 2026-10-19T20:25:46.200+1300 | Huanchen Wu | resolution |  | Done
AKO-28 | 2026-10-19T20:25:46.200+1300 | Huanchen Wu | status | To Do | Done
AKO-28 | 2026-10-25T19:21:36.074+1300 | Huanchen Wu | reporter | Huanchen Wu | Sandhya Tiwari
AKO-29 | 2026-10-19T20:24:04.897+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 1
AKO-29 | 2026-10-19T20:25:30.911+1300 | Huanchen Wu | assignee |  | Huanchen Wu
AKO-29 | 2026-10-19T20:25:48.058+1300 | Huanchen Wu | resolution |  | Done
AKO-29 | 2026-10-19T20:25:48.058+1300 | Huanchen Wu | status | To Do | Done
AKO-30 | 2026-10-19T20:24:05.105+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 1
AKO-30 | 2026-10-19T20:25:35.591+1300 | Huanchen Wu | assignee |  | Shuohui Liu
AKO-30 | 2026-10-19T20:25:49.952+1300 | Huanchen Wu | resolution |  | Done
AKO-30 | 2026-10-19T20:25:49.952+1300 | Huanchen Wu | status | To Do | Done
AKO-31 | 2026-10-19T20:24:05.313+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 1
AKO-31 | 2026-10-19T20:25:39.253+1300 | Huanchen Wu | assignee |  | Shuohui Liu
AKO-31 | 2026-10-19T20:25:51.937+1300 | Huanchen Wu | status | To Do | Done
AKO-31 | 2026-10-19T20:25:51.937+1300 | Huanchen Wu | resolution |  | Done
AKO-32 | 2026-10-21T20:18:25.921+1300 | Huanchen Wu | status | To Do | In Progress
AKO-32 | 2026-10-23T16:46:50.466+1300 | Huanchen Wu | resolution |  | Done
AKO-32 | 2026-10-23T16:46:50.466+1300 | Huanchen Wu | status | In Progress | Done
AKO-33 | 2026-10-21T20:18:30.190+1300 | Huanchen Wu | status | To Do | In Progress
AKO-33 | 2026-10-23T16:46:54.286+1300 | Huanchen Wu | status | In Progress | Done
AKO-33 | 2026-10-23T16:46:54.286+1300 | Huanchen Wu | resolution |  | Done
AKO-34 | 2026-10-23T16:47:05.853+1300 | Huanchen Wu | status | To Do | In Progress
AKO-34 | 2026-10-23T16:47:16.020+1300 | Huanchen Wu | status | In Progress | Done
AKO-34 | 2026-10-23T16:47:16.020+1300 | Huanchen Wu | resolution |  | Done
AKO-35 | 2026-10-23T16:47:24.264+1300 | Huanchen Wu | status | To Do | In Progress
AKO-35 | 2026-10-23T21:31:19.692+1300 | Huanchen Wu | resolution |  | Done
AKO-35 | 2026-10-23T21:31:19.692+1300 | Huanchen Wu | status | In Progress | Done
AKO-36 | 2026-10-23T16:47:27.504+1300 | Huanchen Wu | status | To Do | In Progress
AKO-36 | 2026-10-23T21:31:25.874+1300 | Huanchen Wu | status | In Progress | Done
AKO-36 | 2026-10-23T21:31:25.874+1300 | Huanchen Wu | resolution |  | Done
AKO-37 | 2026-10-23T16:47:30.540+1300 | Huanchen Wu | status | To Do | In Progress
AKO-37 | 2026-10-23T21:31:29.859+1300 | Huanchen Wu | status | In Progress | Done
AKO-37 | 2026-10-23T21:31:29.859+1300 | Huanchen Wu | resolution |  | Done
AKO-38 | 2026-10-23T16:47:38.896+1300 | Huanchen Wu | status | To Do | In Progress
AKO-38 | 2026-10-29T13:59:13.716+1300 | Huanchen Wu | status | In Progress | Done
AKO-38 | 2026-10-29T13:59:13.716+1300 | Huanchen Wu | resolution |  | Done
AKO-39 | 2026-10-23T16:47:42.980+1300 | Huanchen Wu | status | To Do | In Progress
AKO-39 | 2026-10-29T13:59:17.175+1300 | Huanchen Wu | resolution |  | Done
AKO-39 | 2026-10-29T13:59:17.175+1300 | Huanchen Wu | status | In Progress | Done
AKO-40 | 2026-10-23T16:47:47.472+1300 | Huanchen Wu | status | To Do | In Progress
AKO-40 | 2026-10-29T13:59:19.554+1300 | Huanchen Wu | resolution |  | Done
AKO-40 | 2026-10-29T13:59:19.554+1300 | Huanchen Wu | status | In Progress | Done
AKO-41 | 2026-10-29T13:59:21.521+1300 | Huanchen Wu | resolution |  | Done
AKO-41 | 2026-10-29T13:59:21.521+1300 | Huanchen Wu | status | To Do | Done
AKO-42 | 2026-10-29T13:59:25.758+1300 | Huanchen Wu | status | To Do | Done
AKO-42 | 2026-10-29T13:59:25.758+1300 | Huanchen Wu | resolution |  | Done
AKO-43 | 2026-10-21T23:29:10.823+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-43 | 2026-10-23T11:33:22.152+1300 | Pei Wu | resolution |  | Done
AKO-43 | 2026-10-23T11:33:22.152+1300 | Pei Wu | status | To Do | Done
AKO-44 | 2026-10-21T23:39:44.292+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-44 | 2026-10-23T11:37:56.486+1300 | Pei Wu | status | To Do | In Progress
AKO-44 | 2026-10-23T11:47:48.434+1300 | Pei Wu | resolution |  | Done
AKO-44 | 2026-10-23T11:47:48.434+1300 | Pei Wu | status | In Progress | Done
AKO-45 | 2026-10-21T23:40:22.360+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-45 | 2026-10-23T11:55:34.647+1300 | Pei Wu | status | To Do | In Progress
AKO-45 | 2026-10-23T12:24:22.914+1300 | Pei Wu | status | In Progress | Done
AKO-45 | 2026-10-23T12:24:22.914+1300 | Pei Wu | resolution |  | Done
AKO-46 | 2026-10-21T23:40:48.177+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-46 | 2026-10-23T12:42:14.314+1300 | Pei Wu | status | To Do | In Progress
AKO-46 | 2026-10-23T12:48:48.353+1300 | Pei Wu | status | In Progress | Done
AKO-46 | 2026-10-23T12:48:48.353+1300 | Pei Wu | resolution |  | Done
AKO-47 | 2026-10-23T10:01:48.657+1300 | Sandhya Tiwari | description |  | US-006: Create lesson data model and tag list Create the database structure for lessons. * Lesson: id, title, lesson date, author (user) * Tag: id, name * Lesson-tag link so one lesson can have many tags * Attachment: id, lesson, original file name, stored path, "Share with learners" flag (default off) * Seed the tags: transport, health, shopping, history, lifestyle Done when: the tables are created, the tags are loaded, and a lesson can be saved and read back with its tags.
AKO-47 | 2026-10-23T10:24:40.590+1300 | Sandhya Tiwari | labels |  | Lesson-Library
AKO-47 | 2026-10-23T16:48:18.709+1300 | Huanchen Wu | assignee | Huanchen Wu | Sandhya Tiwari
AKO-47 | 2026-10-23T16:48:29.749+1300 | Huanchen Wu | assignee | Sandhya Tiwari | Huanchen Wu
AKO-47 | 2026-10-24T12:39:34.284+1300 | Huanchen Wu | assignee | Huanchen Wu | Sandhya Tiwari
AKO-47 | 2026-10-25T00:52:32.447+1300 | Sandhya Tiwari | description | US-006: Create lesson data model and tag list Create the database structure for lessons. * Lesson: id, title, lesson date, author (user) * Tag: id, name * Lesson-tag link so one lesson can have many tags * Attachment: id, lesson, original file name, stored path, "Share with learners" flag (default off) * Seed the tags: transport, health, shopping, history, lifestyle Done when: the tables are created, the tags are loaded, and a lesson can be saved and read back with its tags. | US-006: Create the lesson data model and tag list *As built* in the Lesson service ({{server/services/lesson/models.py}}, PostgreSQL via SQLAlchemy): * {{lessons}}: id (UUID), title, lesson_date, created_by (user), source_lesson_id (filled in when a lesson is copied, US-007), Māori review fields, created/updated time, and {{deleted_at}} for soft delete * {{tags}}: id, name * {{lesson_tags}}: links a lesson to one or more tags * {{lesson_materials}}: id, lesson, original file_name, storage_key, mime_type, file_size, uploaded_by, {{share_with_learners}} (default off), and {{deleted_at}} * The 7 tags confirmed on 23 Oct are seeded on start-up, in this order: Transport, Health, Shopping, Culture, History, Accommodation, Lifestyle ({{TOPIC_TAGS}} in {{lessons.py}}). {{GET /tags}} returns them. * Both service replicas take a database lock while they create the tables, so they never collide on a new database. Done when: the tables are created, the 7 tags are loaded, and a lesson can be saved and read back with its tags (unit tests in {{tests/test_lessons.py}}).
AKO-47 | 2026-10-25T00:54:05.066+1300 | Sandhya Tiwari | resolution |  | Done
AKO-47 | 2026-10-25T00:54:05.066+1300 | Sandhya Tiwari | status | To Do | Done
AKO-48 | 2026-10-23T10:03:39.336+1300 | Sandhya Tiwari | description |  | Description US-006: Build create-lesson form with validation Build the form for teachers and coordinators to create a lesson. * Fields: title, lesson date, topic tags (choose one or more), file attachment * Show "Title is required" if the title is empty, and do not save * Date and at least one tag are also required, with clear messages * Use large, plain text Done when: AC 1 (valid lesson saves) and AC 2 (empty title is refused) pass.
AKO-48 | 2026-10-23T10:07:53.974+1300 | Sandhya Tiwari | description | Description US-006: Build create-lesson form with validation Build the form for teachers and coordinators to create a lesson. * Fields: title, lesson date, topic tags (choose one or more), file attachment * Show "Title is required" if the title is empty, and do not save * Date and at least one tag are also required, with clear messages * Use large, plain text Done when: AC 1 (valid lesson saves) and AC 2 (empty title is refused) pass. | US-006: Build create-lesson form with validation Build the form for teachers and coordinators to create a lesson. * Fields: title, lesson date, topic tags (choose one or more), file attachment * Show "Title is required" if the title is empty, and do not save * Date and at least one tag are also required, with clear messages * Use large, plain text Done when: AC 1 (valid lesson saves) and AC 2 (empty title is refused) pass.
AKO-48 | 2026-10-23T10:27:02.688+1300 | Sandhya Tiwari | labels |  | Lesson-Library
AKO-48 | 2026-10-24T12:39:37.080+1300 | Huanchen Wu | assignee | Huanchen Wu | Sandhya Tiwari
AKO-48 | 2026-10-25T00:52:37.129+1300 | Sandhya Tiwari | description | US-006: Build create-lesson form with validation Build the form for teachers and coordinators to create a lesson. * Fields: title, lesson date, topic tags (choose one or more), file attachment * Show "Title is required" if the title is empty, and do not save * Date and at least one tag are also required, with clear messages * Use large, plain text Done when: AC 1 (valid lesson saves) and AC 2 (empty title is refused) pass. | US-006: Build the create lesson form with validation *As built:* the page is {{/lessons/new}} ({{web/src/components/lessons/lesson-form.tsx}}), and it saves with {{POST /api/lesson/lessons}}. * Fields: title, lesson date, topic tags (tick one or more of the 7), and files, each with a "Share with learners" tick that starts off. * The same rules run in the browser and on the server ({{clean_lesson_fields}} in {{lessons.py}}). Messages: ** "Title is required" ** "Title must be 255 characters or fewer" ** "Lesson date is required" ** "Choose at least one topic tag" ** "Choose topic tags from the list" * Each message shows under its field, and nothing is saved. * The title is stored exactly as typed, apart from outer spaces, so macrons such as "Te reo Māori" stay unchanged (NFR-10). * Text uses the Ako UI kit: 18 px body text and 44 px controls. Done when: AC1 (a valid lesson saves) and AC2 (an empty title is refused) pass. Covered by unit tests and by browser tests in {{tests/system/test_lessons_page.py}}.
AKO-48 | 2026-10-25T00:54:08.267+1300 | Sandhya Tiwari | resolution |  | Done
AKO-48 | 2026-10-25T00:54:08.267+1300 | Sandhya Tiwari | status | To Do | Done
AKO-49 | 2026-10-23T10:11:58.806+1300 | Sandhya Tiwari | description |  | After saving, show lessons in a list with title, date and tags. The list should be visible to all logged-in teachers and coordinators because lessons are shared. Use a test teacher account until US-001 is merged. Done when: a saved lesson appears in the list with its date and tags (AC 1), and a macron in a title such as "Te reo Māori" displays exactly as typed (NFR-10).
AKO-49 | 2026-10-23T10:27:36.239+1300 | Sandhya Tiwari | labels |  | Lesson-Library
AKO-49 | 2026-10-24T12:39:39.832+1300 | Huanchen Wu | assignee | Huanchen Wu | Sandhya Tiwari
AKO-49 | 2026-10-25T00:52:41.721+1300 | Sandhya Tiwari | description | After saving, show lessons in a list with title, date and tags. The list should be visible to all logged-in teachers and coordinators because lessons are shared. Use a test teacher account until US-001 is merged. Done when: a saved lesson appears in the list with its date and tags (AC 1), and a macron in a title such as "Te reo Māori" displays exactly as typed (NFR-10). | US-006: Show the lesson list *As built:* the page is {{/lessons}} ({{web/src/components/lessons/lessons-screen.tsx}}), which reads from {{GET /api/lesson/lessons}}. * The list shows title, date (for example "21 Oct 2026"), tag chips, file count and the Māori review label. * Every logged-in teacher and coordinator sees every lesson, because lessons are shared. Deleted lessons are left out. * A link to "Add lesson" is at the top. * Login uses US-001's cookie session. Lesson requests go through the web app's server-side bridge ({{/api/staff/lesson/...}}), which sends the session to the Lesson service. A visitor without a session is sent to the login page. * Two test teacher accounts, teacher1 and teacher2, are seeded for testing ({{TEST_TEACHER_PASSWORD}}) until teachers can be added in account management. Done when: a saved lesson appears in the list with its date and tags (AC1), and "Te reo Māori" shows exactly as typed (NFR-10).
AKO-49 | 2026-10-25T00:54:11.312+1300 | Sandhya Tiwari | resolution |  | Done
AKO-49 | 2026-10-25T00:54:11.312+1300 | Sandhya Tiwari | status | To Do | Done
AKO-50 | 2026-10-23T10:12:48.926+1300 | Sandhya Tiwari | description |  | Let users attach files to a lesson. * Allowed types: PDF, DOCX, JPG, PNG * Maximum 10 MB per file * Store files in a folder outside the code zip * Keep the original file name * If a file is rejected, show a message that states the rule, and keep the other details the user already entered * Put the check in one reusable place (for example, a {{FileValidator}})
AKO-50 | 2026-10-23T10:13:31.360+1300 | Sandhya Tiwari | description | Let users attach files to a lesson. * Allowed types: PDF, DOCX, JPG, PNG * Maximum 10 MB per file * Store files in a folder outside the code zip * Keep the original file name * If a file is rejected, show a message that states the rule, and keep the other details the user already entered * Put the check in one reusable place (for example, a {{FileValidator}}) | Let users attach files to a lesson. * Allowed types: PDF, DOCX, JPG, PNG * Maximum 10 MB per file * Store files in a folder outside the code zip * Keep the original file name * If a file is rejected, show a message that states the rule, and keep the other details the user already entered * Put the check in one reusable place (for example, a {{FileValidator}}) Done when: AC 4 passes for a file over 10 MB and for a wrong file type.
AKO-50 | 2026-10-23T10:27:52.465+1300 | Sandhya Tiwari | labels |  | Lesson-Library
AKO-50 | 2026-10-24T12:39:42.529+1300 | Huanchen Wu | assignee | Huanchen Wu | Sandhya Tiwari
AKO-50 | 2026-10-25T00:52:48.508+1300 | Sandhya Tiwari | description | Let users attach files to a lesson. * Allowed types: PDF, DOCX, JPG, PNG * Maximum 10 MB per file * Store files in a folder outside the code zip * Keep the original file name * If a file is rejected, show a message that states the rule, and keep the other details the user already entered * Put the check in one reusable place (for example, a {{FileValidator}}) Done when: AC 4 passes for a file over 10 MB and for a wrong file type. | US-006: Add file upload with type and size checks *As built* ({{server/services/lesson/files.py}}): * Allowed types are PDF, DOCX, JPG and PNG. Files must be from 1 KB to 10 MB (decided 23 Oct). * All checks are in one reusable {{FileValidator}}: the file name, the extension, the size, and the content. The content must match the extension, so a program renamed to {{.pdf}} is refused, and a DOCX must really be a Word file. * Every refusal shows one message that states the whole rule: "Files must be PDF, DOCX, JPG or PNG, from 1 KB to 10 MB". The browser checks first ({{file-rule.ts}}) and keeps the other lesson details that were entered. * {{FileStore}} saves files under a random storage key in {{LESSON_FILES_DIR}}. That is a Docker volume shared by both Lesson replicas, outside the code folder. The original file name is kept in the database. * The upload is {{POST /api/lesson/lessons/{id}/materials}}. Nginx allows request bodies up to 11 MB for the Lesson routes. Done when: AC4 passes for a file over 10 MB, a file under 1 KB and a wrong file type ({{tests/test_files.py}}, {{tests/test_api.py}}, browser tests).
AKO-50 | 2026-10-25T00:54:14.463+1300 | Sandhya Tiwari | resolution |  | Done
AKO-50 | 2026-10-25T00:54:14.463+1300 | Sandhya Tiwari | status | To Do | Done
AKO-51 | 2026-10-23T10:15:38.004+1300 | Sandhya Tiwari | description |  | * Add a download link for each attached file on the lesson page. The downloaded file must have the same name as the uploaded one. * Add a "Share with learners" tick for each file, off by default. It is only stored for now and will be used by US-013. Done when: AC 3 passes (a PDF of 10 MB or less saves and downloads with the same name), and the tick saves as off unless the user turns it on.
AKO-51 | 2026-10-23T10:28:23.406+1300 | Sandhya Tiwari | labels |  | Lesson-Library
AKO-51 | 2026-10-24T12:39:45.351+1300 | Huanchen Wu | assignee | Huanchen Wu | Sandhya Tiwari
AKO-51 | 2026-10-25T00:52:51.428+1300 | Sandhya Tiwari | description | * Add a download link for each attached file on the lesson page. The downloaded file must have the same name as the uploaded one. * Add a "Share with learners" tick for each file, off by default. It is only stored for now and will be used by US-013. Done when: AC 3 passes (a PDF of 10 MB or less saves and downloads with the same name), and the tick saves as off unless the user turns it on. | US-006: Add download of files *As built:* * On the lesson page ({{/lessons/{id}}}, {{lesson-screen.tsx}}), each file has a Download button. It uses {{GET /api/lesson/materials/{id}/download}}. * The downloaded file has the same name as the uploaded one, macrons included. * The server sends the stored file type with {{nosniff}} and {{no-store}}, so the browser never guesses the type. * PDFs and pictures can also be opened in the browser. * Each file has a "Share with learners" tick, off by default. The author or a coordinator can change it later ({{PATCH /api/lesson/materials/{id}}}). It is stored for US-013. Done when: AC3 passes (a PDF of 10 MB or less saves and downloads with the same name), and the tick saves as off unless the user turns it on.
AKO-51 | 2026-10-25T00:54:17.387+1300 | Sandhya Tiwari | resolution |  | Done
AKO-51 | 2026-10-25T00:54:17.387+1300 | Sandhya Tiwari | status | To Do | Done
AKO-52 | 2026-10-23T10:18:30.925+1300 | Sandhya Tiwari | description |  | *Add edit lesson:* Let the author or a coordinator edit a lesson's title and save. * The list shows the new title * The lesson's date and materials stay unchanged * Apply the same validation as the create form ("Title is required") Done when: AC 5 passes. *Add delete lesson with Confirmation* Add a Delete button on the lesson with a confirmation warning. * After the user confirms, remove the lesson from the list * Delete its stored files so they can no longer be downloaded * If the user cancels, nothing changes Done when: AC 6 passes, and the file link no longer works after deletion.
AKO-52 | 2026-10-23T10:28:42.862+1300 | Sandhya Tiwari | labels |  | Lesson-Library
AKO-52 | 2026-10-23T10:28:43.040+1300 | Sandhya Tiwari | assignee | Huanchen Wu | Sandhya Tiwari
AKO-52 | 2026-10-25T00:52:55.217+1300 | Sandhya Tiwari | description | *Add edit lesson:* Let the author or a coordinator edit a lesson's title and save. * The list shows the new title * The lesson's date and materials stay unchanged * Apply the same validation as the create form ("Title is required") Done when: AC 5 passes. *Add delete lesson with Confirmation* Add a Delete button on the lesson with a confirmation warning. * After the user confirms, remove the lesson from the list * Delete its stored files so they can no longer be downloaded * If the user cancels, nothing changes Done when: AC 6 passes, and the file link no longer works after deletion. | US-006: Add edit and delete with confirmation *Edit lesson* ({{/lessons/{id}/edit}}, {{PUT /api/lesson/lessons/{id}}}): * The author or a coordinator can change the title, date and tags. They use the same form and the same messages as Create ("Title is required" and so on). * After saving, the list shows the new title, and the lesson's date and materials are unchanged unless the user changed them. Done when: AC5 passes. *Delete lesson with confirmation* ({{DELETE /api/lesson/lessons/{id}}}): * Delete is on the lesson page and, since 24 Oct, in the Actions column of the lessons list. * A warning asks to confirm: 'Delete "title"? It leaves the lesson list and its files can no longer be downloaded.' with "Yes, delete" and Cancel. * *Soft delete*, decided 23 Oct: the lesson and its files are hidden with {{deleted_at}}, not removed from disk. They leave the list, and their download links answer 404. * Cancel changes nothing. Done when: AC6 passes, and the file link no longer works after deletion.
AKO-52 | 2026-10-25T00:54:20.333+1300 | Sandhya Tiwari | resolution |  | Done
AKO-52 | 2026-10-25T00:54:20.333+1300 | Sandhya Tiwari | status | To Do | Done
AKO-53 | 2026-10-23T10:19:54.767+1300 | Sandhya Tiwari | description |  | Only the lesson's author or a coordinator can edit or delete a lesson. Other teachers can view and download but not change it. * Hide the Edit and Delete buttons for other teachers * Also block the action on the server, in case someone types the address directly, and show "You do not have permission" Done when: a second teacher cannot edit or delete another teacher's lesson, and a coordinator can.
AKO-53 | 2026-10-23T10:29:00.795+1300 | Sandhya Tiwari | labels |  | Lesson-Library
AKO-53 | 2026-10-24T12:39:48.777+1300 | Huanchen Wu | assignee | Huanchen Wu | Sandhya Tiwari
AKO-53 | 2026-10-25T00:52:59.323+1300 | Sandhya Tiwari | description | Only the lesson's author or a coordinator can edit or delete a lesson. Other teachers can view and download but not change it. * Hide the Edit and Delete buttons for other teachers * Also block the action on the server, in case someone types the address directly, and show "You do not have permission" Done when: a second teacher cannot edit or delete another teacher's lesson, and a coordinator can. | US-006: Enforce author or coordinator permissions *As built:* * Only the lesson's author or any coordinator can edit or delete a lesson, add or remove its files, or change a file's "Share with learners" tick ({{can_change}} in {{lessons.py}}). * Other teachers can view and download but not change. * The server checks the session with the User service ({{user_client.py}}) and refuses other teachers with HTTP 403 "You do not have permission", even if they type the address directly. * The API returns {{can_change}} for each lesson, so the web pages hide Edit and Delete from other teachers. Done when: a second teacher (teacher2) cannot edit or delete teacher1's lesson, and a coordinator can (UT-42; unit and browser tests).
AKO-53 | 2026-10-25T00:54:23.315+1300 | Sandhya Tiwari | resolution |  | Done
AKO-53 | 2026-10-25T00:54:23.315+1300 | Sandhya Tiwari | status | To Do | Done
AKO-54 | 2026-10-23T10:20:39.458+1300 | Sandhya Tiwari | description |  | Write a test for each acceptance criterion and record the results as evidence (NFR-09). * AC 1: valid lesson appears in the list * AC 2: empty title is refused * AC 3: PDF of 10 MB or less saves and downloads with the same name * AC 4: file over 10 MB and a wrong file type are both rejected * AC 5: editing the title leaves date and materials unchanged * AC 6: deleting removes the lesson and its files * Extra: another teacher cannot edit or delete; macron displays correctly Done when: all tests pass and the results are recorded in the team's test plan.
AKO-54 | 2026-10-23T10:29:16.976+1300 | Sandhya Tiwari | labels |  | Lesson-Library
AKO-54 | 2026-10-24T12:39:51.294+1300 | Huanchen Wu | assignee | Huanchen Wu | Sandhya Tiwari
AKO-54 | 2026-10-25T00:53:04.877+1300 | Sandhya Tiwari | description | Write a test for each acceptance criterion and record the results as evidence (NFR-09). * AC 1: valid lesson appears in the list * AC 2: empty title is refused * AC 3: PDF of 10 MB or less saves and downloads with the same name * AC 4: file over 10 MB and a wrong file type are both rejected * AC 5: editing the title leaves date and materials unchanged * AC 6: deleting removes the lesson and its files * Extra: another teacher cannot edit or delete; macron displays correctly Done when: all tests pass and the results are recorded in the team's test plan. | US-006: Write tests and record results *As built:* * Unit and API tests are in {{server/services/lesson/tests/}}: {{test_lessons.py}}, {{test_api.py}}, {{test_files.py}} and {{test_materials_access.py}}. They run against a throwaway PostgreSQL database set by {{TEST_DATABASE_URL}}. * Browser tests are in {{tests/system/test_lessons_page.py}} (Playwright). It has 18 tests, including an axe accessibility check. * Manual scripts are in {{docs/system_test/lessons_system_tests.md}}. * Covered: ** AC1: a valid lesson appears in the list ** AC2: an empty title is refused ** AC3: a PDF of 10 MB or less saves and downloads with the same name ** AC4: files over 10 MB, under 1 KB, or of a wrong type are rejected and the details are kept ** AC5: editing the title leaves the date and materials unchanged ** AC6: Delete, after confirming, removes the lesson and its files are no longer downloadable; Cancel changes nothing ** Extra: another teacher cannot edit or delete; macrons display correctly * Latest run, 24 Oct, with US-001 + US-007 merged: Lesson service 130 passed; lesson-related browser tests 38 passed. Done when: all tests pass and the results are recorded in the team's test plan.
AKO-54 | 2026-10-25T00:54:26.145+1300 | Sandhya Tiwari | resolution |  | Done
AKO-54 | 2026-10-25T00:54:26.145+1300 | Sandhya Tiwari | status | To Do | Done
AKO-55 | 2026-10-23T10:21:39.567+1300 | Sandhya Tiwari | description |  | * Add the setup steps for this feature to the README (where uploaded files are stored and how to run it) * Open a pull request from {{US-006-create-lesson}} and ask a teammate to review * Merge into {{main}} * Ask the Story Owner to verify the result against the acceptance criteria Done when: the PR is merged, the Story Owner has verified, and the parent ticket can move to Done.
AKO-55 | 2026-10-23T10:29:37.724+1300 | Sandhya Tiwari | labels |  | Lesson-Library
AKO-55 | 2026-10-23T10:39:21.606+1300 | Sandhya Tiwari | status | To Do | In Review
AKO-55 | 2026-10-24T12:39:53.881+1300 | Huanchen Wu | assignee | Huanchen Wu | Sandhya Tiwari
AKO-55 | 2026-10-25T00:53:08.799+1300 | Sandhya Tiwari | description | * Add the setup steps for this feature to the README (where uploaded files are stored and how to run it) * Open a pull request from {{US-006-create-lesson}} and ask a teammate to review * Merge into {{main}} * Ask the Story Owner to verify the result against the acceptance criteria Done when: the PR is merged, the Story Owner has verified, and the parent ticket can move to Done. | US-006: Update the README and merge *As built:* * {{server/README.md}} explains the Lesson service: ** the {{LESSON_FILES_DIR}} file volume, which is shared by both replicas and kept outside the code ** the test teacher accounts ** how to run the tests * {{tests/system/README.md}} lists the lesson browser tests. * The code was uploaded to {{feature/v1.0_US013}}. On 24 Oct it was merged with US-001's login, together with US-007, on {{feature/v1.0_US007}}. It is waiting to be pushed, because the Claude GitHub App is not yet installed on Enfrai. The bundle and push steps are in the project files, under us-007. * Next steps: ** open a pull request into {{feature/v1.0/dev}} ** a teammate reviews it ** merge it ** the Story Owner verifies the result against the acceptance criteria Done when: the PR is merged, the Story Owner has verified, and the parent ticket can move to Done.
AKO-55 | 2026-10-26T19:58:20.773+1300 | Sandhya Tiwari | resolution |  | Done
AKO-55 | 2026-10-26T19:58:20.773+1300 | Sandhya Tiwari | status | In Review | Done
AKO-56 | 2026-10-23T12:57:27.633+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-56 | 2026-10-23T13:01:21.869+1300 | Pei Wu | status | To Do | In Progress
AKO-56 | 2026-10-23T13:26:12.461+1300 | Pei Wu | status | In Progress | Done
AKO-56 | 2026-10-23T13:26:12.461+1300 | Pei Wu | resolution |  | Done
AKO-57 | 2026-10-23T12:58:14.173+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-57 | 2026-10-23T13:26:26.397+1300 | Pei Wu | status | To Do | In Progress
AKO-57 | 2026-10-23T13:34:57.498+1300 | Pei Wu | status | In Progress | Done
AKO-57 | 2026-10-23T13:34:57.498+1300 | Pei Wu | resolution |  | Done
AKO-58 | 2026-10-23T13:00:40.415+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-58 | 2026-10-23T13:41:31.754+1300 | Pei Wu | status | To Do | Done
AKO-58 | 2026-10-23T13:41:31.754+1300 | Pei Wu | resolution |  | Done
AKO-59 | 2026-10-23T13:00:54.002+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-59 | 2026-10-23T13:41:54.608+1300 | Pei Wu | status | To Do | In Progress
AKO-59 | 2026-10-23T13:56:28.307+1300 | Pei Wu | resolution |  | Done
AKO-59 | 2026-10-23T13:56:28.307+1300 | Pei Wu | status | In Progress | Done
AKO-60 | 2026-10-23T13:01:12.655+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-60 | 2026-10-23T13:57:49.844+1300 | Pei Wu | status | To Do | In Progress
AKO-60 | 2026-10-23T14:05:45.912+1300 | Pei Wu | resolution |  | Done
AKO-60 | 2026-10-23T14:05:45.912+1300 | Pei Wu | status | In Progress | Done
AKO-61 | 2026-10-23T15:27:05.109+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-61 | 2026-10-25T14:50:14.211+1300 | Pei Wu | resolution |  | Done
AKO-61 | 2026-10-25T14:50:14.211+1300 | Pei Wu | status | To Do | Done
AKO-62 | 2026-10-23T15:27:21.155+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-62 | 2026-10-25T14:50:29.449+1300 | Pei Wu | status | To Do | In Progress
AKO-62 | 2026-10-25T14:55:58.046+1300 | Pei Wu | status | In Progress | Done
AKO-62 | 2026-10-25T14:55:58.046+1300 | Pei Wu | resolution |  | Done
AKO-63 | 2026-10-23T15:27:58.390+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-63 | 2026-10-25T15:45:26.024+1300 | Pei Wu | status | To Do | Done
AKO-63 | 2026-10-25T15:45:26.024+1300 | Pei Wu | resolution |  | Done
AKO-64 | 2026-10-23T15:28:01.839+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-64 | 2026-10-25T15:45:47.065+1300 | Pei Wu | status | To Do | In Progress
AKO-64 | 2026-10-25T15:55:00.847+1300 | Pei Wu | resolution |  | Done
AKO-64 | 2026-10-25T15:55:00.847+1300 | Pei Wu | status | In Progress | Done
AKO-65 | 2026-10-23T15:28:32.604+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-65 | 2026-10-25T15:55:13.777+1300 | Pei Wu | status | To Do | In Progress
AKO-65 | 2026-10-25T16:13:28.322+1300 | Pei Wu | resolution |  | Done
AKO-65 | 2026-10-25T16:13:28.322+1300 | Pei Wu | status | In Progress | Done
AKO-65 | 2026-10-25T16:13:33.267+1300 | Pei Wu | resolution | Done
AKO-65 | 2026-10-25T16:13:33.267+1300 | Pei Wu | status | Done | In Progress
AKO-65 | 2026-10-26T13:44:10.894+1300 | Pei Wu | resolution |  | Done
AKO-65 | 2026-10-26T13:44:10.894+1300 | Pei Wu | status | In Progress | Done
AKO-66 | 2026-10-24T14:18:05.900+1300 | Sandhya Tiwari | status | To Do | In Progress
AKO-66 | 2026-10-24T14:22:19.565+1300 | Sandhya Tiwari | description |  | Switch the lesson library from the US-006 test accounts to the real US-001 accounts. * Teachers and coordinators sign in with the accounts made in US-001 * Remove the {{teacher1}} and {{teacher2}} test accounts, or turn them off outside testing * A session ends after 30 minutes without activity, not 30 minutes after sign-in (US-001) * Only the teacher and coordinator roles exist; learners have no sign-in
AKO-66 | 2026-10-24T14:24:01.776+1300 | Sandhya Tiwari | description | Switch the lesson library from the US-006 test accounts to the real US-001 accounts. * Teachers and coordinators sign in with the accounts made in US-001 * Remove the {{teacher1}} and {{teacher2}} test accounts, or turn them off outside testing * A session ends after 30 minutes without activity, not 30 minutes after sign-in (US-001) * Only the teacher and coordinator roles exist; learners have no sign-in | Switch the lesson library from the US-006 test accounts to the real US-001 accounts. * Teachers and coordinators sign in with the accounts made in US-001 * Remove the {{teacher1}} and {{teacher2}} test accounts, or turn them off outside testing * A session ends after 30 minutes without activity, not 30 minutes after sign-in (US-001) * Only the teacher and coordinator roles exist; learners have no sign-in Depends on: US-001 merged. Done when: a real teacher account can sign in and open the lesson library, the test accounts are gone or off, and an idle session ends after 30 minutes. h3.
AKO-66 | 2026-10-25T19:22:26.795+1300 | Huanchen Wu | assignee | Huanchen Wu | Sandhya Tiwari
AKO-66 | 2026-10-26T19:58:23.883+1300 | Sandhya Tiwari | resolution |  | Done
AKO-66 | 2026-10-26T19:58:23.883+1300 | Sandhya Tiwari | status | In Progress | Done
AKO-67 | 2026-10-24T14:24:49.388+1300 | Sandhya Tiwari | description |  | Show signed-in staff the shared lessons, and how many files each one has. * The list shows title, date, tags and the number of files * The lesson page lists each file with its name, type and size * Hidden (deleted) lessons and files never appear * An empty library shows "No lessons found" Done when: AC 1 passes for a teacher and a coordinator. h3.
AKO-67 | 2026-10-25T19:22:31.472+1300 | Huanchen Wu | assignee | Huanchen Wu | Sandhya Tiwari
AKO-67 | 2026-10-26T19:58:25.461+1300 | Sandhya Tiwari | status | To Do | Done
AKO-67 | 2026-10-26T19:58:25.461+1300 | Sandhya Tiwari | resolution |  | Done
AKO-68 | 2026-10-24T14:25:31.867+1300 | Sandhya Tiwari | description |  | Follow the review policy agreed for US-008 when showing files. * Use the existing {{has_maori_content}} and {{review_status}} columns * Show the "Māori content – not yet reviewed" label on the list and the lesson page * If the policy hides unreviewed files from some staff, the server refuses them too, not just the page * Policy to confirm first (see Open questions) Depends on: US-008. Done when: the agreed policy holds both on the page and when calling the server address directly.
AKO-68 | 2026-10-25T19:22:33.906+1300 | Huanchen Wu | assignee | Huanchen Wu | Sandhya Tiwari
AKO-68 | 2026-10-26T19:58:26.988+1300 | Sandhya Tiwari | resolution |  | Done
AKO-68 | 2026-10-26T19:58:26.988+1300 | Sandhya Tiwari | status | To Do | Done
AKO-69 | 2026-10-24T14:26:20.061+1300 | Sandhya Tiwari | description |  | Let teachers open a file in the browser as well as download it. * *Open* shows PDF, JPG and PNG in a new tab; DOCX always downloads * *Download* keeps the original file name, including macrons * Both need a sign-in; a plain link copied to someone else does not work * A missing or hidden file shows "File not found" Done when: AC 2 passes for each of the four file types.
AKO-69 | 2026-10-25T19:22:36.211+1300 | Huanchen Wu | assignee | Huanchen Wu | Sandhya Tiwari
AKO-69 | 2026-10-26T19:58:28.349+1300 | Sandhya Tiwari | resolution |  | Done
AKO-69 | 2026-10-26T19:58:28.349+1300 | Sandhya Tiwari | status | To Do | Done
AKO-70 | 2026-10-24T14:27:05.964+1300 | Sandhya Tiwari | description |  | Make sure a visitor who is not signed in learns nothing about the lessons. * Every lesson and file address returns 401 without a session, and the answer contains no titles or file names * The lesson pages show only "Please log in", even when opened from a direct link * An expired or logged-out session is refused the same way * Nginx serves no file folder directly, and stored file names are random Done when: AC 3 passes for every lesson and file address, logged out and with an expired session.
AKO-70 | 2026-10-25T19:22:38.707+1300 | Huanchen Wu | assignee | Huanchen Wu | Sandhya Tiwari
AKO-70 | 2026-10-26T19:58:29.766+1300 | Sandhya Tiwari | status | To Do | Done
AKO-70 | 2026-10-26T19:58:29.766+1300 | Sandhya Tiwari | resolution |  | Done
AKO-71 | 2026-10-24T14:28:07.358+1300 | Sandhya Tiwari | description |  | * Unit and API tests for AC 1 to AC 3, the review rule and the expired session * Playwright tests in {{tests/system}} for opening, downloading and the logged-out visitor * A manual script in {{docs/system_test/}}, in the same format as the lessons one * Results recorded in the Test Plan (NFR-09) Done when: all tests pass and the results are recorded.
AKO-71 | 2026-10-25T19:22:40.799+1300 | Huanchen Wu | assignee | Huanchen Wu | Sandhya Tiwari
AKO-71 | 2026-10-26T19:58:31.236+1300 | Sandhya Tiwari | status | To Do | Done
AKO-71 | 2026-10-26T19:58:31.236+1300 | Sandhya Tiwari | resolution |  | Done
AKO-72 | 2026-10-24T14:28:54.926+1300 | Sandhya Tiwari | description |  | * Update {{server/README.md}} for any new settings * Open a pull request from {{feature/v1.0/user_story_0XX}} and ask a teammate to review * Merge into {{feature/v1.0/dev}} * The Story Owner checks AC 1 to 3 with a real teacher account Done when: the PR is merged, the Story Owner has checked it, and the story moves to Done.
AKO-72 | 2026-10-25T19:22:43.497+1300 | Huanchen Wu | assignee | Huanchen Wu | Sandhya Tiwari
AKO-72 | 2026-10-27T16:19:06.324+1300 | Huanchen Wu | resolution |  | Done
AKO-72 | 2026-10-27T16:19:06.324+1300 | Huanchen Wu | status | To Do | Done
AKO-73 | 2026-10-24T14:58:35.725+1300 | Huanchen Wu | description |  | Review the existing architecture and US-009 public page. Design the enquiry data model, REST API endpoints, validation rules, and Coordinator access control. Document the design before implementation.
AKO-73 | 2026-10-24T14:58:50.271+1300 | Huanchen Wu | status | To Do | In Progress
AKO-73 | 2026-10-26T14:29:56.699+1300 | Huanchen Wu | resolution |  | Done
AKO-73 | 2026-10-26T14:29:56.699+1300 | Huanchen Wu | status | In Progress | Done
AKO-74 | 2026-10-24T15:00:01.784+1300 | Huanchen Wu | description |  | Develop the public enquiry submission API. Validate required fields, contact details, consent, and the 500-character message limit. Save valid enquiries to PostgreSQL and implement basic spam protection.
AKO-74 | 2026-10-26T14:30:00.460+1300 | Huanchen Wu | resolution |  | Done
AKO-74 | 2026-10-26T14:30:00.460+1300 | Huanchen Wu | status | To Do | Done
AKO-75 | 2026-10-24T15:01:01.817+1300 | Huanchen Wu | description |  | Develop a protected API for Coordinators to retrieve submitted enquiries. Return the visitor's name, contact information, optional message, and submission date, ordered from newest to oldest. Deny access to Teachers and unauthenticated users.
AKO-75 | 2026-10-26T14:30:05.330+1300 | Huanchen Wu | status | To Do | Done
AKO-75 | 2026-10-26T14:30:05.330+1300 | Huanchen Wu | resolution |  | Done
AKO-76 | 2026-10-24T15:01:37.258+1300 | Huanchen Wu | description |  | Implement a public form with name, email or phone, optional message, and required consent checkbox. Display the specified validation messages and a confirmation after successful submission. Integrate the form into the existing public page.
AKO-76 | 2026-10-26T14:30:07.328+1300 | Huanchen Wu | status | To Do | Done
AKO-76 | 2026-10-26T14:30:07.328+1300 | Huanchen Wu | resolution |  | Done
AKO-77 | 2026-10-24T15:02:07.993+1300 | Huanchen Wu | description |  | Create a Coordinator-only enquiry management page. Display submitted enquiries in descending date order. Implement loading, empty, and error states, and integrate with the protected backend API.
AKO-77 | 2026-10-26T14:30:09.806+1300 | Huanchen Wu | resolution |  | Done
AKO-77 | 2026-10-26T14:30:09.806+1300 | Huanchen Wu | status | To Do | Done
AKO-78 | 2026-10-24T15:02:44.097+1300 | Huanchen Wu | description |  | Create and execute backend, frontend, and integration tests covering all five acceptance criteria. Verify database persistence, input validation, access restrictions, and existing authentication functionality. Record test results and outstanding issues.
AKO-78 | 2026-10-26T14:30:12.610+1300 | Huanchen Wu | resolution |  | Done
AKO-78 | 2026-10-26T14:30:12.610+1300 | Huanchen Wu | status | To Do | Done
AKO-79 | 2026-10-29T14:04:44.159+1300 | Huanchen Wu | resolution |  | Done
AKO-79 | 2026-10-29T14:04:44.159+1300 | Huanchen Wu | status | To Do | Done
AKO-80 | 2026-10-26T19:58:22.394+1300 | Sandhya Tiwari | status | To Do | Done
AKO-80 | 2026-10-26T19:58:22.394+1300 | Sandhya Tiwari | resolution |  | Done
AKO-81 | 2026-10-24T22:34:18.136+1300 | Sandhya Tiwari | status | To Do | Done
AKO-81 | 2026-10-24T22:34:18.136+1300 | Sandhya Tiwari | resolution |  | Done
AKO-82 | 2026-10-24T22:34:21.365+1300 | Sandhya Tiwari | resolution |  | Done
AKO-82 | 2026-10-24T22:34:21.365+1300 | Sandhya Tiwari | status | To Do | Done
AKO-83 | 2026-10-24T22:34:24.391+1300 | Sandhya Tiwari | status | To Do | Done
AKO-83 | 2026-10-24T22:34:24.391+1300 | Sandhya Tiwari | resolution |  | Done
AKO-84 | 2026-10-24T22:34:27.584+1300 | Sandhya Tiwari | resolution |  | Done
AKO-84 | 2026-10-24T22:34:27.584+1300 | Sandhya Tiwari | status | To Do | Done
AKO-85 | 2026-10-24T22:34:30.775+1300 | Sandhya Tiwari | resolution |  | Done
AKO-85 | 2026-10-24T22:34:30.775+1300 | Sandhya Tiwari | status | To Do | Done
AKO-86 | 2026-10-24T22:34:33.826+1300 | Sandhya Tiwari | status | To Do | Done
AKO-86 | 2026-10-24T22:34:33.826+1300 | Sandhya Tiwari | resolution |  | Done
AKO-87 | 2026-10-24T22:34:37.046+1300 | Sandhya Tiwari | resolution |  | Done
AKO-87 | 2026-10-24T22:34:37.046+1300 | Sandhya Tiwari | status | To Do | Done
AKO-88 | 2026-10-24T22:34:40.149+1300 | Sandhya Tiwari | resolution |  | Done
AKO-88 | 2026-10-24T22:34:40.149+1300 | Sandhya Tiwari | status | To Do | Done
AKO-89 | 2026-10-24T22:34:43.170+1300 | Sandhya Tiwari | status | To Do | Done
AKO-89 | 2026-10-24T22:34:43.170+1300 | Sandhya Tiwari | resolution |  | Done
AKO-90 | 2026-10-24T22:34:46.239+1300 | Sandhya Tiwari | status | To Do | Done
AKO-90 | 2026-10-24T22:34:46.239+1300 | Sandhya Tiwari | resolution |  | Done
AKO-91 | 2026-10-24T22:34:49.539+1300 | Sandhya Tiwari | resolution |  | Done
AKO-91 | 2026-10-24T22:34:49.539+1300 | Sandhya Tiwari | status | To Do | Done
AKO-92 | 2026-10-24T22:34:52.591+1300 | Sandhya Tiwari | resolution |  | Done
AKO-92 | 2026-10-24T22:34:52.591+1300 | Sandhya Tiwari | status | To Do | Done
AKO-93 | 2026-10-24T22:34:57.901+1300 | Sandhya Tiwari | resolution |  | Done
AKO-93 | 2026-10-24T22:34:57.901+1300 | Sandhya Tiwari | status | To Do | Done
AKO-94 | 2026-10-24T22:35:01.342+1300 | Sandhya Tiwari | resolution |  | Done
AKO-94 | 2026-10-24T22:35:01.342+1300 | Sandhya Tiwari | status | To Do | Done
AKO-95 | 2026-10-24T22:35:04.418+1300 | Sandhya Tiwari | status | To Do | Done
AKO-95 | 2026-10-24T22:35:04.418+1300 | Sandhya Tiwari | resolution |  | Done
AKO-96 | 2026-10-24T22:35:07.494+1300 | Sandhya Tiwari | resolution |  | Done
AKO-96 | 2026-10-24T22:35:07.494+1300 | Sandhya Tiwari | status | To Do | Done
AKO-97 | 2026-10-24T22:35:10.501+1300 | Sandhya Tiwari | resolution |  | Done
AKO-97 | 2026-10-24T22:35:10.501+1300 | Sandhya Tiwari | status | To Do | Done
AKO-98 | 2026-10-24T22:35:13.539+1300 | Sandhya Tiwari | status | To Do | Done
AKO-98 | 2026-10-24T22:35:13.539+1300 | Sandhya Tiwari | resolution |  | Done
AKO-99 | 2026-10-24T22:35:16.490+1300 | Sandhya Tiwari | status | To Do | Done
AKO-99 | 2026-10-24T22:35:16.490+1300 | Sandhya Tiwari | resolution |  | Done
AKO-100 | 2026-10-24T22:35:19.809+1300 | Sandhya Tiwari | resolution |  | Done
AKO-100 | 2026-10-24T22:35:19.809+1300 | Sandhya Tiwari | status | To Do | Done
AKO-101 | 2026-10-24T22:35:23.111+1300 | Sandhya Tiwari | resolution |  | Done
AKO-101 | 2026-10-24T22:35:23.111+1300 | Sandhya Tiwari | status | To Do | Done
AKO-102 | 2026-10-24T22:35:26.331+1300 | Sandhya Tiwari | status | To Do | Done
AKO-102 | 2026-10-24T22:35:26.331+1300 | Sandhya Tiwari | resolution |  | Done
AKO-103 | 2026-10-27T16:18:12.719+1300 | Huanchen Wu | status | To Do | Done
AKO-103 | 2026-10-27T16:18:12.719+1300 | Huanchen Wu | resolution |  | Done
AKO-104 | 2026-10-24T22:35:29.555+1300 | Sandhya Tiwari | resolution |  | Done
AKO-104 | 2026-10-24T22:35:29.555+1300 | Sandhya Tiwari | status | To Do | Done
AKO-105 | 2026-10-27T16:18:14.646+1300 | Huanchen Wu | resolution |  | Done
AKO-105 | 2026-10-27T16:18:14.646+1300 | Huanchen Wu | status | To Do | Done
AKO-106 | 2026-10-24T23:38:47.430+1300 | Sandhya Tiwari | status | To Do | Done
AKO-106 | 2026-10-24T23:38:47.430+1300 | Sandhya Tiwari | resolution |  | Done
AKO-107 | 2026-10-27T16:18:31.595+1300 | Huanchen Wu | status | To Do | Done
AKO-107 | 2026-10-27T16:18:31.595+1300 | Huanchen Wu | resolution |  | Done
AKO-108 | 2026-10-27T16:18:34.349+1300 | Huanchen Wu | status | To Do | Done
AKO-108 | 2026-10-27T16:18:34.349+1300 | Huanchen Wu | resolution |  | Done
AKO-109 | 2026-10-27T16:18:39.421+1300 | Huanchen Wu | resolution |  | Done
AKO-109 | 2026-10-27T16:18:39.421+1300 | Huanchen Wu | status | To Do | Done
AKO-110 | 2026-10-27T16:18:41.451+1300 | Huanchen Wu | resolution |  | Done
AKO-110 | 2026-10-27T16:18:41.451+1300 | Huanchen Wu | status | To Do | Done
AKO-111 | 2026-10-25T00:45:35.487+1300 | Sandhya Tiwari | resolution |  | Done
AKO-111 | 2026-10-25T00:45:35.487+1300 | Sandhya Tiwari | status | To Do | Done
AKO-112 | 2026-10-25T00:45:38.271+1300 | Sandhya Tiwari | status | To Do | Done
AKO-112 | 2026-10-25T00:45:38.271+1300 | Sandhya Tiwari | resolution |  | Done
AKO-113 | 2026-10-25T00:45:43.326+1300 | Sandhya Tiwari | status | To Do | Done
AKO-113 | 2026-10-25T00:45:43.326+1300 | Sandhya Tiwari | resolution |  | Done
AKO-114 | 2026-10-25T00:45:46.423+1300 | Sandhya Tiwari | resolution |  | Done
AKO-114 | 2026-10-25T00:45:46.423+1300 | Sandhya Tiwari | status | To Do | Done
AKO-115 | 2026-10-25T00:45:49.482+1300 | Sandhya Tiwari | status | To Do | Done
AKO-115 | 2026-10-25T00:45:49.482+1300 | Sandhya Tiwari | resolution |  | Done
AKO-116 | 2026-10-25T00:45:52.406+1300 | Sandhya Tiwari | resolution |  | Done
AKO-116 | 2026-10-25T00:45:52.406+1300 | Sandhya Tiwari | status | To Do | Done
AKO-117 | 2026-10-25T00:45:55.410+1300 | Sandhya Tiwari | status | To Do | Done
AKO-117 | 2026-10-25T00:45:55.410+1300 | Sandhya Tiwari | resolution |  | Done
AKO-118 | 2026-10-25T00:45:58.470+1300 | Sandhya Tiwari | status | To Do | Done
AKO-118 | 2026-10-25T00:45:58.470+1300 | Sandhya Tiwari | resolution |  | Done
AKO-119 | 2026-10-25T00:46:01.378+1300 | Sandhya Tiwari | resolution |  | Done
AKO-119 | 2026-10-25T00:46:01.378+1300 | Sandhya Tiwari | status | To Do | Done
AKO-120 | 2026-10-25T00:46:04.604+1300 | Sandhya Tiwari | resolution |  | Done
AKO-120 | 2026-10-25T00:46:04.604+1300 | Sandhya Tiwari | status | To Do | Done
AKO-121 | 2026-10-25T00:46:07.482+1300 | Sandhya Tiwari | status | To Do | Done
AKO-121 | 2026-10-25T00:46:07.482+1300 | Sandhya Tiwari | resolution |  | Done
AKO-122 | 2026-10-25T00:46:10.518+1300 | Sandhya Tiwari | status | To Do | Done
AKO-122 | 2026-10-25T00:46:10.518+1300 | Sandhya Tiwari | resolution |  | Done
AKO-123 | 2026-10-25T00:46:13.500+1300 | Sandhya Tiwari | resolution |  | Done
AKO-123 | 2026-10-25T00:46:13.500+1300 | Sandhya Tiwari | status | To Do | Done
AKO-124 | 2026-10-25T00:46:16.501+1300 | Sandhya Tiwari | status | To Do | Done
AKO-124 | 2026-10-25T00:46:16.501+1300 | Sandhya Tiwari | resolution |  | Done
AKO-125 | 2026-10-27T16:18:22.414+1300 | Huanchen Wu | resolution |  | Done
AKO-125 | 2026-10-27T16:18:22.414+1300 | Huanchen Wu | status | To Do | Done
AKO-126 | 2026-10-27T16:18:27.489+1300 | Huanchen Wu | status | To Do | Done
AKO-126 | 2026-10-27T16:18:27.489+1300 | Huanchen Wu | resolution |  | Done
AKO-127 | 2026-10-25T10:03:00.202+1300 | Huanchen Wu | description |  | Define the CSV template, file size limits, validation rules, duplicate detection, row numbering, and API contract.
AKO-127 | 2026-10-26T14:30:50.189+1300 | Huanchen Wu | status | To Do | In Review
AKO-127 | 2026-10-26T14:30:59.826+1300 | Huanchen Wu | resolution |  | Done
AKO-127 | 2026-10-26T14:30:59.826+1300 | Huanchen Wu | status | In Review | Done
AKO-128 | 2026-10-25T10:03:31.125+1300 | Huanchen Wu | summary | Design CSV Import Requirements and API | Implement CSV Parsing and Validation
AKO-128 | 2026-10-25T10:03:36.801+1300 | Huanchen Wu | description |  | Implement CSV parsing, UTF-8 validation, file size checks, field validation, duplicate detection, and row-level error reporting.
AKO-128 | 2026-10-26T14:30:53.326+1300 | Huanchen Wu | status | To Do | In Review
AKO-128 | 2026-10-26T14:31:01.539+1300 | Huanchen Wu | resolution |  | Done
AKO-128 | 2026-10-26T14:31:01.539+1300 | Huanchen Wu | status | In Review | Done
AKO-129 | 2026-10-25T10:04:57.414+1300 | Huanchen Wu | description |  | Develop a Coordinator-only import API with learner creation, duplicate handling, database transactions, and import result reporting.
AKO-129 | 2026-10-26T14:30:55.776+1300 | Huanchen Wu | resolution |  | Done
AKO-129 | 2026-10-26T14:30:55.776+1300 | Huanchen Wu | status | To Do | Done
AKO-129 | 2026-10-26T14:31:19.049+1300 | Huanchen Wu | resolution | Done
AKO-129 | 2026-10-26T14:31:19.049+1300 | Huanchen Wu | status | Done | In Review
AKO-129 | 2026-10-27T09:39:20.736+1300 | Huanchen Wu | resolution |  | Done
AKO-129 | 2026-10-27T09:39:20.736+1300 | Huanchen Wu | status | In Review | Done
AKO-130 | 2026-10-25T10:08:28.316+1300 | Huanchen Wu | description |  | Create a CSV upload component with template download, file validation, upload progress, and import result display.
AKO-130 | 2026-10-26T14:31:03.972+1300 | Huanchen Wu | status | To Do | In Review
AKO-130 | 2026-10-26T14:31:21.373+1300 | Huanchen Wu | status | In Review | In Progress
AKO-130 | 2026-10-27T09:39:24.318+1300 | Huanchen Wu | resolution |  | Done
AKO-130 | 2026-10-27T09:39:24.318+1300 | Huanchen Wu | status | In Progress | Done
AKO-131 | 2026-10-25T10:09:53.374+1300 | Huanchen Wu | description |  | Add the CSV import feature to the Learners page, restrict access to Coordinators, and integrate it with existing learner management functionality.
AKO-131 | 2026-10-26T14:31:08.531+1300 | Huanchen Wu | status | To Do | In Review
AKO-131 | 2026-10-26T14:31:23.137+1300 | Huanchen Wu | status | In Review | In Progress
AKO-131 | 2026-10-27T09:39:26.514+1300 | Huanchen Wu | status | In Progress | In Review
AKO-131 | 2026-10-27T16:03:27.223+1300 | Huanchen Wu | resolution |  | Done
AKO-131 | 2026-10-27T16:03:27.223+1300 | Huanchen Wu | status | In Review | Done
AKO-132 | 2026-10-25T10:10:55.098+1300 | Huanchen Wu | description |  | Verify AC1–AC5, authentication, duplicate handling, database transactions, error reporting, and end-to-end functionality.
AKO-132 | 2026-10-26T14:31:24.689+1300 | Huanchen Wu | status | To Do | In Progress
AKO-132 | 2026-10-27T09:39:29.088+1300 | Huanchen Wu | status | In Progress | In Review
AKO-132 | 2026-10-27T16:03:30.358+1300 | Huanchen Wu | resolution |  | Done
AKO-132 | 2026-10-27T16:03:30.358+1300 | Huanchen Wu | status | In Review | Done
AKO-133 | 2026-10-25T16:16:48.307+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-133 | 2026-10-25T16:18:04.966+1300 | Pei Wu | status | To Do | In Progress
AKO-133 | 2026-10-25T16:21:28.220+1300 | Pei Wu | resolution |  | Done
AKO-133 | 2026-10-25T16:21:28.220+1300 | Pei Wu | status | In Progress | Done
AKO-134 | 2026-10-25T16:17:10.345+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-134 | 2026-10-25T16:21:48.359+1300 | Pei Wu | status | To Do | In Progress
AKO-134 | 2026-10-25T16:37:38.375+1300 | Pei Wu | resolution |  | Done
AKO-134 | 2026-10-25T16:37:38.375+1300 | Pei Wu | status | In Progress | Done
AKO-135 | 2026-10-25T16:17:23.670+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-135 | 2026-10-25T16:37:50.930+1300 | Pei Wu | status | To Do | Done
AKO-135 | 2026-10-25T16:37:50.930+1300 | Pei Wu | resolution |  | Done
AKO-136 | 2026-10-25T16:17:35.788+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-136 | 2026-10-25T16:37:54.838+1300 | Pei Wu | status | To Do | In Progress
AKO-136 | 2026-10-25T16:55:49.299+1300 | Pei Wu | status | In Progress | Done
AKO-136 | 2026-10-25T16:55:49.299+1300 | Pei Wu | resolution |  | Done
AKO-137 | 2026-10-25T16:17:48.020+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-137 | 2026-10-25T17:03:25.453+1300 | Pei Wu | status | To Do | Done
AKO-137 | 2026-10-25T17:03:25.453+1300 | Pei Wu | resolution |  | Done
AKO-138 | 2026-10-25T16:17:59.514+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-138 | 2026-10-25T17:03:28.470+1300 | Pei Wu | status | To Do | In Progress
AKO-138 | 2026-10-25T17:14:45.510+1300 | Pei Wu | resolution |  | Done
AKO-138 | 2026-10-25T17:14:45.510+1300 | Pei Wu | status | In Progress | Done
AKO-139 | 2026-10-25T17:21:35.319+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-139 | 2026-10-25T17:22:42.142+1300 | Pei Wu | status | To Do | In Progress
AKO-139 | 2026-10-25T17:27:41.862+1300 | Pei Wu | resolution |  | Done
AKO-139 | 2026-10-25T17:27:41.862+1300 | Pei Wu | status | In Progress | Done
AKO-140 | 2026-10-25T17:21:48.362+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-140 | 2026-10-25T17:29:05.251+1300 | Pei Wu | status | To Do | In Progress
AKO-140 | 2026-10-25T17:34:06.092+1300 | Pei Wu | resolution |  | Done
AKO-140 | 2026-10-25T17:34:06.092+1300 | Pei Wu | status | In Progress | Done
AKO-141 | 2026-10-25T17:21:59.840+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-141 | 2026-10-25T17:36:21.678+1300 | Pei Wu | status | To Do | In Progress
AKO-141 | 2026-10-25T17:42:29.921+1300 | Pei Wu | resolution |  | Done
AKO-141 | 2026-10-25T17:42:29.921+1300 | Pei Wu | status | In Progress | Done
AKO-142 | 2026-10-25T17:22:12.889+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-142 | 2026-10-25T17:42:34.389+1300 | Pei Wu | status | To Do | In Progress
AKO-142 | 2026-10-25T21:01:32.740+1300 | Pei Wu | status | In Progress | Done
AKO-142 | 2026-10-25T21:01:32.740+1300 | Pei Wu | resolution |  | Done
AKO-143 | 2026-10-25T17:22:25.358+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-143 | 2026-10-25T21:01:51.829+1300 | Pei Wu | status | To Do | In Progress
AKO-143 | 2026-10-25T21:12:11.145+1300 | Pei Wu | resolution |  | Done
AKO-143 | 2026-10-25T21:12:11.145+1300 | Pei Wu | status | In Progress | Done
AKO-144 | 2026-10-25T17:22:39.298+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-144 | 2026-10-25T21:12:13.504+1300 | Pei Wu | status | To Do | In Progress
AKO-144 | 2026-10-25T21:35:02.809+1300 | Pei Wu | status | In Progress | Done
AKO-144 | 2026-10-25T21:35:02.809+1300 | Pei Wu | resolution |  | Done
AKO-145 | 2026-10-26T10:36:15.425+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-145 | 2026-10-26T10:36:39.160+1300 | Pei Wu | status | To Do | In Progress
AKO-145 | 2026-10-26T20:22:16.632+1300 | Pei Wu | resolution |  | Done
AKO-145 | 2026-10-26T20:22:16.632+1300 | Pei Wu | status | In Progress | Done
AKO-146 | 2026-10-26T10:36:33.596+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-146 | 2026-10-26T13:44:14.464+1300 | Pei Wu | status | To Do | In Progress
AKO-146 | 2026-10-26T14:01:31.423+1300 | Pei Wu | resolution |  | Done
AKO-146 | 2026-10-26T14:01:31.423+1300 | Pei Wu | status | In Progress | Done
AKO-147 | 2026-10-27T12:51:42.537+1300 | Pei Wu | assignee | Huanchen Wu | Pei Wu
AKO-147 | 2026-10-27T12:51:45.346+1300 | Pei Wu | status | To Do | Done
AKO-147 | 2026-10-27T12:51:45.346+1300 | Pei Wu | resolution |  | Done

## Sprint Changes
Issue | Date | Author | Field | From | To
AKO-8 | 2026-10-19T20:07:08.645+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 2
AKO-9 | 2026-10-19T20:07:14.764+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 2
AKO-9 | 2026-10-24T09:05:00.490+1300 | Huanchen Wu | Sprint | SCRUM Sprint 2 | SCRUM Sprint 2, SCRUM Sprint 3
AKO-10 | 2026-10-19T20:07:17.663+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 2
AKO-11 | 2026-10-19T20:07:23.348+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 2
AKO-11 | 2026-10-24T09:05:00.803+1300 | Huanchen Wu | Sprint | SCRUM Sprint 2 | SCRUM Sprint 2, SCRUM Sprint 3
AKO-12 | 2026-10-19T20:07:35.580+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 2
AKO-13 | 2026-10-19T20:07:54.130+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 3
AKO-14 | 2026-10-19T20:08:17.249+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 3
AKO-14 | 2026-10-21T16:41:09.859+1300 | Huanchen Wu | Sprint | SCRUM Sprint 3 | SCRUM Sprint 2
AKO-14 | 2026-10-24T09:05:01.066+1300 | Huanchen Wu | Sprint | SCRUM Sprint 2 | SCRUM Sprint 2, SCRUM Sprint 3
AKO-15 | 2026-10-19T20:08:17.496+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 3
AKO-16 | 2026-10-25T11:26:18.727+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 3
AKO-17 | 2026-10-25T11:26:25.824+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 3
AKO-18 | 2026-10-23T19:55:32.759+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 3
AKO-19 | 2026-10-26T18:42:53.349+1300 | Shuohui Liu | Sprint |  | SCRUM Sprint 3
AKO-20 | 2026-10-25T11:27:51.898+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 3
AKO-21 | 2026-10-19T20:08:17.698+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 3
AKO-22 | 2026-10-25T11:27:56.151+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 3
AKO-23 | 2026-10-26T21:22:24.768+1300 | Shuohui Liu | Sprint |  | SCRUM Sprint 3
AKO-24 | 2026-10-23T19:55:40.010+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 3
AKO-26 | 2026-10-19T20:23:50.087+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 1
AKO-27 | 2026-10-19T20:24:04.405+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 1
AKO-28 | 2026-10-19T20:24:04.678+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 1
AKO-29 | 2026-10-19T20:24:04.897+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 1
AKO-30 | 2026-10-19T20:24:05.105+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 1
AKO-31 | 2026-10-19T20:24:05.313+1300 | Huanchen Wu | Sprint |  | SCRUM Sprint 1

## Worklogs
Issue | Author | Started | Seconds | Created

## Team Contributions
Member | Assigned | Currently Done | Changes Authored | Worklog Hours
(Unassigned) | 5 | 5 | 0 | 0
Huanchen Wu | 29 | 29 | 219 | 0
Pei Wu | 35 | 35 | 94 | 0
Sandhya Tiwari | 69 | 69 | 104 | 0
Shuohui Liu | 6 | 6 | 16 | 0