Ako Project — Scrum, Sprint Planning and Team Responsibilities

By Leon wu

Community English Club Management System  |  MVP v1.0  |  Proposed delivery: 28 October 2026

Status: Proposed for team approval. Story assignments, scope, capacity and final requirement approval remain subject to confirmation.

1. Scrum Approach

One Scrum Team (four members) will work through three short Sprints. Jira hierarchy: Epic → User Story → Subtask. Each Story has one Story Owner coordinating requirements and acceptance; each Subtask has an individual Assignee responsible for delivery. Story Owner is a team convention, not a formal Scrum accountability.

2. Scrum Responsibilities

| Role | Leader | Main responsibilities |
| --- | --- | --- |
| Scrum Master / Project Coordinator | Leon | Jira configuration; facilitate Scrum events; Sprint planning and blockers |
| Product Owner / Requirements Coordinator | Sandhya | Prioritise Product Backlog; coordinate stakeholder feedback; clarify business requirements |
| Technical Lead | Michael | Architecture; GitHub; coding standards; integration and code review |
| QA & Acceptance Coordinator | Pei Wu | Test plan; acceptance criteria verification; defects and testing evidence |

Final business requirement approval authority: PENDING CONFIRMATION with the team and stakeholder. Sandhya coordinates confirmation; neither Sandhya nor Pei should be described as having stakeholder approval without agreement. All four members contribute to development, review, testing and Scrum events.

3. Story Ownership

| Epic | Story | Story Owner | Target Sprint |
| --- | --- | --- | --- |
| Accounts and Access | US-001 Volunteer Login | Leon | 1 |
| Accounts and Access | US-002 Manage Teacher Accounts and Roles | Leon | 3 |
| Learners and Attendance | US-003 Manage Learner Records | Pei | 1 |
| Learners and Attendance | US-014 Manage Class Sessions | Michael | 2 |
| Learners and Attendance | US-004 Manual Attendance Check-in | Pei | 2 |
| Learners and Attendance | US-005 Export Attendance Records | Michael | 3 |
| Lesson Library | US-006 Create Lessons and Upload Materials | Sandhya | 1 (scope review) |
| Lesson Library | US-008 Flag Māori Content for Review | Pei | 3 (consultation dependent) |

Story Owners coordinate acceptance; technical work is assigned across the team through Subtasks. See Appendix A for the complete Epic and Story breakdown.

4. Example Subtask Assignment — US-004

| Subtask | Assignee | Preliminary effort |
| --- | --- | --- |
| Define acceptance criteria and test cases | Pei | 2 h |
| Design attendance database model | Michael | 3 h |
| Implement attendance backend | Leon | 5 h |
| Develop attendance UI | Sandhya | 4 h |
| Execute tests and verify acceptance | Pei | 3 h |
| TOTAL |  | 17 h |

Estimates are illustrative and must be validated in Sprint Planning. Story Points are not equivalent to hours.

5. Three-Sprint Delivery Plan

| Period | Sprint Goal / Work | Review & Retrospective |
| --- | --- | --- |
| 14–15 Oct — Project Setup | Working application skeleton, GitHub workflow, Jira backlog, acceptance criteria and basic tests; begin cultural consultation | Not a formal Sprint |
| 16–19 Oct — Sprint 1 | Foundation: US-001, US-003, US-006. Demonstrate volunteer login, learner records and lesson creation. Split US-006 into independently testable Stories before planning if file uploads exceed capacity. | 19 Oct |
| 20–23 Oct — Sprint 2 | Attendance workflow: US-014, US-004. Demonstrate dated class session, walk-in learner selection/addition, manual attendance and corrections. | 23 Oct |
| 24–27 Oct — Sprint 3 | MVP enhancements: US-002, US-005, US-008 subject to capacity and consultation; integration, testing and prioritised improvements. | 28 Oct |
| 28 Oct — Final Delivery | Regression tests; runnable ZIP; project and reflection reports; demonstration and submission checks. | Delivery checkpoint |

These are short four-calendar-day Sprints, including weekends. Confirm each member’s actual availability before committing scope. Protect the core login → lesson → session → learner → attendance workflow. If capacity is insufficient, renegotiate enhancement scope rather than bypass testing or necessary cultural/privacy safeguards.

6. Scrum Events

| Event | Cadence | Duration / outcome |
| --- | --- | --- |
| Sprint Planning | Start of each Sprint | 30–45 min; Sprint Goal, capacity, selected Stories, Subtasks |
| Daily Scrum | Each development day | 10–15 min; inspect progress and adapt plan |
| Backlog Refinement | As needed | 15–30 min; clarify and estimate upcoming Stories |
| Sprint Review | 19, 23, 27 Oct | 20–30 min; demo working increment and gather feedback |
| Sprint Retrospective | 19, 23, 27 Oct | 15–20 min; agree improvement actions and owners |

Existing twice-weekly Teams meetings may host these events where timing permits; avoid duplicate meetings. A Sprint ends at the end of its timebox, not when documentation is finished.

7. Jira Workflow and Definition of Done

Workflow: To Do → In Progress → In Review → Done. Mark a Story Done only when acceptance criteria are met, code is reviewed and integrated, relevant tests pass, and the Story Owner verifies the result. Log estimated/actual hours, blockers and links to GitHub Pull Requests.

8. Sprint Goals, Review and Retrospective Records

Record each Sprint Goal in Jira. Use the Story Assignee field for Story Owner (or an agreed custom field); assign each Subtask to its implementer. Save Sprint Review and Retrospective notes in docs/sprints/ and link from Jira.

| Sprint Review record | Sprint Retrospective record |
| --- | --- |
| Sprint name, dates, original Goal | What went well? |
| Completed and incomplete Stories; evidence of demos | What could improve? |
| Stakeholder feedback and resulting backlog changes | Specific improvement action, owner and due date |

Record actual results rather than presenting planned features as complete. Finish Review and Retrospective within each Sprint timebox; check previous improvement actions at the next Sprint.

9. Project Requirement Coverage and Evidence

| Assessment / requirement area | Planned evidence | Lead |
| --- | --- | --- |
| Requirements analysis | Interview notes, prioritised backlog, traceability matrix (requirement → Story → acceptance criteria → test) | Sandhya; Pei supports |
| Agile delivery | Sprint Goals, Jira history, Reviews, Retrospectives, PRs and demos | Leon |
| Cost estimation | Estimated/actual labour hours × stated assumed rates; tools, resources and contingency; estimate-vs-actual summary | Leon; everyone logs time |
| Testing and acceptance | Test plan, test results, defects, acceptance evidence | Pei |
| Te Tiriti / Māori perspectives | Document actual partnership, participation and protection considerations; cultural consultation outcomes and review rules | Sandhya coordinates; Pei documents tests |
| Project Report, Reflection Report, source ZIP | PDF reports and runnable source files, setup instructions and test evidence | Leon coordinates reports; Michael coordinates ZIP |

Consultation with Kaiārahi / appropriate cultural adviser and stakeholder approval must be documented as actually conducted; do not imply endorsement before it is received. Use synthetic learner data and minimal personal information in demonstrations.

10. Final Responsibility Matrix (Proposed)

| Activity / deliverable | Lead | Support |
| --- | --- | --- |
| Requirements Analysis | Sandhya | Pei |
| Product Backlog & Prioritisation | Leon | Sandhya |
| Stakeholder Feedback & Approval Coordination | Sandhya | Pei; approval authority pending |
| Jira & Scrum Management | Leon | All members |
| Architecture, GitHub & Coding Standards | Michael | Leon |
| Application Development | All members | Michael coordinates integration |
| Testing & Acceptance | Pei | All members |
| Cost Estimation | Leon | All members provide effort data |
| Cultural Consultation Coordination | Sandhya | Pei |
| Project Report | Leon coordinates | All members contribute |
| Reflection Report | Leon coordinates | All members contribute |
| Final Integration & Source ZIP | Michael | All members |

11. MVP Completion and Immediate Decisions

Core workflow: authorised volunteer login → lesson creation → dated class session → select or add walk-in learner → record/correct attendance. Reporting and account administration are planned enhancements; agreed security, privacy and cultural safeguards remain mandatory. QR attendance, learner accounts, exams, payments and pronunciation scoring are outside the MVP.

Before Sprint 1: confirm final approval authority, technology stack, Story Owners, team capacity (including weekends), estimates, cultural consultation plan and acceptance criteria. The proposed plan is not evidence that stakeholder approval has occurred.

Appendix A — Epic and User Story Breakdown

This appendix documents the proposed requirements-to-Jira breakdown for MVP v1.0. Story descriptions and acceptance checks are working drafts to be validated with the stakeholder. US-014 is a new session-management Story. No advance learner enrolment or learner accounts are required.

Epic 1 — Accounts and Access

US-001 — Volunteer Login

User story: As an authorised volunteer, I want to log in securely so that I can access permitted club functions.

Proposed acceptance checks: Login succeeds for valid accounts; invalid credentials are rejected; role-based access is enforced.

Story Owner: Leon

US-002 — Manage Teacher Accounts and Roles

User story: As a coordinator, I want to manage volunteer accounts and roles so that authorised people have appropriate access.

Proposed acceptance checks: Coordinator can create, update and deactivate accounts; role changes affect permissions.

Story Owner: Leon

Epic 2 — Learners and Attendance

US-003 — Manage Learner Records

User story: As a teacher, I want to maintain minimal learner records so that I can identify returning learners.

Proposed acceptance checks: Add, view and edit learner records; validate required fields; minimise personal data.

Story Owner: Pei

US-014 — Manage Class Sessions

User story: As a teacher, I want to create dated class sessions so that attendance is recorded against a specific meeting.

Proposed acceptance checks: Create and view sessions; associate a lesson; preserve sessions with attendance.

Story Owner: Michael

US-004 — Manual Attendance Check-in

User story: As a teacher, I want to mark learners present at a class session so that participation is recorded without advance enrolment.

Proposed acceptance checks: Select existing or add walk-in learner; record/correct attendance; prevent duplicate learner-session entries.

Story Owner: Pei

US-005 — Export Attendance Records

User story: As authorised staff, I want to export attendance records so that I can prepare reports.

Proposed acceptance checks: Filter by date/session; export accurate CSV or agreed format; restrict access.

Story Owner: Michael

Epic 3 — Lesson Library

US-006 — Create Lessons and Upload Materials

User story: As a teacher, I want to create lessons and attach teaching materials so that I can prepare and reuse class resources.

Proposed acceptance checks: Create/edit lesson; upload validated supported files within agreed limits; staff-only access in current MVP.

Story Owner: Sandhya

US-008 — Flag Māori Content for Review

User story: As an authorised volunteer, I want to flag Māori-related content for review so that cultural materials follow an agreed process.

Proposed acceptance checks: Flag and track review status; implement only consultation-confirmed rules; do not claim unverified approval.

Story Owner: Pei

Appendix B — Requirement Traceability Starter

| Requirement | Jira Story | Acceptance / test focus |
| --- | --- | --- |
| Authorised access | US-001 / US-002 | Login, role restrictions and account administration |
| Walk-in learner management | US-003 | Create or select learner without enrolment |
| Dated class meetings | US-014 | Create session linked to lesson |
| Manual attendance | US-004 | Mark, correct and deduplicate attendance |
| Reporting | US-005 | Accurate authorised export |
| Teaching resources | US-006 | Lesson creation and secure material upload |
| Māori content protection | US-008 | Consultation-confirmed review handling |