## Sprint 2 Overview
Metric | Value
Total Stories | 6
Completed | 3
Incomplete | 3
Completion Rate | 50%
Closed At | 24 Oct 2026 09:05 NZDT

## Completion Split
Outcome | Stories
Completed | 3
Incomplete | 3

## Sprint Comparison
Sprint | Completion Rate | Status basis
Sprint 1 | 100% | Current snapshot (Active)
Sprint 2 | 50% | At closure (Closed)
Sprint 3 | 12.5% | Current snapshot (Active)

## Story Ownership
Assignee | Stories
Leon / Huanchen Wu | 2
Pei Wu | 2
Sandhya Tiwari | 1
Shuohui Liu | 1

## Closure Status
Status | Stories
Done | 3
In Progress | 1
In Review | 1
To Do | 1

## Sprint 2 Stories
Issue | Story | Owner | At closure | Current status
AKO-8 | US-001 Log in by role | Leon / Huanchen Wu | Done | Done
AKO-9 | US-002 Manage staff accounts | Leon / Huanchen Wu | In Progress | Done
AKO-10 | US-003 Keep learner records | Pei Wu | Done | Done
AKO-11 | US-014 Manage class sessions | Shuohui Liu | To Do | To Do
AKO-12 | US-004 Record attendance by hand | Pei Wu | Done | Done
AKO-14 | US-006 Create a lesson | Sandhya Tiwari | In Review | In Review

## Reading Notes
Topic | Explanation
Source | Ako_Project_History(2).xlsx supplied by user
Sprint 2 basis | Reconstructed issue statuses at Sprint 2 close
Sprint 1 and 3 basis | Current snapshot; active Sprints, not final outcomes
Ownership | Current Jira assignee; not a measure of actual coding contribution
Limitations | Sprint association and reconstructed status depend on Jira export history