Sprint 2 Retrospective

Ako MSE800  |  Sprint 2  |  19–23 October 2026  |  Closed 24 October 2026

1. Sprint Overview

Sprint goal: Deliver core MVP functions covering role-based login, staff account management, learner records, manual attendance, class sessions, and lesson creation.

At Sprint closure, 3 of 6 associated stories were Done (50%). One story remained In Progress, one In Review, and one To Do. AKO-9 reached Done after Sprint closure.

| Metric | Value | Basis |
| --- | --- | --- |
| Stories | 6 | Associated with Sprint 2 |
| Done | 3 | At Sprint closure |
| Completion rate | 50% | At Sprint closure |
| Incomplete | 3 | At Sprint closure |

2. Story Status at Sprint Closure

| Issue | User story | Owner | Closure status |
| --- | --- | --- | --- |
| AKO-8 | Log in by role | Leon | Done |
| AKO-9 | Manage staff accounts | Leon | In Progress |
| AKO-10 | Keep learner records | Pei | Done |
| AKO-11 | Manage class sessions | Shuohui Liu | To Do |
| AKO-12 | Record attendance by hand | Pei | Done |
| AKO-14 | Create a lesson | Sandhya | In Review |

3. Statistical Findings

Figure 1 — Completion split: 3 Done and 3 incomplete stories (50% each).

Figure 2 — Cross-Sprint comparison: Sprint 1 100%, Sprint 2 50%, Sprint 3 12.5%. Only Sprint 2 represents a closed-Sprint result; Sprint 1 and 3 are active-Sprint snapshots and should not be compared as final outcomes.

Figure 3 — Sprint 2 story ownership: Leon 2, Pei 2, Sandhya 1, Shuohui Liu 1.

Figure 4 — Closure status: Done 3, In Progress 1, In Review 1, To Do 1.

The four editable charts are provided in the accompanying Excel workbook for insertion into Confluence.

4. What Went Well

Three core stories reached Done by closure: login, learner records, and manual attendance.

Jira provided visible ownership and progress tracking.

Stories and subtasks supported structured task management.

5. What Did Not Go Well

Three of six stories were unfinished at closure.

Some tasks required more technical investigation than expected.

Reviews and development progress were not evenly distributed.

6. Lessons Learned

Break stories into smaller subtasks with clear acceptance criteria.

Identify technical dependencies before Sprint commitment.

Begin review and integration testing earlier, and keep Jira statuses current.

7. Proposed Action Items

| Action | Proposed owner |
| --- | --- |
| Reassess outstanding stories and Sprint priorities | Leon |
| Coordinate code integration and technical dependencies | Michael |
| Review acceptance criteria and testing readiness | Pei |
| Follow up on lesson creation and requirements | Sandhya |

8. Next Sprint Improvements

Prioritise carry-over stories, improve estimates, surface blockers earlier, schedule regular code reviews, and verify task status before closing each Sprint.

Evidence note: Metrics are based on the user-provided Jira export. Retrospective observations and proposed actions should be validated by the team during the meeting.