## Sprint 3 Overview
Metric | Value
Total Stories | 14
Completed | 14
Incomplete | 0
Completion Rate | 1
Status Basis | 29 Oct: 100% Done; Active retained for Board/Backlog access

## Completion Split
Outcome | Stories
Completed | 14
Incomplete | 0

## Sprint Comparison
Sprint | Completion Rate | Status basis
Sprint 1 | 1 | Current snapshot (Active)
Sprint 2 | 0.5 | At actual closure (Closed)
Sprint 3 | 1 | 100% Done; Active retained for reporting access

## Story Ownership
Assignee | Stories
Leon / Huanchen Wu | 3
Pei Wu | 3
Sandhya Tiwari | 4
Michael / Shuohui Liu | 4

## Current Status
Status | Stories
Done | 14
In Progress | 0
In Review | 0
To Do | 0

## Sprint 3 Stories
Issue | Story | Owner | Current status
AKO-11 | US-014 Manage class sessions | Michael / Shuohui Liu | Done
AKO-13 | US-005 Print attendance record | Michael / Shuohui Liu | Done
AKO-14 | US-006 Create a lesson | Sandhya Tiwari | Done
AKO-15 | US-008 Flag Māori content for review | Pei Wu | Done
AKO-16 | US-007 Find and copy lessons | Sandhya Tiwari | Done
AKO-17 | US-009 View club information | Sandhya Tiwari | Done
AKO-18 | US-010 Register interest in classes | Leon / Huanchen Wu | Done
AKO-19 | US-011 Open check-in with a QR code | Michael / Shuohui Liu | Done
AKO-20 | US-012 Sign in by scanning the QR code | Pei Wu | Done
AKO-21 | US-013 Access shared lesson materials after signing in | Sandhya Tiwari | Done
AKO-22 | US-015 Correct a past attendance record | Pei Wu | Done
AKO-23 | US-016 View a learner's attendance history | Michael / Shuohui Liu | Done
AKO-24 | US-017 Import learners from a CSV file | Leon / Huanchen Wu | Done
AKO-9 | US-002 Manage staff accounts | Leon / Huanchen Wu | Done

## Reading Notes
Topic | Explanation
Source | Ako_Project_History_Oct29(1).xlsx
Sprint 3 basis | All 14 Stories Done; Jira kept Active intentionally for Backlog/Board visibility
Sprint 2 basis | Reconstructed at actual closure
Ownership | Current Jira assignee; not an effort metric
Carry-over | AKO-9, AKO-11 and AKO-14 also linked to Sprint 2