MSE800 | Agile-Based Project Schedule

Project period: 10–28 October 2026  |  Submission deadline: 29 October 2026
Team size: 4  |  Proposed tools: Jira (tentative), GitHub

1. Project Objective and Delivery Approach

Deliver a working, demonstrable minimum viable product (MVP) by 28 October 2026, allowing a final submission on 29 October. The team will use a lightweight Agile approach combining short sprints, a Jira Kanban board, frequent progress reporting, continuous code review, and iterative testing. Scope will remain limited to essential, testable features.

2. Sprint Timeline

| Phase | Dates | Expected outcome |
| --- | --- | --- |
| Sprint 0 – Planning & Setup | 10–12 Oct | Scope and MVP, initial backlog, technical stack, Jira and GitHub setup |
| Sprint 1 – Core Development | 13–19 Oct | Core functionality and first working demonstration |
| Sprint 2 – Integration & Testing | 20–25 Oct | Integrated features, code reviews, functional and integration tests |
| Finalisation & Delivery | 26–28 Oct | Bug fixes, regression testing, documentation, final demo and submission package |

2A. Phase Deliverables and Acceptance Evidence

Each phase must produce reviewable artefacts, not only completed activities. The first four planning documents are targeted for completion before 12 October 2026 (by 11 October). Owners and deadlines remain subject to team confirmation.

| Phase / Due | Deliverables (proposed lead) | Review / completion evidence |
| --- | --- | --- |
| Initial baseline · by 12Oct | Project schedule and milestones (Leon); coding standards (Michael); GitHub code management / branching and PR rules (Michael); requirements outline and interview report or initial interview findings (Sandhya / Pei) | Shared files linked in Jira; initial team review; interview report distinguishes completed interviews from pending interviews. |
| Sprint 0 · 10–12 Oct | MVP scope and exclusions; prioritised requirements / user stories; Jira board and initial backlog; technical stack decision record; GitHub repository; architecture and data model draft | Team approval of MVP and technical choices; stories have acceptance criteria; repository and board accessible. |
| Sprint 1 · 13–19 Oct | Updated requirements baseline; UI / API / database design; implemented core modules; pull requests and review records; unit-test cases and results; first working demo; Sprint 1 review notes | Core end-to-end path demonstrated; changes recorded; reviewed code merged; known issues logged. |
| Sprint 2 · 20–25 Oct | Integrated MVP build; integration-test report; updated test cases; defect log; requirements change log and impact decisions; code review / merge evidence; user acceptance feedback | Major flows pass agreed acceptance tests; critical defects assigned; no new non-essential features after 22 Oct. |
| Finalisation · 26–28 Oct | Regression-test summary; resolved defect list and known limitations; final source code and README; installation / user guide; final requirements traceability; demo script / slides; retrospective; submission checklist and package | Reproducible setup and demonstration; required documents checked; final team sign-off by 28 Oct. |

2B. Priority Deliverables Due Before 13October

| Deliverable | Proposed owner | Target | Minimum content |
| --- | --- | --- | --- |
| Project schedule | Leon | 12 Oct | Timeline, sprint plan, owners, milestones, dependencies |
| Coding standards | Michael | 13Oct | Naming, formatting, structure, tests, review checklist |
| Code management standards | Michael | 13Oct | GitHub branching, commit rules, PRs, merges, conflict resolution |
| Requirements outline & interview report | Sandhya / Pei | 13Oct | Stakeholders, questions, findings, assumptions, initial requirements; flag pending interviews |

3. Detailed Work Schedule

| Activity | Dates | Lead / participants |
| --- | --- | --- |
| Project scope and MVP definition | 10–11 Oct | All members |
| Requirements analysis and user stories | 11–14 Oct | Sandhya / Pei |
| Agile workflow and Jira board setup | 11–12 Oct | Leon |
| Technical stack selection | 11–13 Oct | Michael/Leon |
| GitHub repository and coding standards | 12–13 Oct | Michael |
| Architecture and database design | 13–15 Oct | Michael / Leon |
| Core feature development | 14–22 Oct | All developers |
| Requirements changes and backlog updates | 14–25 Oct | Leon / Sandhya / Pei |
| Code review and integration | 16–25 Oct | Michael / Developers |
| Unit and integration testing | 18–26 Oct | All members |
| Bug fixing and regression testing | 23–27 Oct | All members |
| Documentation and presentation preparation | 24–28 Oct | All members |
| Final review and submission readiness | 28 Oct | All members |

Note: Requirements refinement, development, code review, and testing overlap. Owners are proposed and subject to team confirmation.

4. Proposed Team Responsibilities

| Member | Primary responsibilities | Additional contribution |
| --- | --- | --- |
| Leon | Agile coordination, sprint planning, Jira tracking | Architecture, Technical stack, coding, integration |
| Michael | Technical stack, coding standards, GitHub workflow | Core development, code review |
| Sandhya | Customer communication, requirements analysis | Development, acceptance testing |
| Pei | User stories, requirement updates, documentation | Development, testing |

5. Agile Workflow and Communication

Sprint planning: 11, 14, and 20 October: confirm sprint goals, prioritise backlog items, assign owners and review capacity.

Daily updates: Each member posts completed work, blockers, and next steps in the team chat before 7:00 PM each day.

Online meetings: Hold at least two online meetings per week; exact times are agreed based on progress and availability.

Jira Kanban workflow: Each task should have an owner, due date, acceptance criteria and status.

GitHub code review: Use feature branches and pull requests; obtain peer review before merging into the main branch.

Testing and change control: Test features as they are developed. Record changes as Jira backlog items, assess impact on the MVP and reprioritise during team meetings.

6. Key Milestones

| Date | Milestone |
| --- | --- |
| 13 Oct | Project scope, technical stack and Agile tools confirmed |
| 19 Oct | Core features implemented; first working demo |
| 22 Oct | Feature freeze: no new non-essential features |
| 25 Oct | Integration and major testing completed |
| 27 Oct | Critical bugs fixed; documentation finalised |
| 28 Oct | Final review and submission-ready package |

7. Scope, Quality and Risks

Prioritise one complete end-to-end user journey rather than numerous incomplete features. Incorporate relevant Māori perspectives and cultural considerations in requirements and acceptance criteria where appropriate to the assignment. Maintain a clear Definition of Done: code reviewed, tests passed, acceptance criteria met, and Jira updated.

Key risks include scope creep, integration conflicts, uneven workloads, and limited testing time. Mitigations are MVP prioritisation, early GitHub integration, shared coding standards, daily blocker reporting, and a 22 October feature freeze.

8. Immediate Next Steps

Review the four priority planning deliverables by 13 October; confirm the MVP and individual development assignments; finalise the technical stack; create the Jira project and GitHub repository; convert requirements into prioritised user stories; and approve this baseline schedule at the next team meeting.

*MVP: The simplest version of a product that includes only the essential features needed to deliver value and validate the core idea.