## Gantt Chart
MSE800 ¦ Agile Project Gantt Chart
10–28 October 2026 • Deadline: 29 October • 4 members • Jira (proposed)
Key | Task / Activity | Workstream | Owner | Start | Finish | Days | Status | Progress | Dependency | 11 Oct | 12 Oct | 13 Oct | 14 Oct | 15 Oct | 16 Oct | 17 Oct | 18 Oct | 19 Oct | 20 Oct | 21 Oct | 22 Oct | 23 Oct | 24 Oct | 25 Oct | 26 Oct | 27 Oct | 28 Oct
MSE800-01 | Project schedule and milestones | Planning | Leon | 2026-10-10 | 2026-10-12 | 3 | To Do | 0% | bar: 11 Oct to 12 Oct; 18 Oct; 24 Oct to 25 Oct
MSE800-02 | Coding standards document | Technical Setup | Michael | 2026-10-10 | 2026-10-13 | 4 | To Do | 0% | bar: 11 Oct to 14 Oct; 18 Oct; 24 Oct to 25 Oct
MSE800-03 | Code management / GitHub rules | Technical Setup | Michael | 2026-10-10 | 2026-10-13 | 4 | To Do | 0% | bar: 12 Oct to 15 Oct; 18 Oct; 24 Oct to 25 Oct
MSE800-04 | Requirements outline & interview report | Requirements | Sandhya / Pei | 2026-10-10 | 2026-10-13 | 4 | To Do | 0% | bar: 11 Oct to 12 Oct; 18 Oct; 24 Oct to 25 Oct
MSE800-05 | MVP scope and exclusions | Planning | All members | 2026-10-10 | 2026-10-12 | 3 | To Do | 0% | MSE800-04 | bar: 11 Oct to 13 Oct; 18 Oct; 24 Oct to 25 Oct
MSE800-06 | Jira board and prioritised backlog | Planning | Leon | 2026-10-11 | 2026-10-12 | 2 | To Do | 0% | MSE800-05 | bar: 12 Oct to 13 Oct; 18 Oct; 24 Oct to 25 Oct
MSE800-07 | Technical stack decision record | Technical Setup | Michael / Leon | 2026-10-11 | 2026-10-12 | 2 | To Do | 0% | MSE800-05 | bar: 13 Oct to 15 Oct; 18 Oct; 24 Oct to 25 Oct
MSE800-08 | GitHub repository setup | Technical Setup | Michael | 2026-10-12 | 2026-10-13 | 2 | To Do | 0% | MSE800-03 | bar: 14 Oct to 19 Oct; 24 Oct to 25 Oct
MSE800-09 | Requirements analysis and user stories | Requirements | Sandhya / Pei | 2026-10-11 | 2026-10-14 | 4 | To Do | 0% | MSE800-04 | bar: 14 Oct to 19 Oct; 24 Oct to 25 Oct
MSE800-10 | Architecture, UI/API and data model design | Technical Setup | Michael / Leon | 2026-10-13 | 2026-10-15 | 3 | To Do | 0% | MSE800-07 | bar: 15 Oct to 19 Oct; 24 Oct to 25 Oct
MSE800-11 | Core feature development — Leon | Development | Leon | 2026-10-14 | 2026-10-22 | 9 | To Do | 0% | MSE800-10 | bar: 15 Oct to 19 Oct; 24 Oct to 25 Oct
MSE800-12 | Core feature development — Michael | Development | Michael | 2026-10-14 | 2026-10-22 | 9 | To Do | 0% | MSE800-10 | bar: 18 Oct to 19 Oct; 24 Oct to 25 Oct
MSE800-13 | Core feature development — Sandhya | Development | Sandhya | 2026-10-14 | 2026-10-22 | 9 | To Do | 0% | MSE800-09 | bar: 18 Oct; 20 Oct to 22 Oct; 24 Oct to 25 Oct
MSE800-14 | Core feature development — Pei | Development | Pei | 2026-10-14 | 2026-10-22 | 9 | To Do | 0% | MSE800-09 | bar: 18 Oct; 20 Oct to 25 Oct
MSE800-15 | Requirements changes and backlog updates | Requirements | Leon / Sandhya / Pei | 2026-10-14 | 2026-10-25 | 12 | To Do | 0% | MSE800-09 | bar: 14 Oct to 25 Oct
MSE800-16 | Code review, pull requests and integration | Quality | Michael / Developers | 2026-10-16 | 2026-10-25 | 10 | To Do | 0% | MSE800-08 | bar: 16 Oct to 25 Oct
MSE800-17 | Unit tests and test results | Quality | All members | 2026-10-18 | 2026-10-26 | 9 | To Do | 0% | MSE800-11 | bar: 18 Oct to 25 Oct
MSE800-18 | First working demo and Sprint 1 review | Agile | All members | 2026-10-19 | 2026-10-19 | 1 | To Do | 0% | MSE800-11 | bar: 18 Oct; 22 Oct to 26 Oct
MSE800-19 | Integrated MVP and acceptance testing | Quality | All members | 2026-10-20 | 2026-10-25 | 6 | To Do | 0% | MSE800-18 | bar: 18 Oct; 23 Oct to 27 Oct
MSE800-20 | Bug fixes and regression testing | Quality | All members | 2026-10-23 | 2026-10-27 | 5 | To Do | 0% | MSE800-19 | bar: 18 Oct; 24 Oct to 27 Oct
MSE800-21 | Documentation, user guide and demo slides | Delivery | All members | 2026-10-24 | 2026-10-28 | 5 | To Do | 0% | MSE800-19 | bar: 18 Oct; 24 Oct to 28 Oct
MSE800-22 | Final QA, retrospective and submission package | Delivery | All members | 2026-10-28 | 2026-10-28 | 1 | To Do | 0% | MSE800-20 | bar: 18 Oct; 24 Oct to 25 Oct; 28 Oct

## Jira Tasks
Issue Type | Summary | Description | Priority | Assignee (suggested) | Start date | Due date | Labels | Epic Name / Workstream | External ID | Depends on | Status
Task | Project schedule and milestones | MSE800 v0.1 schedule; proposed owner: Leon. Deliverable/evidence to be confirmed in Jira. | High | Leon | 2026-10-10 | 2026-10-12 | mse800,agile | Planning | MSE800-01 |  | To Do
Task | Coding standards document | MSE800 v0.1 schedule; proposed owner: Michael. Deliverable/evidence to be confirmed in Jira. | High | Michael | 2026-10-10 | 2026-10-13 | mse800,agile | Technical Setup | MSE800-02 | MSE800-01 | To Do
Task | Code management / GitHub rules | MSE800 v0.1 schedule; proposed owner: Michael. Deliverable/evidence to be confirmed in Jira. | High | Michael | 2026-10-10 | 2026-10-13 | mse800,agile | Technical Setup | MSE800-03 | MSE800-02 | To Do
Task | Requirements outline & interview report | MSE800 v0.1 schedule; proposed owner: Sandyha / Pei. Deliverable/evidence to be confirmed in Jira. | High | Sandyha / Pei | 2026-10-10 | 2026-10-13 | mse800,agile | Requirements | MSE800-04 |  | To Do
Task | MVP scope and exclusions | MSE800 v0.1 schedule; proposed owner: All members. Deliverable/evidence to be confirmed in Jira. | High | All members | 2026-10-10 | 2026-10-12 | mse800,agile | Planning | MSE800-05 | MSE800-01 | To Do
Task | Jira board and prioritised backlog | MSE800 v0.1 schedule; proposed owner: Leon. Deliverable/evidence to be confirmed in Jira. | High | Leon | 2026-10-11 | 2026-10-12 | mse800,agile | Planning | MSE800-06 | MSE800-05 | To Do
Task | Technical stack decision record | MSE800 v0.1 schedule; proposed owner: Michael / Leon. Deliverable/evidence to be confirmed in Jira. | High | Michael / Leon | 2026-10-11 | 2026-10-13 | mse800,agile | Technical Setup | MSE800-07 | MSE800-05 | To Do
Task | GitHub repository setup | MSE800 v0.1 schedule; proposed owner: Michael. Deliverable/evidence to be confirmed in Jira. | High | Michael | 2026-10-12 | 2026-10-13 | mse800,agile | Technical Setup | MSE800-08 | MSE800-07 | To Do
Task | Requirements analysis and user stories | MSE800 v0.1 schedule; proposed owner: Sandyha / Pei. Deliverable/evidence to be confirmed in Jira. | High | Sandyha / Pei | 2026-10-11 | 2026-10-14 | mse800,agile | Requirements | MSE800-09 | MSE800-07 | To Do
Task | Architecture, UI/API and data model design | MSE800 v0.1 schedule; proposed owner: Michael / Leon. Deliverable/evidence to be confirmed in Jira. | High | Michael / Leon | 2026-10-13 | 2026-10-15 | mse800,agile | Technical Setup | MSE800-10 | MSE800-03 | To Do
Task | Core feature development — Leon | MSE800 v0.1 schedule; proposed owner: Leon. Deliverable/evidence to be confirmed in Jira. | High | Leon | 2026-10-14 | 2026-10-22 | mse800,agile | Development | MSE800-11 | MSE800-03 | To Do
Task | Core feature development — Michael | MSE800 v0.1 schedule; proposed owner: Michael. Deliverable/evidence to be confirmed in Jira. | High | Michael | 2026-10-14 | 2026-10-22 | mse800,agile | Development | MSE800-12 | MSE800-08 | To Do
Task | Core feature development — Sandyha | MSE800 v0.1 schedule; proposed owner: Sandyha. Deliverable/evidence to be confirmed in Jira. | High | Sandyha | 2026-10-14 | 2026-10-22 | mse800,agile | Development | MSE800-13 | MSE800-12 | To Do
Task | Core feature development — Pei | MSE800 v0.1 schedule; proposed owner: Pei. Deliverable/evidence to be confirmed in Jira. | High | Pei | 2026-10-14 | 2026-10-22 | mse800,agile | Development | MSE800-14 | MSE800-09 | To Do
Task | Requirements changes and backlog updates | MSE800 v0.1 schedule; proposed owner: Leon / Sandyha / Pei. Deliverable/evidence to be confirmed in Jira. | High | Leon / Sandyha / Pei | 2026-10-14 | 2026-10-25 | mse800,agile | Requirements | MSE800-15 | MSE800-03 | To Do
Task | Code review, pull requests and integration | MSE800 v0.1 schedule; proposed owner: Michael / Developers. Deliverable/evidence to be confirmed in Jira. | High | Michael / Developers | 2026-10-16 | 2026-10-25 | mse800,agile | Quality | MSE800-16 | MSE800-06 | To Do
Task | Unit tests and test results | MSE800 v0.1 schedule; proposed owner: All members. Deliverable/evidence to be confirmed in Jira. | High | All members | 2026-10-18 | 2026-10-26 | mse800,agile | Quality | MSE800-17 | MSE800-11 | To Do
Task | First working demo and Sprint 1 review | MSE800 v0.1 schedule; proposed owner: All members. Deliverable/evidence to be confirmed in Jira. | High | All members | 2026-10-19 | 2026-10-19 | mse800,agile | Agile | MSE800-18 | MSE800-14 | To Do
Task | Integrated MVP and acceptance testing | MSE800 v0.1 schedule; proposed owner: All members. Deliverable/evidence to be confirmed in Jira. | High | All members | 2026-10-20 | 2026-10-25 | mse800,agile | Quality | MSE800-19 | MSE800-18 | To Do
Task | Bug fixes and regression testing | MSE800 v0.1 schedule; proposed owner: All members. Deliverable/evidence to be confirmed in Jira. | High | All members | 2026-10-23 | 2026-10-27 | mse800,agile | Quality | MSE800-20 | MSE800-03 | To Do
Task | Documentation, user guide and demo slides | MSE800 v0.1 schedule; proposed owner: All members. Deliverable/evidence to be confirmed in Jira. | High | All members | 2026-10-24 | 2026-10-28 | mse800,agile | Delivery | MSE800-21 | MSE800-12 | To Do
Task | Final QA, retrospective and submission package | MSE800 v0.1 schedule; proposed owner: All members. Deliverable/evidence to be confirmed in Jira. | High | All members | 2026-10-28 | 2026-10-28 | mse800,agile | Delivery | MSE800-22 | MSE800-19 | To Do

## Guide
Project planning notes
Planning assumption | Draft plan; task ownership and scope should be confirmed by the team.
Jira | Jira is proposed, not yet confirmed. Import Jira Tasks after setting up the project.
Assignee field | Suggested names may not match Jira account IDs; map or leave unassigned during import.
Dependency field | External IDs are planning references; Jira issue links must be configured after import.
Progress | Update Progress and Status in the Gantt sheet manually as work advances.
Agile cadence | Daily async updates before 7 PM; at least two online meetings each week.
Feature freeze | 22 October 2026; limit subsequent changes to essential fixes.
Internal completion | 28 October 2026, ahead of 29 October deadline.
Cultural requirements | Include Māori perspectives and relevant cultural considerations in acceptance criteria.
Team | Leon, Michael, Sandyha, Pei (proposed role assignments).
Date discrepancy | Section 2A says first four documents before 12 Oct; Section 2B specifies 12–13 Oct. This chart follows Section 2B.
Phase deliverables | Sprint 0: MVP, backlog, technical decision, repository and draft architecture. Sprint 1: core modules, PRs, unit tests and demo. Sprint 2: integrated MVP, test reports, defect and change logs. Final: regression summary, guides, slides and package.